## All activities export 1
Annual Report on the Implementation of the 2024 Action Plan for the: |  |  |  |  | ACTION PLAN FOR THE PERIOD 2021- 2025 FOR THE IMPLEMENTATION OF THE PUBLIC ADMINISTRATION REFORM STRATEGY IN THE REPUBLIC OF SERBIA FOR THE PERIOD 2021 - 2030
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | Public Administration Reform Strategy in the Republic of Serbia for the period 2021−2030
Overall objective 1: FURTHER IMPROVEMENT OF THE WORK OF PUBLIC ADMINISTRATION AND THE QUALITY OF PUBLIC POLICY DEVELOPMENT IN ACCORDANCE WITH THE EUROPEAN PRINCIPLES OF PUBLIC ADMINISTRATION, ENSURING HIGH QUALITY SERVICES TO CITIZENS AND BUSINESS ENTITIES, AND A PROFESSIONAL PUBLIC ADMINISTRATION WHICH WILL SIGNIFICANTLY CONTRIBUTE TO THE ECONOMIC STABILITY AND THE IMPROVEMENT OF THE LIVING STANDARD
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Government Effectiveness (percentile ranking (from 0 to 100)) |  |  | 53.37 (2019) |  | 57- 60 | 51.89 | The value was measured in 2024, and refers to 2023 according to the World Bank methodology. https://databank.worldbank.org/source/worldwide-governance-indicators/Series/GE.EST
Level of satisfaction of citizens and businesses with the services delivered by public administration (Number) |  |  | 4 (2020) |  | 6.5 | - | The Balkan Barometer does not measure 4 of the five indicators that make up this composite indicator in 2024, thus it is not possible to measure the value for 2024.
.
Specific objective 1.1: IMPROVED QUALITY OF PUBLIC POLICY DOCUMENTS AND REGULATIONS
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Regulatory quality indicator – World Bank ranking (Number) |  |  | 60.1 (2019) |  | 64 | 56.6 | The indicator value is for 2023. There are still no values for 2024.
Indicator of alignment and quality of policy planning (Scale (1–5)) - |  |  | 0 (2021) |  | 4 | 4 | /
.
Measure 1.1.1: SPECIFIC OBJECTIVE 1 of the Public Policy Management and Regulatory Reform Advancement Programme — REGULATORY REFORM AIMED AT IMPROVING THE BUSINESS ENVIRONMENT AND REDUCING UNNECESSARY BURDEN ON CITIZENS AND BUSINESSES
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The share of adopted laws containing complete impact assessments in the total number of adopted laws requiring impact assessments, per calendar year (%) |  |  | 30.4 (2020) |  | 50 | 31.1 | In 2024, the National Parliament did not pass laws in the first two quarters, so laws were prepared and passed in a short period of time, which affected the value of the performance indicator.
The share of adopted regulations containing complete impact assessments in the total number of adopted regulations requiring impact assessments, per calendar year (%) |  |  | 58.3 (2020) |  | 62 | 77.6
.
.
Measure 1.1.2: SPECIFIC OBJECTIVE 2 of the Public Policy Management and Regulatory Reform Advancement Programme - STRENGTHENING CAPACITY AND IMPLEMENTING TOOLS FOR QUALITY DEVELOPMENT AND MONITORING OF THE IMPLEMENTATION OF PUBLIC POLICIES AND REGULATIONS
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The share of adopted PPDs within a single calendar year, containing complete impact assessments, in the total number of adopted PPDs requiring impact assessments (%) |  |  | 50 (2020) |  | 90 | 50 | Of the total of 14 adopted public policy documents (PPDs) by the Government in 2024, 6 PPDs required an impact assessment. Of these 6 PPDs in total, 3 PPDs had a full impact assessment (50%), while 3 PPDs had a partial impact assessment (50%).
.
.
Measure 1.1.3: SPECIFIC OBJECTIVE 3 of the Public Policy Management and Regulatory Reform Advancement Programme — EFFECTIVE PUBLIC POLICY COORDINATION
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The total number of planning areas with a revised and optimised planning framework (a clear hierarchical structure of PPDs established within planning areas) (Number) |  |  | 1 (2020) |  | 12 | 4 | The following areas had been optimised: public administration, education, public information and youth.
.
.
Measure 1.1.4: SPECIFIC OBJECTIVE 4 of the Public Policy Management and Regulatory Reform Advancement Programme — INCREASED INVOLVEMENT OF CIVIL SOCIETY, BUSINESSES AND OTHER STAKEHOLDERS IN THE EARLY STAGES OF THE DEVELOPMENT OF PUBLIC POLICIES AND REGULATIONS AND IN MONITORING THEIR IMPACTS
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The share of adopted PPDs, during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted PPDs in a calendar year (%) |  |  | 100 (2020) |  | 100 | 100 | Of the total of 14 adopted lPPDs by the Government for which consultations were required, consultations were conducted for all 14 PPDs in 2024.
The share of adopted laws during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted laws in a calendar year (%) |  |  | 35.71 (2020) |  | 71.25- 75 | 58.3 | In 2024, the National Parliament did not pass laws in the first two quarters, so laws were prepared and passed in a short period of time, which affected the value of the performance indicator. After the drop in 2022 (29%), the value of the indicator has been increasing for the last two years (52.9% and 58.3%).
The share of adopted regulations during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted regulations in a calendar year (%) |  |  | 11.46 (2020) |  | 29.45- 31 | 29.7
.
.
Specific objective 1.2: AN IMPROVED RECRUITMENT PROCESS IN PUBLIC ADMINISTRATION
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Meritocracy and effectiveness of recruitment of civil servants (SIGMA principle) (Number) |  |  | 3 (2019) |  | 4 | - | Since this is an indicator monitored in SIGMA reports, and that for the preparation of the 2024 Report, there was a change in the SIGMA methodology for collecting data and changes to the indicators themselves, it cannot be determined with certainty whether the aforementioned indicator has been achieved.
.
Measure 1.2.1: Improvement of personnel planning and promoting state administration as a desirable employer
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Recruitment based on stated personnel needs of bodies (%) |  |  | 0 (2019) |  | 35- 40 | 12.82 | A deviation from the target value occurred due to the failure to adopt the 2024 Personnel Plan for ministries, special organisations, Government agencies and expert services of administrative districts, which would have allowed for all rulebooks on internal organisation and systematisation of job positions to be aligned with the adopted Personnel Plan/approved budgetary resources in 2024. Another reason for the deviation is the fact that during 2024, the Committee for approvals of new recruitments and additional hirings by public funds beneficiaries was granting approvals for filling employees positions, successively during 2024, in accordance with in accordance with the additional funds provided from the current budget reserve. The values used in the formula for calculating the percentage of persons who have been recruited for these job positions compared to the total number of persons who are to be recruited, are based on the number of systematised positions in applicable rulebooks which were approved by the Government of the Republic of Serbia by 31 December, 2024, monthly records of the number and structure of employees in these bodies on 31 December, 2023, and data on the influx of civil servants in 2024.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.1.1: Analysing the application of the existing personnel planning framework in state bodies and issuing recommendations for improvement, including a proposal to recruit personnel to work in priority-areas | Q3 2021 | MPALSG |  | - | ..
1.2.1.2: Reviewing the principles of internal organisation and management in state administration bodies with the aim of more efficient personnel planning | Q3 2022 | MPALSG |  | - | ..
1.2.1.3: Innovating the methodology for personnel planning in accordance with the recommendations from the previous activity | Q3 2022 | MPALSG |  | - | ..
1.2.1.4: Preparation and implementation of training for employees in the HRMS and HR units for the implementation of the new methodology for personnel planning | Q4 2023 | NAPA | Completed | - | ..
1.2.1.5: Development of a personnel plan for state administration bodies for 2024 in accordance with the innovative methodology for personnel planning | Q4 2023 | HRMS | Not commenced | - | This activity was reported in the previous reporting period...
1.2.1.6: Development of a communication plan for promotional activities aimed at presenting the state administration as an employer. Organisation of promotional activities envisaged by the communication plan aimed at presenting the state administration as a preferred employer. | Q4 2025 | HRMS | In progress | - | In order to promote the state administration as a desirable employer, in 2024 the Service presented 3 state administration bodies to the public, activities were initiated for 3 more bodies, and announcements and promotions of the competition procedure for 7 bodies were made. Benefits and other aspects of working in the state administration are promoted through social networks and the Service's blog. A calculator for calculating salaries in the state administration was developed and published. An international conference was organised with a focus on the exchange of systems in terms of attracting talented persons to the state administration...
1.2.1.7: Attracting appropriate profiles (students) to work in the state administration through student internship by promoting mechanisms of cooperation with higher education institutions | Q4 2025 | HRMS | In progress | 119.8% | The Service has concluded 2 cooperation agreements with higher education institutions in the form of attracting students to work in state administration. Student internship in the Service has been provided for 15 students. Social networks are actively used for this purpose...
1.2.1.8: Preparation of a training programme regarding the competition procedure in state administration, for students conducting the student internship | Q4 2022 | NAPA | Completed | - | https://napa.gov.rs/tekst/5403/drugi-programi-obuka-naju.php..
1.2.1.9: Support to local self-government units in the personnel planning process | Q2 2022 | MPALSG |  | - | ..
.
Measure 1.2.2: Improvement of the selection process and the process of introduction of new employees
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Extent to which the competency framework matches the public administration needs and core values (Number) |  |  | 1 (2020) |  | 3 | 2 | The Ministry of Public Administration and Local Self-Government has begun work on improving the competency framework for civil servants within the framework of the Project "Integrated Human Resources Management in Public Administration of the Republic of Serbia". The HRMS has developed a Proposal for a New Competency Framework for Senior Civil Servants
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.1: Improving tools for assessing competencies, especially those for remote testing, and supporting competition committees in the application of modern technologies for e-recruitment | Q 2023 -> Q4 2025 | HRMS | In progress | - | The improvement is partly achieved through the ongoing battery of psychological tests that are used and adapted in live checks (no new measuring instruments have been purchased). The implementation of the selection procedure in certain phases is held online, and the commissions are supported in using various platforms both for checking specific functional competencies and for final interviews, in order to make the competition procedure more economical and expedited. A certain number of authorities support the submission of applications electronically, while the review of applications is often conducted online. The authority obtains documents from official records for candidates participating in the selection procedure electronically via E-Government. The Service has opened 5 testing centres for the dislocated assessment of candidates' competencies in the selection procedure, more easily accessible to citizens outside Belgrade (in the cities of Novi Sad, Čačak, Niš, Kraljevo and Zaječar)...
1.2.2.2: Preparing a quality analysis of filling the work positions in competition procedures in state administration bodies and monitoring the implementation of measures to improve the procedures for filling the work positions | Q4 2023 | HRMS |  | - | ..
1.2.2.3: Ex post analysis of laws and by-laws on the procedure and manner of conducting competition procedures in state administration bodies and preparation of proposals for improving the regulatory framework | Q4 2024 -> Q4 2025 | MPALSG | Not commenced | - | In February 2025, the implementation of the complementary support contract financed from the CBC IPA 2022 funds will begin, through which the data analysis will be carried out...
1.2.2.4: Developing and implementing an online training programme for members of the competition commission and personnel units for the application of modern selection methods | Q4 2025 | NAPA | In progress | - | In 2024, 3 online training sessions were available, Methods and Techniques of Personnel Selection, completed by 17 participants, Modern Concept of Human Resources Management in Local Self-Government Units, completed by 13 participants, and Regulations and Procedures in the Field of Employment of Civil Servants, completed by 29 participants...
1.2.2.5: Preparing a comparative legal analysis on centralised employment of trainees in state administration, with a proposal for a model that is optimal for the state administration of the Republic of Serbia | Q4 2023 -> Q4 2025 | MPALSG | Not commenced | - | In September 2023, the implementation of the project "Integrated Human Resources Management in Public Administration of the Republic of Serbia" began, which, with the support of the EU Delegation, is being implemented by the Ministry of Public Administration and Local Self-Government - Human Resources Management Sector, in cooperation with the Personnel Management Service of the Government of the Republic of Serbia. The project, among other things, also envisages the development of career models as well as the creation of new and improved solutions for human resources management. Through proposals for the introduction of career management modalities, a number of modern instruments will be included at the institutional and individual levels... |  | Considering all the activities envisaged by the Project, as well as limited funds, it will not be possible to implement the aforementioned activity through the aforementioned Project. | Finding donor support for the preparation of the aforementioned analysis.
1.2.2.6: Designing an introductory training programme for work in state administration for trainees, recruits on a probation period and persons starting their employment in state administration who are not on probation period | Q4 2021 | NAPA | Completed | - | ..
1.2.2.7: Analysing the relationship between the examination of general and specific functional competencies in the recruitment process, the state professional exam and introductory training for work in the state administration and a proposal for measures to eliminate multiple examinations of the those competencies in different phases of the employment relationship | Q4 2023 -> Q4 2025 | MPALSG | Not commenced | - | In February 2025, the implementation of the complementary support contract financed from the CBC IPA 2022 funds will begin, through which the data analysis will be carried out...
1.2.2.8: Drafting a Competency Framework for Employees in Bodies of Autonomous Provinces and LSGs to include a map for integration into the HRM | Q2 2021 | MPALSG |  | - | ..
1.2.2.9: Amendment to the regulatory framework for employees in AP and LSG bodies in order to integrate the competency framework | Q3 2023 | MPALSG |  | - | ..
1.2.2.10: Developing and implementing training for employees in personnel units and managers in AP and LSG bodies for the implementation of the Competency Framework | Q4 2025 | NAPA | In progress | - | 46 training courses financed from the regular budget were implemented and attended by 1066 participants...
.
Measure 1.2.3: Improvement of the procedure for merit-based filling of work positions and induction to work
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of senior civil service positions filled in accordance with the competency framework, compared to the total number of positions (%) |  |  | 34 (2020) |  | 85.5- 90 | 40 | The lower percentage of senior civil servants than the target value can be explained by the fact that in the period from November 2023 to May 2024, the Government was in a technical mandate and did not have the authority to appoint senior civil servants following a completed competition, and that a new Government was formed, which resulted in the transfer of persons from one body to another, the adoption of new regulations on internal organisation and job classification.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.3.1: Preparing analysis of the legislative framework regulating the procedure and authority for the appointment of an acting officer and proposals for improvement measures | Q4 2022 -> Q4 2025 | MPALSG | In progress | - | After the establishment of the new Government in May 2024, the new Minister of Public Administration and Local Self-Government established a new Special Working Group for Monitoring the Status and Proposing Measures Regarding the Management of Senior Civil Servants. The institutions the representatives of which participate in the work of the working group have not changed compared to the previous group, so the working group continues to consist of representatives of the MPALSG, the Office of the Prime Minister, the High Civil Service Council, the General Secretariat, SORS, HRMS, NAPA, the Ministry of Justice, the General Secretariat of the National Parliament and the General Secretariat of the President of the Republic. The members of the working group have been changed only in those institutions where there have been personnel changes in management. The operation of the working group is chaired and managed by the Minister of Public Administration. We would like to point out that the continuity with the previous period of work on this topic has not been interrupted, for the most part not even in terms of personnel solutions, but the analytical foundations for the operation of the working group and the previous findings from the previous period have also been presented as a basis for its further work. Therefore, the task of the working group has not changed compared to the previous one, i.e. it is expected to continue communication between key institutions on issues related to the implementation of competitions and the appointment of senior civil servants, to monitor the situation regarding the filling of work positions and the appointment of acting officers, and to make proposals that can contribute to the quantitative and qualitative improvement of the situation and coordination regarding work positions... |  |  | The Special Working Group will continue its work, which should result in the specification and harmonisation of proposals for further directions of system development.
1.2.3.2: Amending the regulatory framework in the area of ​​appointment of acting officers in accordance with the proposal for improvement measures | Q4 2022 -> Q4 2025 | MPALSG | Not commenced | - | Implementation report has been provided within the activity 1.2.3.1...
1.2.3.3: Creating a mechanism of cooperation between institutions responsible for the senior civil servants management policy | Q2 2021 -> Q1 2023 | HRMS |  | - | ..
1.2.3.4: Developing guidelines for improving job classification legal documents in the section on job descriptions and required competencies for senior civil servants | Q4 2022 -> Q4 2023 -> Q4 2024 -> Q4 2025 | HRMS | In progress | - | The implementation of this activity is ongoing and can be linked to the implementation of activities 2.3.1 and 3.3.1. During 2023, the HRMS prepared an improved draft job description for senior civil servants and a proposal for two models of a new competency framework for senior civil servants, which were submitted to the Special Working Group for Monitoring the Status and Proposing Measures Regarding the Management of Senior Civil Servants... |  | Given that this activity is connected to the implementation of activities 2.3.1 and 3.3.1, which are ongoing, this activity will be implemented only after the completion of the implementation of the aforementioned activities. | After the implementation of activity 2.3.1. Preparing analysis of the legislative framework regulating the procedure and authority for the appointment of an acting officer and proposals for improvement measures for activity 3.3.1. The development of a strategic document on the management of senior civil servants in state administration bodies with a roadmap for integration into regulations will make it possible to implement this activity.
1.2.3.5: Innovating the competency framework for senior civil servants | Q4 2022 -> Q4 2023 | HRMS |  | - | ..
1.2.3.6: Improving the training programme for senior civil servants and determining its effects in accordance with the newly developed Competency Framework for Senior Civil Servants | Q4 2023 | NAPA | Completed | - | ..
1.2.3.7: Building the capacity of the High Civil Service Council to implement the competency-based selection process for senior civil servants, through continuous training and support in the application of modern selection methods | Q 2024 -> Q4 2025 | HRMS |  | - | ..
.
Specific objective 1.3: AN EFFICIENT CAREER MANAGEMENT SYSTEM APPLIED IN PRACTICE
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Degree to which the career management system for the senior civil servants is developed (Number) |  |  | 1 (2020) |  | 3 | 4 | The HRMS has developed and uses various career tools for a large number of civil servants ahead of schedule. (Over 900 civil servants in 2024). The development of comprehensive systemic career models that will be universally applicable in state administration bodies is underway. The IPA project is funded by the European Union and is called "Integrated Human Resources Management in the Public Administration of the Republic of Serbia", which started in the 4th quarter of 2023)
.
Measure 1.3.1: Developing an environment for an efficient, innovative and motivated civil servant
Institution in charge: HUMAN RESOURCES MANAGEMENT SERVICE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The distribution of performance evaluation outcomes corresponds to HRM standards (%) |  |  | 75 (2020) |  | 57.75- 50 | 74 | The number of civil servants in state administration bodies with the highest grades is higher than planned because the heads of the bodies made such a decision.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.1: Developing and implementing tools for career development of managers within the Career Development Centre (360 degrees, competency passport, coaching, etc.) and human resources units of the authorities | Q4 2023 | HRMS |  | - | ..
1.3.1.2: Preparing a study on possible career models in state administration with recommendations for the implementation and development of career models in accordance with the analysis and integration into regulations | Q4 2023 -> Q4 2025 | HRMS | In progress | 100% | A study on possible career models in state administration with recommendations for implementation is being prepared within the framework of the IPA project "Integrated Human Resources Management in the Public Administration of the Republic of Serbia", supported by the EU, which started in the 4th quarter of 2023 and is still ongoing. The Human Resources Management Service is the beneficiary of the project, together with the main beneficiary, the Ministry of Public Administration and Local Self-Government... |  | The project started only at the beginning of the 4th quarter of 2023, and it includes several interdependent areas of human resources management that are being improved, of which this activity is one.. | Project implementation in accordance with the roadmap.
1.3.1.3: Establishing a talent management system (from identification, working with them to the rules of movement during service, organising special training for them) and integration into regulations | Q4 2025 | HRMS | In progress | - | A study on the system of talent management in state administration with recommendations for implementation is being prepared within the framework of the IPA project "Integrated Human Resources Management in the Public Administration of the Republic of Serbia", supported by the EU, which started in the 4th quarter of 2023 and is still ongoing. The Human Resources Management Service is the beneficiary of the project, together with the main beneficiary, the Ministry of Public Administration and Local Self-Government... |  | The project started only at the beginning of the 4th quarter of 2023, and it includes several interdependent areas of human resources management that are being improved, of which this activity is one.. | Project implementation in accordance with the roadmap.
1.3.1.4: Preparing a study on models of employee engagement outside the employer's premises (working from home or remote work) with a proposal for the possibility of their introduction into the work of state administration bodies of the Republic of Serbia | Q2 2021 | MPALSG |  | - | ..
1.3.1.5: Preparing a comparative analysis of models of engagement of civil servants in international projects and finding their role in the EU accession process with a proposal of a model for the state administration of the Republic of Serbia, as well as an analysis of internship of civil servants in related institutions of EU member states and EU institutions | Q3 2022 | MPALSG |  | - | ..
1.3.1.6: Preparing a draft law regulating the salaries of civil servants and employees in accordance with the systemic law on salaries | Q4 2024 | MPALSG | The idea was abandoned | - | During 2024, a working version of the Draft Law on Salaries of Civil Servants and Employees was prepared, which was harmonised with the basic principles and criteria, i.e. the provisions of the Law on Salaries System of Public Sector Employees. However, at the end of 2024, the Government of the Republic of Serbia decided to repeal the new salary system, established by the normative framework, namely the Law on the Salaries System of Public Sector Employees, the Law on Salaries of Civil Servants and Employees in Bodies of an Autonomous Province and a Local Self-Government Unit, the Law on Employees in Public Services and the Law on Salaries of Employees in Public Agencies and Other Organisations Established by the Republic of Serbia, an Autonomous Province or a Local Self-Government Unit, which was conditioned by the need to consider the possibilities for reforming the salaries system in the public sector on a different basis, given the numerous changes in the salaries system in the previous period. Numerous social circumstances (the COVID-19 pandemic in the territory of the Republic of Serbia, fiscal consolidation, the increase in public sector salaries from the gradual "unfreezing of salaries" to their uneven growth, a significant increase in the minimum wage) have had a significant impact on the relations established by the new salaries system, which has led to the need to reconsider key provisions in the systemic law, in order to take into account the changes in salaries and ensure that the expected reform processes take place in accordance with budgetary possibilities and projections of salaries growth in the coming period. All of the abovementioned has necessitated the implementation of a new analytical process for the public sector salaries system, which is also supported by the new arrangement that the Republic of Serbia reached with the International Monetary Fund (IMF), which will provide support for the new analytical process for regulating the public sector salaries system, taking into account all circumstances relevant to planning the future reform of the public sector salaries system. Given all the facts, the need to harmonise the provisions of the Law on Salaries of Civil Servants and Employees with the systemic law on salaries has ceased to exist with the aforementioned Government decision. In the coming period, a new dynamic for the implementation of measures and activities in the preparation of the new Law on Salaries of Civil Servants and Employees will be established...
1.3.1.7: Implementing the public sector salaries system reform | Q4 2025 | MPALSG | The idea was abandoned | - | For all the reasons stated in the progress report referred to in point 1.3.1.6, we are of the opinion that the implementation of the public sector salaries system reform will not be possible during 2025, i.e. that additional deadlines will be set for the establishment of a new regulatory framework for the public sector salaries system...
1.3.1.8: Analysing the effects of the proposed measures for staff retention and prevention of their outflow and proposals for improvement | Q4 2023 | HRMS |  | - | ..
1.3.1.9: Developing the guidelines and recommendations to state administration bodies for improving the quality of performance evaluation of civil servants | Q2 2022 | HRMS |  | - | ..
1.3.1.10: Preparing the ex post analysis of laws and by-laws on performance evaluation and preparation of proposals for improvement measures | Q1 2025 | MPALSG | Not commenced | - | In February 2025, the implementation of the complementary support contract financed from the CBC IPA 2022 funds will begin, through which the data analysis will be carried out...
1.3.1.11: Preparing an analysis of the HRM function in public agencies with proposals for improvement | Q4 2022 | MPALSG |  | - | ..
1.3.1.12: Further development of the competency framework for all categories of civil servants | Q4 2023 | HRMS | In progress | 100% | Further development of the competency framework for all categories of civil servants is being developed within the framework of the IPA project "Integrated Human Resources Management in the Public Administration of the Republic of Serbia", supported by the EU, which started in the 4th quarter of 2023 and is still ongoing. The Human Resources Management Service is the beneficiary of the project, together with the main beneficiary, the Ministry of Public Administration and Local Self-Government... |  | The project started only at the beginning of the 4th quarter of 2023, and it includes several interdependent areas of human resources management that are being improved, of which this activity is one.. | Project implementation in accordance with the roadmap.
1.3.1.13: Preparing a comparative analysis of measures taken by EU member states to create conditions for civil servants to be initiators of change and innovation in public administration | Q4 2025 | MPALSG |  | - | ..
1.3.1.14: Support for the implementation of the Competency Framework for the functions of the HRM in AP and LSGU | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.3.2: Development of institutional and administrative capacities for human resources management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Degree to which the organisation of personnel affairs in state administration bodies has been standardised, and quality of personnel affairs (Number) |  |  | 0 (2020) |  | 3 | - | The indicator was not measured for 2024 due to delays in the implementation of the new Information System from which data for determining the indicator value would be generated.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.1: Establishing and developing the Human Resources Management Information System in state bodies and in AP and LSG bodies and its connection with other information systems in which data on employees in state bodies is collected (Treasury, CROSO, Tax Administration, etc.) | Q4 2025 | HRMS | In progress | 100% | The Human Resources Management Service has begun providing support to state administration bodies and government services for entering data into the information system and the entry continues. (In February 2025, 60% of data on organisational charts and job positions of bodies was entered). During 2024, training of employees in personnel units for the use of IS began, based on the training plan prepared by the Service. In terms of IS development, the 3rd phase of IS improvement was implemented during 2024, which covers the appeal procedure, as well as the drafting of acts from the labour and legal relations. |  |  | Activities are underway to merge the HRMIS information system with CROSO, NAPA and consider options for merging with the ISKRA system. Further training of employees in personnel units in the use of IS will continue.
1.3.2.2: Preparing an action plan for building the capacities of personnel units in state administration bodies and implementing activities envisaged by the AP | Q4 2021 | MPALSG |  | - | ..
1.3.2.3: Developing competence-based training for managers and personnel units | Q4 2021 | NAPA | Completed | - | ..
1.3.2.4: Preparing an analysis on the application of quality standards in the field of HRM for state administration bodies and establishing a unit in the MPALSG/HRMS for quality management in the field of HRM | Q4 2025 | HRMS |  | - | ..
1.3.2.5: Analysing the organisation of the HRM function in the state administration bodies and defining directions for future development in accordance with modern HRM forms | Q4 2023 | MPALSG |  | - | ..
1.3.2.6: Analysing the organisation of the HRM function in AP and LSG bodies and defining directions for future development in accordance with modern HRM forms | Q4 2022 -> Q4 2023 -> Q4 2025 | MPALSG | Not commenced | - | The activity has not yet been implemented... |  |  | Support for the implementation of this activity is expected from the Council of Europe through the continuation of the project "Human Resources Management in Local Self-Government" - Phase III, which is financed by the EU from IPA funds and co-financed by the CoE.
.
Measure 1.3.3: Strengthening the professionalisation of senior civil servants/managers
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Extent to which legal protection is provided to senior civil servants/managers (based on five SIGMA sub-indicators) (Number) |  |  | 9 (2019) |  | 13 | - | Based on the 2024 Sigma report, it was established that two out of five SIGMA indicators (according to the old methodology) were assessed. More specifically: Categorical specificity and coverage of the system of senior civil servants: 8/11 and Stability of senior civil servants 11/20.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.1: Developing a strategic document on the management of senior civil servants in state administration bodies with a roadmap for integration into regulations. | Q4 2022 -> Q4 2025 | MPALSG | In progress | - | Implementation report has been provided within the activity 1.2.3.1
1.3.3.2: Implementing the policy on the management of senior civil servants into the regulatory framework | Q4 2025 | MPALSG |  | - | ..
1.3.3.3: Establishing performance indicators in meeting annual objectives for senior civil servants in the performance evaluation process | Q4 2021 | MPALSG |  | - | ..
1.3.3.4: Establishing appropriate networks of senior civil servants for the purpose of exchanging experience | Q4 2022 -> Q4 2023 | HRMS |  | - | ..
1.3.3.5: Supporting the professional development of senior civil servants through the activities of the Career Management Centre (application of various career development tools) | Q4 2025 | HRMS | In progress | - | The Career Management Centre of the Human Resources Management Service continuously provides support to senior civil servants in the area of ​​identifying career and development needs and achieving their goals. During 2024, 45 senior civil servants used various services of the Centre, using various tools...
1.3.3.6: Developing continuous training programmes for managers and senior civil servants in accordance with competencies | Q4 2025 | NAPA | In progress | - | During 2024, a new cycle of development of the Training Programme for Managers in Local Self-Government Units for 2024 was implemented. Taking into account the specific functional competencies for the field of work management and the behavioural competencies "Human Resources Management" and "Strategic Management", two programme units of this Programme were drafted. The first programme unit comprises training programmes intended for officials and senior civil servants in LSGUs, officers assigned to positions of managers of organisational units in the city, municipal administration or city municipality administration and officers preparing for assignment to positions of managers in LSGUs. On the other hand, the second programme unit is intended exclusively for officials and senior civil servants in LSGUs. The draft training programme was submitted to the Council for Professional Development of Employees in the LSGUs for its opinion on 27 September, 2023. At the proposal of the National Academy of Public Administration, the Government, at its session held on 14 December, 2023, adopted the Training Programme for Managers in LSGUs...
.
Specific objective 1.4: A FUNCTIONAL AND INNOVATIVE SYSTEM OF PROFESSIONAL DEVELOPMENT AND PROFESSIONAL EXAMS IN PUBLIC ADMINISTRATION BASED ON THE ANALYSIS OF NEEDS FOR THE IMPROVEMENT OF EMPLOYEES' COMPETENCIES, KNOWLEDGE, SKILLS AND ABILITIES DEVELOPED AND IMPLEMENTED
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
The extent to which the system of professional development in public administration is normatively and in practice based on an analysis of the needs for improving the knowledge and skills, i.e. the abilities of public administration employees (Number) |  |  | 1 (2019) |  | 4 | 4 | A consolidated report on the analysis of professional development needs has been prepared and published on the NAPA website.https://napa.gov.rs/tekst/605/analiza-potreba-za-strucnim-usavrsavanjem.php, усвојени програми су објављени на интернет страници НАЈУ https://napa.gov.rs/tekst/49/godisnji-programi-obuka-naju.php. The consolidated report also contains data on the number of institutions that have conducted needs analyses.
.
Measure 1.4.1: Improvement of a unified system of professional development in state bodies and bodies of local self-government units
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Degree of implementation of the quality system in elements of professional development in public administration (Number) |  |  | 1 (2020) |  | 5 | 5 | Information on the adopted special programmes is available on the NAPA website https://napa.gov.rs/tekst/61/lista-akreditovanih-programa.php
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.1: Improving the accreditation system and methods of engaging training programme implementers, as well as developing trainer competencies | Q4 2021 | NAPA | Completed | - | ..
1.4.1.2: Improving the system of evaluation of training programmes in state bodies and bodies of local self-government units and developing the knowledge and skills of participants in the evaluation process for its implementation | Q4 2021 | NAPA | Completed | - | ..
1.4.1.3: Developing a methodology for analysing and planning the costs of training programmes, as well as improving the knowledge and skills of civil servants and employees in LSGUs for their implementation | Q4 2021 | NAPA | Completed | - | ..
1.4.1.4: Developing instruments and methodology for conducting surveys of user satisfaction (citizens and other entities) with the work of public administration bodies in order to determine priority areas of professional development of civil servants and employees in local self-government units | Q4 2023 | NAPA | Completed | - | The methodology was developed within the project "Civil Service Training for the 21st Century in the Republic of Serbia" implemented by the United Nations Development Programme (UNDP) with the participation of the National Academy of Public Administration (NAPA) and the Political Science Association of Serbia. The electronic version of the methodology is available athttps://napa.gov.rs/tekst/605/analiza-potreba-za-strucnim-usavrsavanjem.php..
1.4.1.5: Providing the participation of managers in the processes of a unified system of professional development, by improving the acts regulating the scope of work of internal units and job descriptions of managers of internal units in state bodies and bodies of local self-government units, by determining the tasks of participation in professional development processes | Q4 2021 | SAB (Public administration body) |  | - | ..
1.4.1.6: Improving the capacity of state bodies and local self-government units for the successful management and implementation of the process of a unified system of professional development in state bodies and local self-government units | Q4 2025 | NAPA | In progress | - | NAPA provides continuous support to public administration bodies (NAPA contact persons for training) in the processes of determining needs for professional development, developing and implementing training programmes, accrediting and engaging trainers, and evaluating training... |  |  | Continued support to public administration bodies..
.
Measure 1.4.2: Improvement of professional development programmes in state and LSGU bodies and of the manner of their organisation and delivery
Institution in charge: NATIONAL ACADEMY FOR PUBLIC ADMINISTRATION
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Fulfilment of participants’ expectations from training sessions where innovative forms and methods of professional development were applied (%) |  |  | 0 (2020) |  | 75 | 84.29
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.2.1: Developing innovative training programmes in state bodies and local self-government units, with the application of modern (unconventional) forms and methods of professional development, with special emphasis on the areas of innovation management, change management and crisis management | Q4 2023 | NAPA | Completed | - | In 2023, within the framework of the training programmes developed and implemented by NAPA, 47 training programmes in the field of innovation and public services were developed, as well as 65 in the field of digital transformation and data use. In addition, it is envisaged that each training programme can be implemented through a modernised training system: The modernised training system or blended learning involves the implementation of training in two phases: online training and consultations. The first phase takes place through online training when participants independently learn from prepared material (written and video lessons, presentations, infographs, tasks and exercises) along taking a test. The second phase involves consultation with a trainer (in the classroom or online) to apply knowledge in practice. In intensive direct communication with the training provider, participants recapitulate what they have learned, resolve their dilemmas, and receive practical advice on how to apply the knowledge acquired through online training in practice, as well as how to plan their activities to that end. During consultations, participants' knowledge and experience are systematised, corrected, expanded, and deepened. Upon completion of the training, participants will have continuous access to training materials (written and video lessons, presentations, infographs, tasks and exercises, a glossary of terms and FAQs) within the NAPA Infotheque. In 2023, 147 innovative programmes were implemented with 3,460 participants. During 2023, 64 training programmes were developed in the field of innovation and public services, as well as 76 in the field of digital transformation and data use, which are an integral part of the NAPA training programme for 2024. A special thematic area of ​​Innovation and the Digital Age was also developed, as well as Quality Management...
1.4.2.2: Developing training programmes tailored to the needs of trainees and persons who are being trained for independent work in the profession | Q4 2022 | NAPA | Completed | - | ..
1.4.2.3: Improving the application of innovative forms of professional development in state bodies and local self-government units (coaching, mentoring, study visits, etc.), with particular application in the professional development of managers | Q4 2023 | NAPA | Completed | - | Within the framework of the General Continuous Programme for the Professional Development for Civil Servants for 2023, the programme area ""Personal Development"" was developed, which includes the training courses Mentoring and Individual Coaching. During 2023, 10 participants completed the online training course - Individual Coaching, while another 21 participants started the same training. In addition, 9 senior civil servants completed the live training course - Individual Coaching. When it comes to developing the capacity of civil servants for the role of mentors, special training has been developed within the programme area ""Training of Trainers"": Mentor Training. During 2023, 9 participants completed the online training course - Mentor Training, while another 12 begun the same training. As part of the EU project "Strengthening the Professional Capacities of Senior Civil Servants", NAPA implemented coaching conversations with senior civil servants participating in the Training Programme for Managers in State Bodies. During 2023, a total of 7 senior civil servants attended coaching sessions (the project envisages that each interested SCS has from three to seven individual coaching sessions, depending on individual needs and the coaching plan established with their coach)...
1.4.2.4: Providing support to local self-government units in the process of identifying professional development needs, developing, preparing and implementing special training programmes in the local self-government unit and a unified plan for the annual professional development plan for local self- government units employees | Q4 2021 | NAPA | Completed | - | ..
1.4.2.5: Providing support to state bodies and local self-government units in the preparation and implementation of special training programmes using e-learning, in order to provide equal access to the right to professional development for a representative number of civil servants and employees in local self-government units | Q4 2025 | NAPA | In progress | - | The implementation of webinars on the development of special programmes continuously provides support to authorities in this process...
.
Measure 1.4.3: Improvement of the regulatory framework governing professional development in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Quality of new regulations governing the area of professional development (%) |  |  | 0 (2020) |  | 72- 80 | 72
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.3.1: Performance evaluation and review of the law regulating the field of professional development in state bodies (ex-post analysis of the law) | Q4 2022 | MPALSG |  | - | ..
1.4.3.2: Performance evaluation and review of the law regulating the field of professional development in bodies of local self-government units (ex-post analysis of the law) | Q1 2022 | MPALSG |  | - | ..
1.4.3.3: Performance evaluation and review of by-laws adopted based on laws regulating the field of professional development in public administration (ex-post analysis of by-laws) | Q4 2021 | NAPA | Completed | - | ..
1.4.3.4: Conducting ex-ante analysis of the law regulating the field of professional development in state bodies and consultations with stakeholders and target groups, with the aim of proposing optimal improvements to the law | Q4 2023 | MPALSG |  | - | ..
1.4.3.5: Conducting ex-ante analysis of the law regulating the field of professional development in bodies of local self-government units and consultations with stakeholders and target groups, with the aim of proposing optimal improvements to the law | Q4 2023 | MPALSG |  | - | ..
1.4.3.6: Implementing the process of planning and formulating amendments to the law regulating the field of professional development in state bodies | Q4 2024 | MPALSG | Not commenced | - | Based on the measurement of the performance of public policies in the field of professional development in state bodies and the prepared ex-ante analysis of the law regulating the field of professional development in state bodies (Law on Civil Servants and Law on the National Academy of Public Administration), the preparation of the starting points for the development of amendments to the Law on Civil Servants is underway... |  | In order to define the basis for the preparation of the Draft Law on Civil Servants, it was necessary, in addition to the ex-ante analysis of the law regulating the field of professional development in state bodies, to include the results of the Comparative Study on Lifelong Professional Development of Public Administration Employees in Representative Legal Systems, with a proposal for recommendations for the Republic of Serbia (activity established in the AP for the Implementation of the PAR Strategy in the Republic of Serbia for the period from 2021 to 2025, with a deadline of implementation in 2024), since the aforementioned ex-ante analysis indicated the need to amend the Law on Civil Servants and introduce criteria, measures and standards for the introduction of the process of continuous professional development with mandatory elements, i.e. define the steps in the process of standardising and implementing the master plan for lifelong professional development in state bodies. | Adoption of a decision on the establishment of a Special Working Group for the preparation of the Draft Law on Amendments to the Law on Civil Servants; Completion of work on the preparation of the Starting Points for the preparation of the Draft Law on Amendments to the Law on Civil Servants; Announcement of the start of work on the preparation of the Draft Law on Amendments to the Law on Civil Servants on the eConsultation portal; Invitation of the interested public to submit comments, proposals and suggestions regarding the proposed Starting Points for the preparation of the Draft Law on Amendments to the Law on Civil Servants; Preparation of the text of the Draft Law on Amendments to the Law on Civil Servants..
1.4.3.7: Implementing the process of planning and formulating amendments to the law regulating the field of professional development in bodies of local self-government units | Q4 2024 | MPALSG | Not commenced | - | Based on the measurement of the performance of public policies in the field of professional development in bodies of local self-government units and the prepared ex-ante analysis of the law regulating the field of professional development in bodies of local self-government units (Law on Employees in Autonomous Provinces and Local Self-Government Units), the preparation of the starting points for the development of amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units is underway... |  | In order to define the basis for the preparation of the Draft Law on Employees in Autonomous Provinces and Local Self-Government Units, it was necessary, in addition to the ex-ante analysis of the law regulating the field of professional development in state bodies, to include the results of the Comparative Study on Lifelong Professional Development of Public Administration Employees in Representative Legal Systems, with a proposal for recommendations for the Republic of Serbia (activity established in the AP for the Implementation of the PAR Strategy in the Republic of Serbia for the period from 2021 to 2025, with a deadline of implementation in 2024), since the aforementioned ex-ante analysis indicated the need to amend the Law on Employees in Autonomous Provinces and Local Self-Government Units and introduce criteria, measures and standards for the introduction of the process of continuous professional development with mandatory elements, i.e. define the steps in the process of standardising and implementing the master plan for lifelong professional development in bodies of local self-government units. In addition, the planned support for the preparation of this draft law was not provided in 2024, given that its implementation has not yet begun.. | Adoption of a decision on the establishment of a Special Working Group for the preparation of the Draft Law on Amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units; Completion of work on the preparation of the Starting Points for the preparation of the Draft Law on Amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units; Announcement of the start of work on the preparation of the Draft Law on Amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units; Invitation of the interested public to submit comments, proposals and suggestions regarding the proposed Starting Points for the preparation of the Draft Law on Amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units; Preparation of the text of the Draft Law on Amendments to the Law on Employees in Autonomous Provinces and Local Self-Government Units
1.4.3.8: Implementing the process of planning, formulating and adopting by-laws for the implementation of the law regulating the field of professional development in public administration | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.4.4: Standardisation and establishment of a quality system in the area of professional development in public administration, with full application of ICT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of business processes conducted with the use of information technologies (Number) |  |  | 1 (2020) |  | 3 | 3
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.4.1: Preparing a study on professional development in public administration, with an assessment of the needs for establishing minimum uniform criteria, benchmarks and standards in capacity building and professional development of public administration employees | Q4 2022 | MPALSG |  | - | ..
1.4.4.2: Establishing a more specific organisational unit within the basic organisational unit that performs professional development tasks in the MPALSG to guide the development and monitor the implementation of the standardisation of the professional development process and the quality system in the field of professional development in public administration | Q4 2025 | MPALSG |  | - | ..
1.4.4.3: Establishing an organisational unit at NAPA for the implementation of the quality system of professional development in public administration (quality management centre) | Q4 2025 | NAPA | In progress | - | The Rulebook on the Job Classification, adopted on 29 December, 2022, the Quality Management Job Position was classified as an independent employee within the Sector for the Preparation of Training Programmes and Quality Management, as a transitional solution until the establishment of a separate organisational unit.
1.4.4.4: Preparing a study on the optimisation of business processes in the field of professional development - analysis of business processes and a proposal for reorganisation for the purpose of standardisation and digitisation of the professional development process in public administration, as well as improvement of the supervisory function and application of ICT in this area | Q4 2023 | NAPA | The idea was abandoned | - | Project activity which was abandoned...
1.4.4.5: Developing ICT systems and network infrastructure for the implementation of standardised business processes for professional development in public administration | Q4 2023 | NAPA | Completed | - | ..
1.4.4.6: Developing a distance learning platform, with the application of multimedia and interactive online learning methods (group work with live sessions, forums, joint exercises in Blackboard systems - virtual classrooms, work on joint projects, learning in a "face to face" environment, and finally "mandatory socialising" training) and providing conditions for the application of this form of professional development in all segments of professional development in public administration (a single platform that can be used by all authorities) | Q4 2022 | NAPA | Completed | - | ..
.
Measure 1.4.5: Establishment of a system for planning and managing the process of lifelong professional development in public administration (lifelong professional development master plan)
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Degree of development of a system for planning and managing the process of lifelong professional development (Number) |  |  | 0 (2019) |  | 0 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.5.1: Preparing a comparative study on lifelong professional development of public administration employees in representative legal systems, with proposed recommendations for the Republic of Serbia | Q4 2024 | MPALSG | Completed | 100% | Prepared Study on Lifelong Professional Development of Public Administration Employees – Comparative Review of Practice in Member States of the Council of Europe and Beyond, with Proposal for Recommendations for the Republic of Serbia.
1.4.5.2: Preparing a Master Plan Model for Lifelong Professional Development in Public Administration, with Elements of Impact on the Human Resources Planning System in the Administration, the Evaluation System and the Reward System, and Impact Analysis | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.4.6: Establishment of instruments for cooperation between institutions responsible for professional development of employees in state and other bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Extent of development of the framework for cooperation between institutions in charge of the professional development of employees (Number) |  |  | 0 (2019) |  | 1 | 1
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.6.1: Establishing a framework for improving cooperation between institutions the scope of which includes the organisation and implementation of professional development programmes for employees in state and other bodies (network of schools) | Q4 2023 | MPALSG |  | - | ..
1.4.6.2: Promoting and encouraging interdepartmental professional development in multi-sectoral areas | Q4 2025 | NAPA | In progress | - | The Joint Body for the Promotion of Cooperation of Institutions Responsible for Capacity Building and Professional Development in State and Other Bodies – the School Network, one of whose tasks is the development of interdepartmental professional development in multi-sectoral topics, has adopted the Annual Programme of the School Network for 2024, which created the conditions for the implementation of the first specific tasks of the School Network and the beginning of the achievement of the goals for which it was established. The implementation bodies in the activities established by the Annual Programme of the School Network for 2024 were the Ministry of Public Administration and Local Self-Government, the Ministry of Justice, the Ministry of Interior, the Ministry of Foreign Affairs – the Diplomatic Academy, the National Academy of Public Administration and the Judicial Academy. In accordance with the implementation deadlines, training programmes in multi-sectoral areas of professional development were successfully implemented, attended by civil servants, employees of local self-government units, employees of social work centres, judges, judicial assistants, prosecutors, prosecutorial assistants and other representatives of target groups envisaged by the Annual Programme of the School Network for 2024. In addition to the abovementioned training sessions, a roundtable meeting of trainers (training implementers) accredited at the National Academy of Public Administration and the Judicial Academy was held, where experiences were exchanged, with the proposal of activities to improve the process of training participants of both academies through the development of curricula for innovative training programmes and the application of modern forms and methods of interdisciplinary professional development in multi-sectoral topics...
1.4.6.3: Developing and implementing cooperation between special expert bodies (programme council, permanent programme commissions, etc.) of institutions the scope of which includes professional development of employees in state and other bodies | Q4 2025 | NAPA | In progress | - | ..
.
Measure 1.4.7: Introduction of uniform criteria, benchmarks and standards in the field of professional exams in the state administration system
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Extent of establishment of uniform standards concerning professional examinations in the public administration system (Number) |  |  | 0 (2019) |  | 12 | 15
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.7.1: Preparing an analysis with a proposal for measures to establish a unified regulation of issues that are common to all professional exams in the public administration system, with an impact analysis | Q4 2022 | MPALSG |  | - | ..
1.4.7.2: Preparing an analysis of the need to establish a relationship between professional exams and professional development, i.e. the obligation to attend training to prepare for taking the professional exam before taking the professional exam, with an impact analysis | Q4 2022 | MPALSG |  | - | ..
1.4.7.3: Conducting ex-ante analysis of the law regulating on unified grounds the field of professional examinations in public administration system and consultations with stakeholders and target groups, with the aim of proposing optimal regulation of the law | Q4 2023 | MPALSG |  | - | ..
1.4.7.4: Implementing the process of planning and formulating a law that regulates the field of professional examinations in the public administration system on uniform grounds | Q4 2023 | MPALSG |  | - | ..
1.4.7.5: Preparing a study on the optimisation of business processes in the field of professional exams (analysis of business processes and a proposal for reorganisation for the purpose of standardisation of the professional examinations, as well as improvement of the supervisory function and application of ICT in this area) | Q4 2024 | MPALSG | Completed | 100% | A Study on the Optimisation of Business Processes in the Field of Professional Examinations in the Public Administration System has been prepared, with identified key aspects for the introduction of ICT into the professional examination system, with a proposal for the optimal option, or the optimal combination of the considered options...
1.4.7.6: Developing ICT systems and network infrastructure for the implementation of standardised business processes in the area professional examinations in the system the public administration | Q4 2025 | ITE Office |  | - | ..
.
Measure 1.4.8: Development of cooperation with higher education institutions to support schooling and/or additional education of staff for public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of public administration bodies and bodies of local self-government units participating in the student internship programme (%) |  |  | 0 (2020) |  | 36- 40 | 54
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.8.1: Establishing instruments to support the implementation of the public administration training and education system, equally focused on theory and practice | Q4 2024 | MPALSG | Completed | - | In accordance with the Agreement on Cooperation in Providing Public Administration Support to Higher Education Institutions in the Educational Process concluded on 15 October, 2021, the Cooperation Programme in Providing Public Administration Support to Higher Education Institutions in the Educational Process for the academic year 2024/2025 was concluded, in accordance with which the student internship programme in public administration is being implemented. Five state universities (in Belgrade, Kragujevac, Niš, Novi Sad and Novi Pazar) and 141 state and other bodies in 70 cities and municipalities are currently participating in the student internship programme, with a range of almost 1,500 internship places.
1.4.8.2: Providing conditions for the continuous obligation to implement student internship programme in state administration bodies and bodies of local self-government units | Q4 2025 | MPALSG | Completed | - | In order to further improve the effects of the new policy for strengthening administrative capacities in public administration, through support for the education of public administration personnel and the promotion of public administration as a preferred employer, at the proposal of the Ministry of Public Administration and Local Self-Government, the Government adopted Conclusion 05 number: 612-4917/2024 from 6 June, 2024, aiming, among other things at the following: - to accept the Report on activities carried out regarding the development of cooperation instruments with higher education institutions to support the education of public administration personnel, number: 001622959 2024 14800 008 000 151 002 from 9 May, 2024; - to order ministries, administrative bodies within ministries, special organisations, Government services and expert services of administrative districts to provide participation in cooperation programmes in providing public administration support to higher education institutions in the educational process for each academic year; - to recommend to the bodies of local self-government units to provide participation in cooperation programmes in providing public administration support to higher education institutions in the educational process for each academic year. This Government Conclusion provides the conditions for the continuous obligation to implement student internship programme in state administration bodies and bodies of local self-government units within the deadline set by the Action Plan. The given Conclusion resulted in an almost 100% increase in the number of public administration bodies that joined the initiative of student internship in public administration in 2024...
1.4.8.3: Organizing the annual conference "Student Internship in Public Administration" to promote professional training and development in public administration | Q4 2025 | MPALSG | Completed | 100% | The Student Internship Fair in Public Administration was held for the fourth time in a row – on 4 December, 2024, for the first time financed from the Budget of the Republic of Serbia, i.e. without donor support. The fair was organised as a virtual event, and for this occasion, a 3D platform was created that faithfully depicts the interior of the Serbia Palace. Students and other visitors had the opportunity to get acquainted with all public administration bodies and their internship offers at the Fair – at the bodies' virtual stands, through brochures, at forums and panels, but also through conversations in chat rooms with representatives of their universities and bodies that have internship offers for that university. Considering the interest in this event beyond the borders of our country, as a regional example of good practice, representatives of the European Institute for Public Administration EIPA, the Regional School of Public Administration ReSPA and the Ministry of Public Administration of the Republic of North Macedonia also participated in this fair. In the days before the Fair and on the day of the Fair, the Virtual Community of Student Internship in Public Administration (which is also the entrance to the Fair) recorded more than 10,000 visitors and 35,000 views. The Fair was preceded by promotional activities by means of: - Virtual community of student internship in public administration where relevant news, information about internship were regularly published and direct communication with students was established via the Q&A option. By the end of 2024, the Virtual Community had 2,089 full/registered members, 65,977 visitors, 245,878 views, 624,766 events. - The Ministry's website and social networks where information was shared about all the most important steps in the calendar of activities (roadmap) of student internship in public administration. - Forums and panels at the faculties of universities participating in this process for which public administration bodies had a predominant offer of places for attending internship programme. A total of 18 forums and panels were held, attended by a significant number of students, faculty teachers and representatives of public administration bodies (5 at the faculties of the University of Belgrade, 3 at the faculties of the University of Kragujevac, 5 at the faculties of the University of Niš, 4 at the faculties of the University of Novi Sad and a joint forum for all departments of the State University in Novi Pazar). Also, for the purpose of promoting professional practice in public administration at faculties, promotional material was prepared (flyers with information about the practice and how to obtain additional information about it, badges with this year's motto of professional practice, etc.), and after the forums, video material was prepared that was promoted at the Virtual Community and the Student Internship Fair in Public Administration 2024/2025... |  |  | Organisation of the Student Internship Fair in Public Administration 2025/2026, with the participation of an even larger number of state and other bodies and a richer and more diverse offer of professional practice. Funds for the implementation of this activity in 2025 have been provided in the budget of the Republic of Serbia for 2025.
1.4.8.4: Developing and implementing the training programme for master's studies "Preparatory Class for Public Administration" | Q4 2024 | NAPA | Completed | - | https://napa.gov.rs/tekst/5403/drugi-programi-obuka-naju.php..
1.4.8.5: Improving analytical, research and other activities of the NAPA in cooperation with higher education institutions and scientific research organisations | Q4 2023 | NAPA | Completed | - | ..
.
Specific objective 1.5: PUBLIC ADMINISTRATION PROVIDES SERVICES IN AN EFFICIENT AND INNOVATIVE MANNER MATCHING THE NEEDS OF END USERS AND ENHANCES THEIR USER EXPERIENCE
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
SIGMA evaluation average score for service delivery for all four measured pillars (Grade 0–5) |  |  | 3 (2019) |  | - | -
The GDP share of the administrative burden of citizens and businesses (%) |  |  | 3.26 (2018) |  | 3.08- 2.8 | - | We are unable to show data for 2024, the latest data we have is 2022. For 2023, the calculation was supposed to start in the middle of last year, when the data for the calculation became available, but due to delays, this analysis has not yet started. The value of 2.91% of GDP is for 2022. The administrative burden for 2023 will be measured in 2025 - a delay of 7 months due to the World Bank's procedures in selecting contractors.
.
Measure 1.5.1: Promoted development of new and optimisation of existing services tailored for end users
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of simplified administrative procedures for citizens and businesses (Number) |  |  | 125 (2020) |  | 450- 500 | 556 | In 2024, 81 procedures were optimised, while another 39 procedures were abolished.
Number of one-stop shops set up in LSGUs (Number) |  |  | 14 (2020) |  | 30.6- 34 | 65 | In 2024, 16 one-stop shops were opened, and the total number of those opened so far amounts to 65.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.5.1.1: Designing a methodology for the development of new and the optimisation of existing services based on a systematic involvement of end users in all the phases of the development through the use of advanced and innovative toolsmethodology for the development | Q3 2022 -> Q4 2025 | PPS | In progress | - | The text of the Methodology for the Regulation of Administrative Procedures has been prepared for adoption in the form of a Conclusion of the Government of the Republic of Serbia... |  | During 2024, the GIZ project "Redesign of Services Based on User Needs (HCD Human Centred Design)" was launched, where it was recognised that the already prepared text could be further improved. | Adoption of a Conclusion of the Government of the Republic of Serbia on the Adoption of the Methodology for the Regulation of Administrative Procedures.
1.5.1.2: Preparing the Programme for the Simplification of Administrative Procedures and Regulations for the period after 2021 (the e-Paper Programme) | Q2 2022 | PPS | Completed | - | ..
1.5.1.3: Popularising the use of digital services, and increasing the availability of electronic certified signature issued by the certification body of the Ministry of Interior | Q4 2025 | MoI | Completed | - | "The Information and Communication Technologies Sector of the Ministry of Interior is continuously working on the development of new eServices of the Ministry of the Interior on the eGovernment Portal, where a certificate is used for authentication/digital signature for citizens and businesses: Declaration/consent for admission to citizenship of the Republic of Serbia of a minor child, Declaration/consent for registration of residence of a minor child, Declaration/consent for issuing an ID card/passport to a minor child, Power of attorney for receiving a passport, Declaration/consent for termination of citizenship of the Republic of Serbia for a minor child, Consent of the owner of real estate for registration of residence of an adult, Power of attorney for submitting a request and receiving a certificate of residence/stay, Declaration/consent for registration of temporary stay abroad of a minor longer than 90 days, Fire certificate, Issuing a permit for movement and stay in the border crossing area, Registration of gatherings, Renewal of a license for a legal entity and an entrepreneur for performing private security services; the Directorate for Administrative Affairs is improving existing electronic services, as well as creating new ones, in order to create a modern, efficient and more effective public administration. In its work, it continues to enter electronic signatures into the chip of citizens' ID cards. ".. |  |  | Continued development of new eServices.
1.5.1.4: Drafting the Guidelines for the Choice of Priority Administrative Services to be Digitalised (creating priority contactless services) | Q4 2021 | PPS | Completed | - | ..
1.5.1.5: Developing a "Plan for Providing Priority Administrative Services During Crisis Situations" in order to provide continuity of service delivery in times of crisis (similar to the Covid epidemic) | Q4 2022 | MPALSG |  | - | ..
1.5.1.6: Revising the Electronic Government Development Programme with the accompanying action plan | Q4 2022 | MPALSG |  | - | ..
1.5.1.7: Defining standards for the establishment of one-stop shops through the preparation of a decree of the Government of the Republic of Serbia regulating this area | Q4 2022 | MPALSG |  | - | ..
1.5.1.8: Establishing a legal framework for the systematic inclusion of users in the development/design of (new and existing) services at all stages of development (Decree on the Principles of Service and Information Management) | Q4 2023 | MPALSG |  | - | ..
1.5.1.9: List of administrative requirements and other business conditions | Q2 2025 | PPS | In progress | - | 3,531 administrative requests were registered in the RAP (documentation and business conditions in total). The inventory was completed for 600 procedures, project support was provided for the inventory of 1,000 through the EDGE project, the remaining AR are under review in the PPS. |  | Delay in project support from EDGE for the inventory of requests.. | Completion of the inventory of administrative requests.
1.5.1.10: Developing 20 public administration services for the businesses, based on the episode business principle, which will be digitised and available to users through the e-Government Portal | Q1 2025 -> Q4 2027 | PPS | In progress | - | Harmonised narratives (text of future digitised forms of business episodes) have also been prepared, as follows: 3 general business episodes (tax liabilities, employment and cessation of business activity), starting a business and doing business in the following areas: domestic and international freight transport, catering (accommodation and serving food and beverages), media, production of beverages (soft drinks, strong alcoholic beverages, beer and wine). Harmonisation of 5 more thematic areas (pharmacy, dentistry, bakery, specialised and non-specialised retail) is underway. |  | The grant agreement for the PPS within which these activities will be implemented became effective in May 2024, and it was originally planned that the grant agreement would be signed by the end of 2021. Due to this delay, an extension of the grant duration for an additional 24 months was requested, in order to implement all planned activities. | In 2025, the first business episode in the media field is expected to be digitised.
1.5.1.11: Improving the infrastructure for providing electronic services (missing registers, modules, etc.) | Q1 2025 -> Q4 2027 | PPS | In progress | - | Due to the delay in the grant agreement, the first implementation/digitisation of the business episode for the media can be expected in 2025. Digitisation processes have been identified in a number of areas... |  | The grant agreement for the PPS within which these activities will be implemented became effective in May 2024, and it was originally planned that the grant agreement would be signed by the end of 2021. Due to this delay, an extension of the grant duration for an additional 24 months was requested, in order to implement all planned activities. | The digitisation of missing registers/modules will be implemented together with the digitisation of business episodes.
1.5.1.12: A detailed list of all steps and elements of administrative procedures related to citizens through the Register of Administrative Procedures, which are implemented by the SAB | Q4 2022 | PPS | Completed | - | ..
1.5.1.13: Launching initiatives, innovative campaigns and implementing ICT training in the SKIP centre for citizens, especially for those categories of the population who, due to an insufficient level of ICT knowledge, are at risk of "digital exclusion" from the electronic service delivery system of the Republic of Serbia | Q4 2025 | MPALSG | In progress | - | This is an ongoing activity. During 2024, more than 240 free training sessions for citizens were organised for more than 12,000 citizens. Since the opening of the SKIP centre, more than 3,000 training sessions have been conducted in the field of computer and innovative technologies for more than 90,000 citizens...
1.5.1.14: 1.5.1.14: Conducting an analysis of all administrative procedures related to citizens and preparing recommendations for simplification in accordance with the established methodology at the national level, as well as simplifying administrative procedures/public services for businesses and citizens | Q4 2025 | PPS | In progress | - | In 2024, a revised ePAPER Action Plan for 2025 was prepared, which included proposals for the optimisation and digitisation of 450 new administrative procedures... |  |  | Adoption of the Decision on Amendments to the Action Plan for the ePAPER Programme.
.
Measure 1.5.2: Raising human and technical-technological capacities of public administration for service delivery to end users
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of state administration civil servants and local self-government employees in service delivery jobs who successfully completed a training in the area of service delivery quality improvement (%) |  |  | 0 (2020) |  | 49.5- 55 | - | There were 1706 participants in these training sessions in 2024. We cannot express this in percentages, since we do not know how many people are employed in these jobs in total.
EU Benchmark for e-Government – key prerequisites put in place (Index 0–100) |  |  | 35 (2020) |  | 67.5- 75 | 62.5
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.5.2.1: Drafting a training plan for employee development in accordance with the results of the analysis and the strategic commitment of the Government of the Republic of Serbia | Q3 2023 | NAPA | Completed | - | ..
1.5.2.2: Implementing training for public administration officers on the use of the National eGovernment Portal for providing services | Q4 2022 | NAPA | In progress | - | ..
1.5.2.3: Developing a methodology for determining jobs and the number of employees working on tasks related to the delivery of public services | Q4 2023 | HRMS |  | - | ..
1.5.2.4: Conducting an analysis of the availability and structure of human capacities within public administration and local self-government for the delivery of public services | Q4 2024 -> Q4 2025 | HRMS | In progress | 96.3% | During 2024, the Human Resources Management Service held several meetings with GIZ; in the third quarter of 2024, GIZ conducted a call for proposals and selected consultants for the project. GIZ prepared a document defining the tasks for expert support, as well as deadlines. In October 2024, the HRMS adopted a decision on the appointment of a Special Working Group for Conducting an Analysis of the Availability and Structure of Human Capacities within the Public Administration and Local Self-Government for the Delivery of Public Services, which met four times by the end of 2024. The consultants have developed a document entitled Development of a Methodology for Determining the Number of Jobs and the Number of Employees Working on Tasks Related to the Delivery of Public Services, in order to collect the necessary data for conducting the Analysis of the Availability and Structure of Human Capacities within the Public Administration and Local Self-Government for the Delivery of Public Services. The members of the Special Working Group defined the issues for HRMIS, as well as for the application, which was then developed by the HRMS for local self-government units, in which data will be filled in by personnel units regarding the performance of public service delivery tasks... |  |  | During 2025, it is necessary to develop HRMIS, in the part related to the collection of data for the analysis of the availability and structure of human capacities for the delivery of public services, as well as to collect the necessary data for analysis through the HRMIS software, for state administration bodies, as well as through the application for local self-government units and to develop an Analysis of the Availability of the Structure of Human Capacities within the Public Administration and Local Self-Government for the Delivery of Public Services.
1.5.2.5: Developing and implementing the training "Designing Services" for senior civil servants (Honeycomb core) | Q4 2023 | NAPA | Completed | - | NAPA GRANT 1 training session implemented, attended by 9 SSCs
1.5.2.6: Implementing online training "Creative User-Oriented Service and Policy Development (Design Thinking)" | Q4 2023 | NAPA | Completed | - | Self-paced online training available from May 2021, total of 257 participants since posting, of which 73 completed and 184 are ongoing, in 2023 alone 14 completed and 14 started...
1.5.2.7: Developing and implementing training "Essentials" - Achieving Results Through Public Service Delivery" for senior civil servants | Q4 2023 | NAPA | Completed | - | NAPA GRANT 2 Essentials groups, 58 participants, through 17 modules in 2023 implemented in 21 days...
1.5.2.8: Developing and implementing training programmes for officers who are in direct contact with service users (with a special focus on providing services to people with disabilities, users with special needs, vulnerable users, marginalised users) | Q4 2023 | NAPA | Completed | - | 2 workshops were conducted in cooperation with the OSCE, attended by 27 participants.
1.5.2.9: Implementing training for officers for the optimisation of administrative procedures/services | Q4 2023 | NAPA | Completed | - | 2 training sessions were implemented, 1 live and 1 in the form of a webinar, with a total of 39 participants. Within the e-Paper project (PPS) we supported the implementation of 3 training sessions on this topic, in which 28 participants participated...
1.5.2.10: Implementing training sessions in the application of standards for the delivery of public services | Q4 2023 | NAPA | In progress | - | Training has been developed, the implementation of the portal improvement in the area of ​​creating new services is pending...
1.5.2.11: Improving the technical and technological equipment of the administrative inspection service | Q4 2025 | MPALSG |  | - | ..
1.5.2.12: Establishing one-stop shops in the territory of local self-government units | Q4 2025 | MPALSG | In progress | - | ..
1.5.2.13: Developing and implementing the training programme "Managing the Quality of Public Administration" - balanced scorecards (BSC), common self-assessment framework (CAF); collaborative reviews in the public sector, etc. | Q4 2025 | NAPA | In progress | - | 36 participants completed the online training, 9 participants attended the classic training.
1.5.2.14: Strengthening the capacity of the administrative inspection in supervising the implementation of public service delivery standards for the purpose of performing internal quality control of service delivery and providing support to the ministry responsible for service delivery policy for effectively ensuring the quality of services provided | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.5.3: Improved system of service quality control and quality assurance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of SABs which have already implemented the CAF or any other quality management tool in the course of one calendar year based on the corresponding legal framework (Number) |  |  | 0 (2020) |  | 8 | 23
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.5.3.1: Creating a legal framework which prescribes the establishment of a comprehensive and updated electronic records of administrative procedures/ services in a form of a public registry | Q2 2021 | PPS |  | - | ..
1.5.3.2: Translation of the CAF 2020 into the Serbian language | Q4 2021 | MPALSG |  | - | ..
1.5.3.3: Establishing methodologies for measuring the administrative burden on businesses and citizens related to public administration services; methodologies for measuring the costs of providing public services. | Q4 2024 | PPS |  | - | ..
1.5.3.4: Promotion of CAF through the drafting of promotional materials (video and printed content) on internet portals | Q4 2025 | MPALSG |  | - | ..
1.5.3.5: Preparing an analysis of the existing system of monitoring, control and quality assurance of public administration services, along with an analysis of best international practice in that area | Q4 2022 | MPALSG |  | - | ..
1.5.3.6: Implementing CAF in 10 SABs and/or other public administration institutions | Q4 2023 | MPALSG |  | - | ..
1.5.3.7: Establishing a methodology for measuring the results/performance of public service providers | Q4 2022 | MPALSG |  | - | ..
1.5.3.8: Identifying the needs for improving physical accessibility to services for members of endangered and vulnerable groups as well as members of minority communities through improving physical access and territorial availability of services | Q4 2022 | MPALSG |  | - | ..
1.5.3.9: Establishing a methodology for measuring end-user satisfaction with public administration services pdelivered (electronically and traditionally) | Q4 2022 -> Q4 2023 | MPALSG | In progress | - | ..
1.5.3.10: Increasing the number of employees in the Strategic Planning Department of the MPALSG for the implementation of the CAF | Q4 2025 | MPALSG | In progress | - | ..
1.5.3.11: Measuring/conducting research on end-user satisfaction with the services delivered and calculating indicators | Q4 2023 | MPALSG | In progress | - | On the e-Government Portal, a measurement of user satisfaction with e-services has been established. For services provided at physical locations, a technical specification has been developed for launching a pilot of satisfaction measurements at all OSSs...
1.5.3.12: Developing recommendations and defining a legal framework for the establishment of an independent body-agency for external monitoring, control and quality assurance of service delivery | Q4 2023 | MPALSG | Not commenced | - | ..
1.5.3.13: Establishing an independent body – agency for external monitoring, control and quality assurance of service delivery | Q4 2025 | MPALSG |  | - | ..
.
Specific objective 1.6: INCREASED LEVEL OF ACCOUNTABILITY AND TRANSPARENCY AT ALL LEVELS OF THE GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
EC's annual assessment of progress in the area of accountability (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | EC report: Management accountability remains to be improved. There has been no progress in addressing systemic organisational problems of the administration, such as overlapping roles and unclear reporting lines, with limited application of the concept of management accountability.
SIGMA indicator: accessibility of public information (Point/30) |  |  | 21 (2017) |  | - | -
.
Measure 1.6.1: Establishment of systemic solutions for management accountability in public administration bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of state administration bodies in which authorised officials have been appointed to conduct administrative procedures and make decisions in administrative matters (%) |  |  | 23 (2020) |  | 33.25- 35 | 85 | Out of a total of 59 state administration bodies /which consist of ministries, special organisations and government services/, 50 state administration bodies have designated employees for conducting administrative procedures and making decisions in administrative matters.
Percentage of state administration bodies, independent state bodies and bodies of local self-government units the managers of which attended training on the application of the principle of management accountability (%) |  |  | 0 (2020) |  | 0 | 16
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.1.1: Preparing a comprehensive analysis of the current situation and guidelines for defining systemic solutions within the legal and institutional framework of the Republic of Serbia for management accountability (delegation of accountability, clear lines of accountability between institutions and performance measurement at the institutional level) in public administration bodies. | Q3 2022 | GENSEC |  | - | ..
1.6.1.2: Harmonising the legal framework in accordance with the guidelines for the purpose of defining systemic solutions for management accountability in public administration bodies. | Q2 2023 | SAB (Public administration body) |  | - | ..
1.6.1.3: Establishing the Register of Holders of Public Authorities | Q4 2023 -> Q4 2026 | MPALSG |  | - | ..
1.6.1.4: Developing a manual for the application of the principles of management accountability - a practical guide for managers with a focus on basic management issues in the context of public administration; resource management; planning; performance management and reporting. | Q3 2023 | MoF |  | - | ..
1.6.1.5: Developing a training module on the topic of Application of the Principles of Management Accountability for Managers | Q3 2023 | MoF |  | - | ..
1.6.1.6: Implementing a training module on the topic of Application of the Principles of Management Accountability for Managers | Q4 2025 | NAPA | In progress | - | The online training, which was launched in 2022, was completed by 75 managers from 37 out of 221 different bodies by the end of 2024...
1.6.1.7: Organising expert meetings aimed at exchanging experience and best practice examples regarding the principle of management accountability, as well as monitoring achievements and identifying future steps in improving this area in the public sector of the Republic of Serbia | Q4 2025 | MoF |  | - | ..
.
Measure 1.6.2: Improvement of the vertical and horizontal system of supervision and monitoring of work in public administration (Establishing mechanism for performance management of public administration bodies)
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of priority objectives from the Action Plan for the Implementation of Government Programmes referring to state administration bodies, which were taken into account when preparing medium-term plans of medium-term planning obligors (%) |  |  | 0 (2019) |  | 38- 40 | 62.5
Percentage of state administration bodies, independent state bodies and bodies of local self-government units the managers of which attended training on the application of unified methodology for performance management (%) |  |  | 0 (2020) |  | 3 | 22
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.2.1: Implementing a pilot project with a focus on improving performance management, testing and determining an adequate mechanism for collecting and processing relevant data for measuring and reporting on performance, i.e. determining the necessary capacities and job descriptions for these tasks in a selected number of public administration bodies. | Q2 2023 | MoF |  | - | ..
1.6.2.2: Developing Guidelines with a unified methodology for performance management - work control, supervision and internal and external reporting on work results within the competence of public administration bodies based on lessons learned from the pilot project implemented in the previous activity (6. 2.1) | Q4 2023 | MoF |  | - | ..
1.6.2.3: Developing a training module on the application of a unified methodology for performance management - work control, supervision and internal and external reporting on work results within the competence of public administration bodies as part of the training programme for managers and employees | Q4 2023 | MoF |  | - | ..
1.6.2.4: Implementing a training module on the application of a unified methodology for performance management - work control, supervision and internal and external reporting on work results within the competence of public administration bodies as part of the training programme for managers and employees. | Q4 2025 | NAPA | In progress | - | The training sessions conducted during 2024 were attended by 113 managers from 49 out of 221 different bodies...
1.6.2.5: Prescribing mandatory elements of annual operational plans of public administration bodies and organisations and their basic organisational units, which necessarily include specific and measurable objectives, accompanied by clear indicators and target values, as well as prescribing mandatory elements of annual performance reports submitted by these entities to the body supervising their work/head of the public administration body. | Q4 2023 | SAB (Public administration body) |  | - | ..
1.6.2.6: Prescribing the obligation of institutions to: analyse reports on the performance of constituent bodies and basic organisational units; provide recommendations/instructions to these bodies for improving their performance; and regularly monitor whether the constituent body complies with the given recommendations/instructions. | Q4 2023 | SAB (Public administration body) |  | - | ..
1.6.2.7: Harmonising the legal framework in the field of financial management and control in accordance with the activity from the previous activity (6.2.6.) | Q4 2023 | MoF |  | - | ..
1.6.2.8: Prescribing the obligation to submit a consolidated performance report (with data on the results of meeting planned objectives and measures from medium-term plans) for all state administration bodies to the Government for consideration and adoption. | Q4 2023 | SAB (Public administration body) |  | - | ..
.
Measure 1.6.3: Strengthening integrity and ethical standards in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of state administration bodies and independent state bodies which organise and implement training in ethics and integrity for their managers and employees (%) |  |  | 0 (2020) |  | 47.5- 50 | - | The implementation of the Ethics and Integrity training is an obligation of all public authorities in accordance with the Law on the Prevention of Corruption. The training is implemented in three-year cycles, followed by a one-year break, for the purpose of evaluating the previous cycle and preparing for the next cycle. Bearing this in mind, during 2024, public authorities were not obliged to attend the Ethics and Integrity training, i.e. during that period there was a one-year break.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.3.1: Based on the Guidelines and Recommendations for the Introduction of Ethics and Integrity Officers in the Public Administration of the Republic of Serbia, preparation of a document with findings on the level of establishment of ethical infrastructure in public administration bodies, recommendations for systematising and integrating various tasks related to preventing corruption and strengthening integrity in public administration bodies; conditions and criteria for appointing ethics and integrity officers and rules of their conduct, as well as a proposal for criteria and methods for selecting public administration bodies that will participate in the pilot project referred to in activity 4.1.3.2. | Q1 2023 | MPALSG |  | - | ..
1.6.3.2: Based on the recommendations, systematising and integrating various tasks related to preventing corruption and strengthening integrity in public administration bodies, meeting conditions and criteria for appointing ethics and integrity officers and the rules of their conduct referred to in activity 4.1.3.1, implementing a pilot project for appointing ethics and integrity officers in a selected number of public administration bodies, which will also include the preparation and implementation of training programmes for these officers. | Q4 2024 -> Q5 2025 | MPALSG | In progress | - | In order to strengthen the ethical infrastructure in state administration bodies, following the development of a Study on the Introduction of Ethics and Integrity Officers, a Pilot Project on the Introduction of Ethics and Integrity Officers in Public Administration Bodies of the Republic of Serbia is currently being implemented in four state administration bodies (MPALSG, NAPA, Ministry of Human and Minority Rights and Social Dialogue, and Ministry of Mining and Energy) with the support of UNODC. During the one-year duration of the Pilot Project, ethics and integrity officers were appointed in these selected state administration bodies, who underwent training and developed a work plan. The activities of the Ethics and Integrity Officers are related to the adoption, implementation and reporting on the implementation of integrity plans, managing conflicts of interest of employees, acting according to the rules of internal whistleblowing, acting upon complaints about the work of the body and employees, monitoring the implementation of the Code of Conduct for Civil Servants in the body, promoting ethical behaviour in the body, educating employees in the body on issues of ethics and integrity, etc. So far, two quarterly meetings have been held at which the participants presented the implemented activities from the work plan. Based on the experience gained during the implementation of the Pilot Project, it is planned to adopt a Final Report, which will, among other things, provide recommendations on the possibility of introducing these officers in all state administration bodies of the Republic of Serbia...
1.6.3.3: Preparing an analysis of the content of the Code of Conduct for Civil Servants and Procedures for Data Collection and Reporting, with the aim of improving ethical standards and mechanisms for monitoring the implementation of the rules of ethical conduct for civil servants | Q4 2022 | High Civil Service Council (HCSC) |  | - | ..
.
Measure 1.6.4: Promoting proactive disclosure of data held by public administration bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of public administration bodies and other holders of public authority which share/publish open data on the Open Data Portal (Number) (Number) |  |  | 45 (2019) |  | 133- 140 | 117
Percentage of state administration bodies and LSGU bodies whose employees attended training in open data standards and the Open Data Portal (%) |  |  | 0 (2020) |  | 19- 20 | 21
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.4.1: Developing a manual/guidelines for managers on the positive effects of increasing transparency in the work of public administration bodies and the development of an e-Informer for public administration bodies | Q4 2023 -> Q4 2024 -> Q4 2025 | Commissioner for information of public importance and protection of personal data |  | - | ..
1.6.4.2: Developing and updating of training modules on open data standards, their reuse and work with the Open Data Portal as part of the training programme for employees in state bodies and local self-government units | Q4 2025 | ITE Office |  | - | ..
1.6.4.3: Implementing training modules on open data standards, their reuse and work with the Open Data Portal as part of the training programme for employees in state bodies and local self-government units | Q4 2025 | NAPA | Completed | - | ..
1.6.4.4: Developing and adopting the Action Plan for the implementation of the Open Government Partnership initiative in the Republic of Serbia for the period 2022-2024 | Q4 2022 -> Q4 2023 | MPALSG |  | - | ..
1.6.4.5: Developing and adopting the Action Plan for the implementation of the Open Government Partnership initiative in the Republic of Serbia for the period 2024-2026 | Q4 2024 | MPALSG |  | - | ..
.
Measure 1.6.5: Improvement of reactive transparency, acting according to regulations within the purview of independent state bodies, i.e. according to the recommendations of independent state bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Percentage of execution of proposed, i.e. instructed measures of inspectoral supervision over the application of the regulations on free access to public information (%) |  |  | 75 (2019) |  | 86.24- 88 | 100
Percentage of execution of acts of the Commissioner for information of Public Importance and Personal Data Protection (%) |  |  | 65 (2019) |  | 74.48- 76 | -
Percentage of executed documents by the Protector of Citizens (%) |  |  | 81.43 (2019) |  | 87.22- 89 | 89.71
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.5.1: Amendments to the Law on Free Access to Information of Public Importance in order to improve accountability and transparency in the work of public authorities | Q4 2021 | MPALSG |  | - | ..
1.6.5.2: Preparing new Instructions for the preparation and publication of the Work Information Bulletin | Q4 2022 | Commissioner for information of public importance and protection of personal data |  | - | ..
1.6.5.3: Strengthening the capacity of the Commissioner through the employment of additional employees for the tasks of supervising the implementation of the Law on Access to Information of Public Importance in the part performed by the Commissioner, as well as providing financial resources for the necessary training for other bodies that supervise the implementation of the Law. | Q3 2025 | Commissioner for information of public importance and protection of personal data |  | - | ..
1.6.5.4: Strengthening human resources capacity, increasing the number and education of employees in the competent authority responsible for carrying out inspection supervision over the implementation of the Law on Free Access to Information of Public Importance. | Q4 2025 | MPALSG |  | - | ..
1.6.5.5: Improving the technical and spatial capacities necessary for exercising competence - inspection supervision over the implementation of the Law on Free Access to Information of Public Importance | Q4 2025 | MPALSG |  | - | ..
1.6.5.6: Amendments to the Law on Protector of Citizens to improve accountability and transparency in the work of public authorities | Q4 2021 | MPALSG |  | - | ..
.
Specific objective 1.7: EXECUTION OF A SUSTAINABLE BUDGET WITH A STABLE PUBLIC DEBT-TO-GDP RATIO, HELPED BY BETTER FINANCIAL MANAGEMENT AND CONTROL, AUDIT PROCESS AND CONNECTING BUDGET PLANNING WITH THE GOVERNMENT POLICIES
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Real growth of the Gross Domestic Product (GDP) (%) |  |  | 0 (2020) |  | - | -
General government debt-to-GDP (%) |  |  | 59 (2020) |  | - | -
.
Measure 1.7.1: SPECIFIC OBJECTIVE 1 of the Public Financial Management Reform Programme — IMPROVED CAPACITIES FOR BUDGET PLANNING AND PUBLIC INVESTMENT MANAGEMENT
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Public service delivery performance data (PEFA: 4-A, 3.5-B+, 3-B, 2.5-C+, 2-C, 1.5-D+, 1-D, 1-D*) |  |  | 2.5 (2020) |  | - | -
.
.
Measure 1.7.2: SPECIFIC OBJECTIVE 2 of the Public Financial Management Reform Programme — EFFICIENT COLLECTION AND MANAGEMENT OF PUBLIC FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Actual revenues and expenditures of the general government budget at annual level are within the range of 5% of those projected in the fiscal strategy (%) |  |  | 5 (2019) |  | 5 | -
Average duration of an open procedure (Number) |  |  | 52 (2020) |  | 45 | -
Annual cost of public debt servicing (interest payment – net amount) as % of the GDP (%) |  |  | 1.9 (2020) |  | - | -
.
.
Measure 1.7.3: SPECIFIC OBJECTIVE 3 of the Public Financial Management Reform Programme — IMPROVED BUDGETARY DISCIPLINE AND MORE TRANSPARENT USE OF PUBLIC FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Average number of illegalities and irregularities per control compared to the total number of controls (Number) |  |  | 2 (2020) |  | 1.1- 1 | -
Percentage of accepted and implemented recommendations which an audit body issues to subjects of indirect EU funds management (%) |  |  | 0 (2020) |  | 58.5- 65 | -
.
.
Measure 1.7.4: SPECIFIC OBJECTIVE 4 of the Public Financial Management Reform Programme — IMPROVEMENT OF THE APPLICATION OF THE INTERNAL FINANCIAL CONTROL SYSTEM IN PUBLIC SECTOR
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
PIFC-related progress identified in the EC progress report on the Republic of Serbia for a specific year (EC's assessment following the General Assessment of Preparedness value scale: 1 – Early stage of preparedness, 2 – Some level of preparedness, 3 – Moderate preparedness, 4 – Good level of preparedness) |  |  | 3 (2020) |  | 3 | -
.
.
Measure 1.7.5: SPECIFIC OBJECTIVE 5 of the Public Financial Management Reform Programme — IMPROVED ACCOUNTING IN THE PUBLIC SECTOR WITH THE APPLICATION OF INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS (IPSAS)
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Financial report prepared and presented to the Ministry of Finance of the Republic of Serbia in accordance with Cash Basis IPSAS (Number) |  |  | 0 (2020) |  | 1 | -
.
.
Measure 1.7.6: SPECIFIC OBJECTIVE 6 of the Public Financial Management Reform Programme — STRENGTHENING OF EXTERNAL SUPERVISION OF PUBLIC FINANCES
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of reviewed audit reports (Number) |  |  | 194 (2020) |  | 223.25- 235 | -
.
.
Specific objective 1.8: ESTABLISHMENT OF A SYSTEM OF LOCAL SELF-GOVERNMENT THAT ENABLES EFFECTIVE AND SUSTAINABLE EXERCISE OF CITIZENS' RIGHTS TO LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Compliance of the local self-government system with the key principles of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 3- 4 | 3 | A Draft Law on Amendments to the Law on Ratification of the European Charter of Local Self-Government has been prepared and submitted to the Government, which has approved the Draft Law and submitted it to the National Parliament of the Republic of Serbia.
Share of LSG expenditures and consolidated public expenditures in the Republic of Serbia (%) |  |  | 14.75 (2019) |  | 17 | -
The capacity of LSGUs to implement the principles of good governance (%) |  |  | 39 (2018) |  | - | -
Availability and quality of implementation of priority public services by LSG (Composite scale (1–10)) |  |  |  |  | - | -
.
Measure 1.8.1: SPECIFIC OBJECTIVE 1 of the Local Self-Government System Reform Programme — IMPROVING THE STATUS AND ACCOUNTABILITY OF LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Level of ratification of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 3- 4 | 3 | A Draft Law on Amendments to the Law on Ratification of the European Charter of Local Self-Government has been prepared and submitted to the Government, which has approved the Draft Law and submitted it to the National Parliament of the Republic of Serbia.
Average index value in selected areas: 1) accountability; 2) transparency, openness and participation (%) |  |  | 43 (2018) |  | - | -
The share of adopted laws in the total number of adopted laws which concern local self-government to a larger degree, which were prepared with the participation of LSGUs (Scale (1–5)) |  |  | 3 (2020) |  | - | -
.
.
Measure 1.8.2: SPECIFIC OBJECTIVE 2 of the Local Self-Government System Reform Programme — IMPROVEMENT OF THE LOCAL SELF-GOVERNMENT FINANCING SYSTEM
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of LSG tax revenues in total tax revenues in the Republic of Serbia (%) |  |  | 10.12 (2020) |  | 11.64- 11.7 | 10.3 | Local self-government unit`s tax revenues represent local self-government unit's own revenues, i.e. those for which it independently determines the rates. Problems have been observed both in terms of planning these revenues and in terms of their collection. Support is needed in this area to improve the situation.
Share of capital expenditures in total expenditures of local self-government (%) |  |  | 15.54 (2019) |  | 17.11- 17.2 | 18
Share of LSGUs which have adopted medium-term plans (%) |  |  | 0 (2020) |  | 27- 30 | 12.4 | For the medium-term planning cycle 2024-2026, 18 LSGUs adopted their medium-term plans, which is a weaker result compared to the previous cycle 2023-2025, when 27 LSGUs adopted medium-term plans. This indicates the need for further support and additional efforts to address the challenges in harmonising medium-term planning and linking it to programme budgeting at the local level.
.
.
Measure 1.8.3: SPECIFIC OBJECTIVE 3 of the Local Self-Government System Reform Programme — IMPROVING THE ORGANISATION AND CAPACITY OF LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
LSGU capacity for HRM in local administration (%) |  |  | 51 (2020) |  | - | -
Share of LSGUs which have established inter-municipal cooperation in the total number of LSGUs (%) |  |  | 27 (2020) |  | 42 | 61
.
.
Measure 1.8.4: SPECIFIC OBJECTIVE 4 of the Local Self-Government System Reform Programme — IMPROVING QUALITY AND ACCESSIBILITY OF SERVICES DELIVERED BY LOCAL ADMINISTRATION, UTILITY COMPANIES AND PUBLIC INSTITUTIONS
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Index to measure availability and quality of services delivered by LSGUs developed (0 – no, 1 – yes) |  |  | 0 (2020) |  | - | - | The adopted Action Plan for the period 2024-2025 introduced a new indicator: Established baseline values ​​for improving user satisfaction with local services, as the previous two indicators: Developed index for measuring the availability and quality of local self-government services and Developed index for measuring user satisfaction with local self-government services have been implemented.
Index to measure user satisfaction with services delivered by local self-government developed (0 – no, 1 – yes) |  |  | 0 (2020) |  | - | - | The adopted Action Plan for the period 2024-2025 introduced a new indicator: Established baseline values ​​for improving user satisfaction with local services, as the previous two indicators: Developed index for measuring the availability and quality of local self-government services and Developed index for measuring user satisfaction with local self-government services have been implemented.
.
.
Specific objective 1.9: COORDINATION AND COMMUNICATION
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
.
Measure 1.9.1: Ensure efficient coordination and monitoring of PAR Action Plan measures and activities
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of public policy documents pertaining to PAR, the monitoring results of which are available through the OMT (Number) |  |  | 1 (2020) |  | 5 | 6
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.1.1: Increasing the number of employees in the Strategic Planning Department of the MPALSG for the PAR coordination and monitoring. | Q4 2025 | MPALSG |  | - | ..
1.9.1.2: Training employees in the Strategic Planning Department of the MPALSG for the PAR coordination and monitoring. | Q4 2023 | MPALSG |  | - | ..
1.9.1.3: Holding a minimum of 2 administrative level coordination meetings per year | Q4 2023 -> Q4 2025 | MPALSG |  | - | ..
1.9.1.4: Holding a minimum of 2 political level coordination meetings per year | Q4 2023 -> Q4 2025 | MPALSG |  | - | ..
1.9.1.5: Expansion of the Online Monitoring Tool (OMT) to other public policy documents in the area of ​​PAR and improvement of the SAB web portal | Q4 2023 -> Q4 2025 | MPALSG |  | - | ..
1.9.1.6: Conducting a mid-term evaluation of the PAR Strategy 2021-2030 with the aim of preparing a new action plan for the period after 2025 | Q4 2023 | MPALSG |  | - | ..
1.9.1.7: Developing a new mid-term PAR expenditure framework | Q4 2021 | MPALSG |  | - | ..
1.9.1.8: Annual revision of the PAR medium-term expenditure framework, in light of the implementation of the AP PARS, as well as other PPDs within the PAR | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.9.2: Provision of efficient coordination of donor support to PAR
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of active and trained non-managerial staff working in the sector for European integration and international cooperation (Number) |  |  | 6 (2020) |  | 9 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.2.1: GAP analysis and roadmap for recommendations on the achievement of PAR sector budget support target values ​​in light of the future implementation of the Sector Reform Contract, its management and monitoring, including the functioning of the "Policy dialogue" and other coordination platforms | Q4 2022 | MPALSG |  | - | ..
1.9.2.2: Developing a risk management system for the PAR SBS, using the OMT and governance structures for PAR and the Sector Reform Contract | Q4 2022 | MPALSG |  | - | ..
1.9.2.3: Increasing the resources of the Sector for European Integration and International Cooperation, including the contact points for monitoring the implementation of the sector budget support instrument, the Sector Reform Contract for the PAR area, as well as complementary assistance projects. | Q4 2025 | MPALSG |  | - | ..
1.9.2.4: Capacity building of the Sector for European Integration and International Cooperation for donor coordination and project management through training, mentoring and study visits | Q4 2022 | MPALSG |  | - | ..
.
Measure 1.9.3: Establishment of a functional coordination mechanism for planning, implementation and monitoring of PAR communication at the national level
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Existence of an annual operational plan for PAR communication that establishes a coordination mechanism for PAR communication (Number) |  |  | 0 (2020) |  | 1 | 1 | An Annual Operational Plan for Communicating Public Administration Reform Topics for 2024 has been developed and adopted by the national coordination mechanism for communicating reform, the Special Working Group for Planning and Communicating Reform.
Level of fulfilment of annual operational plans for PAR communication (%) |  |  | 0 (2020) |  | 80 | - | The implementation of the communication plan was not monitored.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.3.1: Four-day annual workshop for members of the coordination mechanism for PAR communication with the aim of developing annual operational plans in accordance with the AP for the implementation of the PARS (25 participants) | Q4 2022 | MPALSG |  | - | ..
1.9.3.2: Developing annual operational plans for communicating the PAR in accordance with the AP for the implementation of the PARS and the findings from the annual survey of awareness of key stakeholders and the public | Q4 2022 | MPALSG |  | - | ..
1.9.3.3: Preparing quarterly monitoring reports on the implementation of annual operational plans in order to improve current and planned activities | Q4 2022 | MPALSG |  | - | ..
1.9.3.4: Preparing an annual report on the implementation of operational plans for the communication of PAR processes and results | Q4 2022 | MPALSG |  | - | ..
1.9.3.5: Conducting an annual public opinion survey on public awareness of the PAR process and results | Q4 2022 | MPALSG |  | - | ..
.
Measure 1.9.4: Harmonisation, standardisation and continuous PAR communication in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Proportion of SABs and LSGUs that publish PAR-related information in a standardised manner on the Notice Board (%) |  |  | 25 (2020) |  | 100 | - | Activities related to the introduction of the Notice Board have been abandoned and therefore it is not possible to measure the indicator value.
Total number of trained public relations and human resources management staff in SABs and LSGUs (Number) |  |  | 0 (2020) |  | 500 | 330 | The data refer only to participants of the online training programme "Successful Communication" posted on the online platform of the National Academy of Public Administration: - Public Speaking - Communication on Social Networks - Crisis Communication - Public Administration - Efficient Service to Citizens and the Economy - Communicator
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.4.1: Training for public relations officers and organisational units for HRM from the SABs on the importance, methods, channels and tools of interdepartmental and internal communication of the PAR | Q4 2022 | NAPA | Completed | - | ..
1.9.4.2: Training for public relations officers , and HRM from the LSGUs on the importance, methods, channels and tools of interdepartmental and internal communication of the PAR | Q4 2022 | NAPA | Completed | - | ..
1.9.4.3: Improving technical capacities and developing the functionality of the "Notice Board" for use (user access and content management) by all public administration bodies | Q3 2021 -> Q3 2023 | MPALSG |  | - | ..
1.9.4.4: Technical maintenance of the "Notice Board" in accordance with the needs of the PA | Q4 2025 | MPALSG |  | - | ..
1.9.4.5: Training of "Notice Board" administrators in all public administration bodies for content management and creation of user accounts | Q4 2022 | MPALSG |  | - | ..
1.9.4.6: Promotion of the "Notice Board" as an internal communication channel for civil servants in public administration bodies through an internal campaign (presentations, email, video clips, posters) | Q4 2022 | MPALSG |  | - | ..
1.9.4.7: Annual survey on awareness of the process and results of the PAR among employees in public administration bodies, via online survey (sending a link by email and posting on the Notice Board) | Q4 2022 | MPALSG |  | - | ..
1.9.4.8: Conducting annual surveys of public administration employees on their awareness of the PAR process and results through focus groups with SAB (2 groups) and LSGU (4 groups) officers | Q4 2022 | MPALSG | Not commenced | - | The research was not conducted in 2024 due to lack of financial resources, while it was previously conducted with the support of the EU project "Visibility and Communication of Public Administration Reform"... |  |  | The research is planned to be conducted within the framework of the SBS IPA 2022 comparative support.
.
Measure 1.9.5: Increasing visibility and communication of the PAR process and achieved results
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of affirmative and neutral posts (feature stories) about the public administration reform in the media (Number) |  |  | 1,178 (2020) |  | 1,725 | - | not measured
Presence of PAR topics on institutions' websites and their social media pages/profiles (Number) |  |  | 146 (2020) |  | 213 | - | not measured
Proportion of citizens who are informed about the results of the public administration reform (%) |  |  | 0 (2020) |  | 37 | - | No research was conducted in 2024.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.5.1: SAB and LSGU capacity mapping for PAR communication (organisation of public relations activities, communication channels, technical capacities, level of training, etc.). Survey and two focus groups. | Q2 2021 | MPALSG |  | - | ..
1.9.5.2: Development of PAR Communication Standards with guidelines for the application of unique visual solutions, targeted messages and slogans ensuring that SABs and LSGUs coherently inform the public about PAR | Q2 2021 | MPALSG |  | - | ..
1.9.5.3: Distribution of PAR communication standards to all SABs and LSGUs | Q3 2021 | MPALSG |  | - | ..
1.9.5.4: Developing and updating guidelines for creating and managing SAB and LSGU profiles on social networks | Q4 2022 | ITE Office |  | - | ..
1.9.5.5: Workshops for SAB managers (state secretaries and assistant ministers) and PR officers on the importance of communicating the PAR process and results achieved. | Q3 2021 -> Q3 2022 | NAPA | Completed | - | ..
1.9.5.6: Training and individual coaching for SAB leaders to improve communication skills necessary for communicating with PAR (public speaking, crisis communication, etc.). | Q4 2022 | NAPA | Completed | - | ..
1.9.5.7: Advanced education of SAB PRs to improve PAR communication - workshops and mentoring sessions with experts in specific areas of communications, training, digital platforms, etc.) | Q4 2022 | NAPA | Completed | - | ..
1.9.5.8: Building the capacity of local government PR services to more efficiently and effectively communicate PAR results through training and creating a network of local PRs. | Q4 2022 | NAPA | Completed | - | ..
1.9.5.9: Building the capacity of the media to report on PAR and achieved results, through training and briefings | Q4 2022 -> Q4 2025 | MPALSG | Not commenced | - | Due to lack of financial resources, there was no organisation of media briefings in the form of meetings with journalists and training for journalists with the aim of transferring knowledge on important topics in the field of public administration reform. |  |  | The activity will continue until the end of 2025. Direct donor support is planned for the continuation of implementation (EU, IPA 2022 - sector budget support).
1.9.5.10: Preparing and implementing media promotion of the process and achieved results of the PAR (quarterly, four areas per year, through media announcements in national (up to 15 national media with 1-3 features per topic) and local media (up to 25 local media with 3 features per topic) and promotion of posts on social networks) | Q4 2022 -> Q4 2025 | MPALSG | In progress | - | Four interviews and a series of articles were published covering the topic of public administration reform: https://mduls.gov.rs/saopstenja/zaric-kovacevic-reforma-javne-uprave-u-fokusu-i-2025-godine/?script=lat https://www.youtube.com/watch?v=tSGGv7ZX8vk https://www.politika.rs/sr/clanak/636443/reforma-javne-uprave-uslov-je-za-pristupanje-eu https://www.novosti.rs/vesti/politika/1418804/intervju-jelena-zaric-kovacevic-ustedeli-gradjanima-milione-sati-salterima https://www.euronews.rs/srbija/politika/145402/zaric-kovacevic-srbija-je-ucinila-javnu-upravu-otvorenijom-i-po-meri-gradana/vest https://www.telegraf.rs/vesti/politika/3967226-zaric-kovacevic-mehanizam-medjuopstinske-saradnje-u-duhu-transformacije-javne-uprave https://www.youtube.com/watch?v=6zfyex5RKcY https://www.novosti.rs/c/vesti/politika/1409664/zaric-kovacevic-nisu-promovisala-uslugu-pisarnica-posetila-centar-drago-vidim-niski-centar-dobro-funkcionise https://www.rts.rs/vesti/drustvo/5501010/e-pisarnica-e-uprava-ministarka-zaric-kovacevic.html https://www.svrljig.info/2025/01/24/ministarka-jelena-zaric-kovacevic-i-predsednik-opstine-miroslav-markovic-svecano-otvorili-jum/.. |  |  | This activity will be continued.
1.9.5.11: Raising citizens' awareness of their rights before public administration bodies when it comes to services - through posts on social media, media announcements in national and local media, posters in SABs and LSGUs | Q4 2021 | MPALSG |  | - | ..
1.9.5.12: Promoting the SKIP Centre as a centre for training public administration officers and citizens in the use of information technologies, with a special focus on the use of e-services (posts on social media, posts on institutional websites, guest appearances by SKIP representatives in national and local media) | Q4 2025 | MPALSG |  | - | ..
1.9.5.13: Support for the promotion of e-Informer for public administration bodies (positive effects of increasing publicity in the work of public administration bodies) - towards public administration bodies via the Notice Board application, towards citizens via posts on social media, institutional websites) | Q4 2023 -> Q4 2024 -> Q4 2025 | Commissioner for information of public importance and protection of personal data |  | - | ..
1.9.5.14: Promoting prepared brochures/guidelines (in printed and electronic form) for the implementation of system solutions related to management accountability in public administration bodies, as well as related training and expert meetings, via the Notice Board application, email. | Q4 2025 | MoF |  | - | ..
1.9.5.15: Promoting the process and results of the Tax Administration transformation as topic for segments of continuous comprehensive media promotion | Q4 2022 | MoF - PA |  | - | ..
1.9.5.16: Promoting the implementation of internal financial control in the public sector - benefits for citizens, through media briefings, features in national and local media and posts on social media. | Q4 2022 | MoF |  | - | ..
1.9.5.17: Promoting the Citizens' Guide through the Budget of the Republic of Serbia, through guest appearances by representatives of the Ministry of Finance in the media, posts on social media, and promotional video formats. | Q4 2022 | MoF |  | - | ..
1.9.5.18: Promoting the Citizens' Guide through the Budget of the of Local Self-Government Units, through guest appearances by LSGU representatives in the media, posts on social media, and promotional video formats. | Q4 2022 | MPALSG |  | - | ..
1.9.5.19: Promoting the internal labour market as a career management tool by placing texts and video materials on the Notice Board application and the HRMS website. | Q4 2022 | HRMS |  | - | ..
1.9.5.20: Promoting the Registry of Administrative Procedures (organisation of a presentation event, conducting media promotion on national and local media and social networks) | Q2 2021 | PPS |  | - | ..
1.9.5.21: Promoting the e-Paper Programme (visual and technical improvement) | Q4 2021 | PPS |  | - | ..
1.9.5.22: Updating and further developing the segment of the MPALSG website dedicated to PAR: regular publication of content, technical improvements (visual redesign, database, new functionalities). | Q4 2022 | MPALSG |  | - | ..
1.9.5.23: Promoting the participation of the Republic of Serbia in the Open Government Partnership (visual and technical improvement and promotion of the website ogp.rs (priority), design of various promotional materials, including the current Action Plan and the report on the implementation of the previous one, support for the organisation and promotion of events dedicated to the Partnership). | Q4 2025 | MPALSG | In progress | - | ..
1.9.5.24: Promoting the One-Stop Shop as a new form of providing services to citizens (conducting media promotion on national and local media and social networks, production of video material, guest appearances in the media). | Q4 2022 | MPALSG |  | - | ..
1.9.5.25: Promoting good practice examples in the use of open data | Q4 2022 | MPALSG |  | - | ..
1.9.5.26: Promotiong the public procurement portal | Q4 2022 | Public Procurement Office |  | - | ..
1.9.5.27: Promoting eServices (media announcements, video tutorial clips, social media posts for 5 new electronic services each year). | Q4 2022 | ITE Office |  | - | ..
1.9.5.28: Promotiong citizen participation in the participatory budgeting process in local self-government units - examples of good practice with the promotion of municipalities and cities that implement this process. | Q4 2022 | MPALSG |  | - | ..
1.9.5.29: Competition for the best managed social media profiles (focus on two-way communication with citizens) | Q4 2022 | MPALSG |  | - | ..
1.9.5.30: Celebrating International Public Service Day on 23 June (organising a competition for the best public service officer, rewarding LSGUs for their achievements, etc.). | Q4 2022 | MPALSG |  | - | ..
1.9.5.31: Providing graphic design and translation services for the PAR annual report | Q4 2025 | MPALSG |  | - | ..
1.9.5.32: Promoting the most important results mapped by the Annual Report on the Implementation of the PAR Strategy 2021 - 2025 Action Plan | Q4 2022 | MPALSG |  | - | ..