## All activities export_1
Annual Report on the Implementation of the 2024 Action Plan for: |  |  |  |  | Action Plan for Implementation of the Programme for the Improvement of Public Policy and Regulatory Reform Management for 2025, with a review of previously implemented activities
Institution responsible for coordination and reporting: |  |  |  |  | PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Public policy document for which the action plan was determined: |  |  |  |  | Programme for the Improvement of Public Policy and Regulatory Reform Management with the Action Plan for the period from 2021 to 2025
Overall objective 1: Quality of public policy documents and regulations has been improved
Document proponent: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Regulatory quality indicator – the World Bank rank (percentage rank (from 0 to 100)) |  |  | 60.1 (2019) |  | 64 | 56.6 | Indicator value is for 2023 There is still no value for 2024.
Indicator of compliance and policy planning quality (Scale (1-5)) |  |  | 0 (2021) |  | 4 | 4 | The achieved value of the indicator could not be calculated in full, given that at the time of the report cut-off, the GAWP (The Government`s Annual Work Plan) for 2024 had not been adopted.
.
Specific objective 1.1: Regulatory reform In function of improving the business environment and reducing unnecessary burdens for citizens and economy
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of adopted laws containing a complete impact assessment in the total number of adopted laws for which it was necessary to conduct an impact assessment during one calendar year (%) |  |  | 30.4 (2020) |  | 50 | 31.1 | In 2024, the National Assembly did not pass laws in the first two quarters, so laws were prepared and passed in a short period of time, which affected the value of the performance indicator.
Share of adopted regulations containing a complete impact assessment in the total number of adopted regulations for which it was necessary to conduct an impact assessment during one calendar year (%) |  |  | 58.3 (2020) |  | 62 | 77.6
.
Measure 1.1.1: Establishing a system for monitoring changes in the number of valid regulations on an annual basis by area and monitoring the adoption of by-laws in accordance with the prescribed deadlines for their adoption
Institution in charge: GENERAL SECRETARIAT OF THE GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of the by-laws adopted within the deadlines stipulated by the new adopted laws during a calendar year in the total number of by-laws that should be adopted during that calendar year in accordance with the Government`s Annual Work Plan (%) |  |  | 56 (2023) |  | 56 | - | Deadline for activities has been postponed to the 4th quarter of 2025.
A mechanism has been established for regular annual reporting on the adoption of by-laws within the prescribed deadlines through the Government`s Work Plan/Government`s Work Report (0 - no, 1 - yes) |  |  | 0 (2020) |  | 1 | - | Deadline for activities has been postponed to the 4th quarter of 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.1.1.1: Preparation of a three-year report on changes in the regulatory framework by areas and types of regulations | Q2 2025 | PPS | In progress | - | During the period 2022-2024, materials for the report were prepared |  | /. | The report will be prepared during February 2025.
1.1.1.2: Establishment of a mechanism for regular annual determination of the number and reporting on by-laws that have not been adopted within the established deadlines through the Government`s Work Plan/Government`s Work Report | Q4 2025 | GENSEC |  | - | ..
1.1.1.3: Analysis of changes in the regulatory framework and development of recommendations to achieve greater predictability of the business environment for business operations of economic entities and the lives of citizens | Q3 2025 | PPS | In progress | - | During the period 2022-2024, materials for conducting the analysis were prepared and negotiations with the donor are underway regarding the engagement of experts. |  |  | After the selection of experts, the analysis is expected to be prepared.
1.1.1.4: Strengthening the capacity of the Government's GenSec for establishment of a mechanism for regular annual determination of the number and reporting on by-laws that have not been adopted within the established deadlines through the Government`s Work Plan/Government`s Work Report | Q4 2025 | GENSEC |  | - | ..
.
Measure 1.1.2: Improving the framework for systematic monitoring of the quality and effectiveness of regulations (ex-post analysis)
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Regulation on the Regulatory Impact Assessment was adopted, which regulates the methodology of ex-post evaluation (0 - no, 1- yes) |  |  | 0 (2023) |  | 1 | 0 | Adoption of the Regulation on the Regulatory Impact Assessment was slowed down due to the coordination with stakeholders regarding the regulation of the consultation process. Proposal of the regulation is in the process of gathering opinions.
Share of adopted regulations that, within the report on the conducted impact assessment, have a presentation of the results of the regulation being changed in the total number of adopted regulations for which it is necessary to present the results of the regulation being changed (%) |  |  | 76 (2023) |  | 78 | 65.9 | During 2024, there was a need to pass a large number of laws and regulations in a short period of time, which affected the value of the performance indicator.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.1.2.1: Improving the content of ex-post analysis for regulations and supplementing the questions that SABs answer when preparing ex-ante and ex-post analyses by amending the Regulation on the Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on the Regulatory Impact Assessment suggested regulation of the methodology for implementing ex-post analysis. Proposal of the Regulation is in the process of gathering opinions. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.2.2: Criterion and mechanism established for determining priority regulations for which ex-post analysis should be conducted on an annual basis, regardless of whether their amendment is planned in that year, through an amendment to the Regulation on the Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on the Regulatory Impact Assessment suggested that the Government may determine a list of regulations for which ex-post analysis will be conducted. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.2.3: Improving the Public Policy and Regulatory Impact Assessment Handbook in the part of conducting ex-post regulatory impact analysis, in accordance with the amendments to the Regulation on Regulatory Impact Assessment | Q3 2025 | PPS | not started | - | .. |  | Before improving the handbook, it is necessary to adopt the Regulation on the Regulatory Impact Assessment. Adoption of the Regulation on the Regulatory Impact Assessment was slowed down due to the coordination with stakeholders regarding the regulation of the consultation process. | Adoption of the Regulation on the Regulatory Impact Assessment, which is expected in Q1 of 2025, is a prerequisite for implementation of the activity.
1.1.2.4: Establishment of the annual list of priority regulations for which an ex-post analysis should be conducted on an annual basis, in accordance with the Regulation on the Regulatory Impact Assessment | Q4 2025 | PPS | not started | - | .. |  | Before preparing the annual list of priority regulations for which an ex-post analysis should be conducted, it is necessary to adopt the Regulation on the Regulatory Impact Assessment. Adoption of the Regulation on the Regulatory Impact Assessment was slowed down due to the coordination with stakeholders regarding the regulation of the consultation process. | Adoption of the Regulation on the Regulatory Impact Assessment, which is expected in Q1 of 2025, is a prerequisite for implementation of the activity.
1.1.2.5: Developing a training programme for conducting ex-post analyses (TOT for PPS and SAB/IUPDMS) and implementing ToT | Q3 2025 | PPS | not started | - | .. |  | Before developing a training programme, it is necessary to adopt the Regulation on the Regulatory Impact Assessment. Adoption of the Regulation on the Regulatory Impact Assessment was slowed down due to the coordination with stakeholders regarding the regulation of the consultation process. | Adoption of the Regulation on the Regulatory Impact Assessment, which is expected in Q1 of 2025, is a prerequisite for implementation of the activity.
1.1.2.6: Include training related to ex-post regulatory impact analysis in the annual NAPA training programme | Q4 2025 | PPS |  | - | ..
1.1.2.7: Network of experts established for ex-ante and ex-post analyses from SABs (including employees of Analytical Units) | Q4 2025 | PPS | not started | - | /.. |  | /. | Coverage of the network will be considered, as well as the existing capacities of the state administration for functioning of the network.
1.1.2.8: Organising an annual event on Impact Assessment | Q4 2025 | PPS | In progress | - | The annual event on the Regulatory Impact Assessment was held in 2022 and 2023, while it was not held in 2024 due to lack of financial resources. |  | The annual event on the Regulatory Impact Assessment was not held in 2024 due to lack of financial resources. | Activities are underway to secure donor funds for organising the event in the Q3 of 2025.
1.1.2.9: Improvement of the PPS website in terms of presenting tools for conducting the Public Policy and Regulatory Impact Assessment and examples of good practice | Q4 2022 | PPS | Completed | - | /.. |  | /. | /.
.
Measure 1.1.3: Improving the business environment and reducing administrative costs for economy and citizens through the systematic use of impact analysis tools (MSME test, administrative cost measurement and checklist of regulatory impact assessment in relation to competition)
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of adopted regulations for which administrative costs/savings and impact on MSMEs and competition were estimated within the report on the conducted impact assessment, compared to the total number of adopted regulations for which it was necessary to estimate administrative costs and impact on MSMEs and competition (%) |  |  | 6.8 (2023) |  | 10 | 10.3
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.1.3.1: Redefining the obligation to apply the MSME test and present the results within the Regulatory Impact Assessment for all regulations that affect the business environment, through the amendment of the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on Regulatory Impact Assessment foresees a special issue within the methodology for conducting ex-ante impact assessment and preparing reports related to impact assessment for micro, small and medium-sized enterprises conducted applying MSME test. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.3.2: Development of web application of MSME test | Q4 2025 | PPS | In progress | - | During 2024, a technical specification was developed and a competition is underway to select a contractor to develop the application. |  |  | Selection of the contractor, after which the application is planned to be developed by the end of the 2nd quarter of 2025.
1.1.3.3: Redefining the obligation to calculate administrative costs and present the results within the Regulatory Impact Assessment for all regulations that affect the administrative burden for end users, through the amendment of the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on Regulatory Impact Assessment foresees a special issue within the methodology for conducting ex-ante impact assessment and preparing reports related to impact assessment for administrative costs. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.3.4: Redefining the obligation to assess impact on competition and present the results within the Regulatory Impact Assessment for all regulations that affect the competition, through the amendment to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on Regulatory Impact Assessment foresees a special issue within the methodology for conducting ex-ante impact assessment and preparing reports related to assessment of impacts on competition. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.3.5: Improving the Public Policy and Regulatory Impact Assessment Handbook in respect of application of tests, in accordance with the amendments to the Regulation on Regulatory Impact Assessment | Q3 2025 | PPS | not started | - | .. |  | Before improving the handbook, it is necessary to adopt the Regulation on the Regulatory Impact Assessment. Adoption of the Regulation on the Regulatory Impact Assessment was slowed down due to the coordination with stakeholders regarding the regulation of the consultation process. | Adoption of the Regulation on the Regulatory Impact Assessment, which is expected in Q1 of 2025, is a prerequisite for implementation of the activity.
1.1.3.6: Implementation of at least one e-training on the application of economic impact analysis tools | Q4 2025 | NAPA |  | - | ..
1.1.3.7: Providing support to authorities in conducting tests | Q4 2025 | PPS | In progress | - | Support was provided for calculating the reduction of administrative costs in two cases. |  | /. | After the launch of the web application for the MSME test, support will be provided for this test as well.
.
Measure 1.1.4: Improving the quality of regulations by introducing a gender perspective
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of adopted regulations for which impacts on gender equality were assessed within the Report on the Conducted Impact Assessment |  |  | 0 (2023) |  | 2 | 0 | There is a noticeable lack of capacity and interest among the competent proponents of regulations to independently conduct assessment of impacts on gender equality
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.1.4.1: Redefining the obligation to apply gender equality and present the results within the Regulatory Impact Assessment for all regulations that affect the gender equality, through the amendment to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on Regulatory Impact Assessment suggests redefined obligation to apply gender equality test and present the results within the Regulatory Impact Assessment for all regulations that affect the gender equality. Proposal of the Regulation is in the process of gathering opinions. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.4.2: Gender equality test and instructions for its application harmonised with the new law regulating gender equality | Q2 2022 | PPS | Completed | - | /.. |  | /. | /.
1.1.4.3: Training on the application of the GE test for 20 civil servants in a specific priority area for gender equality | Q4 2022 | PPS | Completed | - | /.. |  | /. | /.
1.1.4.4: Training programme developed to use gender equality test | Q2 2022 | PPS | Completed | - | /.. |  | /. | /.
.
Measure 1.1.5: Improving the use of impact assessment in the process of harmonising domestic legislation with the EU acquis
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of adopted regulations during a calender year to be harmonised with the EU acquis for which a complete impact assessment has been conducted, which also includes an analysis of comparative practice in the total number of adopted regulations that are harmonised with the EU acquis during the calendar year (%) |  |  | 21.7 (2023) |  | 25 | 23.8 | During 2024, there was a need to pass a large number of laws and regulations in a short period of time, which affected the value of the performance indicator.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.1.5.1: Determining the specificity of impact assessment for regulations harmonising with the EU acquis in the Regulation on the Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | Proposal of the Regulation on Regulatory Impact Assessment foresees a special issue within the methodology for conducting ex-ante impact assessment and preparing reports related to impact assessment for regulations harmonising with the EU acquis. |  |  | Adoption of the Regulation on the Regulatory Impact Assessment which is expected in Q1 of 2025.
1.1.5.2: Providing support to the SABs in conducting impact assessmens for at least two regulations harmonising with EU regulation, which will be undertaken once the relevant legal framework is in place. | Q4 2025 | MEI |  | - | .
.
Specific objective 1.2: Strengthening capacities and application of instruments for quality development and monitoring of public policies and regulations
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of adopted PPDs during one calendar year that contain a complete impact assessment compared to the total number of adopted PPDs for which it is necessary to make an impact assessment (%) |  |  | 50 (2020) |  | 90 | 50 | Out of a total of 14 PPDs adopted by the Government in 2024, for 6 PPDs an impact assessment was mandatory. Out of a total of these 6 PPDs, 3 PPDs had a complete impact assessment (50%), while 3 PPDs had a partial impact assessment (50%).
.
Measure 1.2.1: Organisational establishment of internal units for planning documents and management support (IUPDMS)
Institution in charge: GENERAL SECRETARIAT OF THE GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of ministries that have established internal units for planning documents and management support (IUPDMS) in relation to the total number of ministries that are obliged to specify the internal units for planning documents and management support (%) |  |  | 0 (2020) |  | 80 | - | Relevant data regarding the indicator will be available after the Guidelines for the Establishment and Operation of the IUPDMS (activity 1.2.1.2) are adopted, given that they should specify the relevant provisions of the Regulation on the Principles for Internal Organisation and Systematisation of Jobs in Ministries, Special Organisations and State Services.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.2.1.1: Preparation of an Analysis on the Strategic and Regulatory Framework for the Establishment of Analytical Units with a review of already established analytical units with conclusions and recommendations for improving the framework and facilitating the establishment of fully functional analytical units | Q1 2025 | MoF | Completed | - | With the support of the UNDP project "Support to Public Financial Management", a detailed Report on the Strategic and Regulatory Framework for the Establishment of Analytical Units with conclusions and recommendations for improving the framework and facilitating the establishment of fully functional analytical units was prepared.
1.2.1.2: Drafting and adoption of the Guidelines for the Establishment and Operation of the IUPDMS,which are adopted by the Government through its act | Q1 2025 | MPALSG | In progress | - | Through UNDP project "Support to Public Financial Management", an expert has been engaged to meet the needs of developing the Guidelines. Questionnaires have been prepared to obtain the necessary information on the current situation in relevant institutions when it comes to analytical units, the need for their establishment and the tasks they would perform. The responses received from this questionnaire will serve as the basis for developing the Guidelines for the Establishment and Operation of the IUPDMS. |  |  | The questionnaire is planned to be distributed to all line ministries. After collecting the information from the questionnaire, focus groups will be organised with representatives of relevant organisations. This will be followed by development of Guidelines for the Establishment and Operation of the IUPDMS or analytical units.
1.2.1.3: Support to implementation of the Guidelines in selected SABs. | Q4 2025 | SAB |  | - | ..
.
Measure 1.2.2: Improving the skills of managers and civil servants in preparing, monitoring and reporting on the implementation of planning documents and a more effective financial management and control system
Institution in charge: NATIONAL ACADEMY OF PUBLIC ADMINISTRATION
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Training programme for managers and civil servants on data management developed (0 - no, 1- yes) |  |  | 0 (2020) |  | - | 1 | In the general training programmes for civil servants and managers in state bodies adopted by the NAPA for 2024, data management training is included within a special thematic unit "Data Management".
Number of managers and civil servants who have successfully completed data management training provided for in the annual training programme (Number (annually)) |  |  | 0 (2020) |  | 50 | 523 | Within the thematic unit "Data Management", 33 training sessions were held, and 523 civil servants were trained in 2024 (of which 110 were managers).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.2.2.1: Analysis of the required competencies of IUPDMS employees with recommendations | Q4 2021 | HRMS | Completed | - | ..
1.2.2.2: Harmonisation of the Regulation on Determining Competencies for the Work of Civil Servants in accordance with the recommendations from the previous activity | Q4 2021 | HRMS | Completed | - | ..
1.2.2.3: Analysis of available training sessions in annual training programmes related to data management (collection, storage, analytical processing and exchange) | Q4 2021 | NAPA | Completed | - | ..
1.2.2.4: Development of a training programme for managers and civil servants for data management (collection, storage, analytical processing and exchange) (it will be implemented complementary to the activities envisaged in the Action Plan for the period 2021-2025 for implementation of the PADS in the RS for the period 2021-2030) | Q1 2022 | NAPA | Completed | - | ..
1.2.2.5: Piloting the created training programme for managers and civil servants in data management (collection, storage, analytical processing and exchange) | Q4 2022 | NAPA | abandoned | - | Piloting the training programme for data management is not necessary, because the training has become part of the regular training organised by NAPA since 2022 with the adoption of general training programmes for civil servants and managers in state bodies.
1.2.2.6: Implementation of at least 2 training sessions for managers and civil servants for data management (collection, storage, analytical processing and exchange) every year, in accordance with the annual training programme(it will be implemented complementary to the activities envisaged in the Action Plan for the period 2021-2025 for implementation of the PADS in the RS for the period 2021-2030) | Q4 2025 | NAPA | In progress | - | Within the general training programmes for the republican and local levels, special thematic units Data Management have been developed. A total of 33 training sessions were held in 2024. Within this thematic unit, 523 participants were trained, of which 110 managers in 2024.
.
Measure 1.2.3: Laying the foundations for introducing a systematic approach to data management
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Standards for data management (collection, storage, analytical processing and exchange) were developed from SAB records for one planning document (0 - no, 1 - yes) |  |  | 0 (2023) |  | 0 | 0 | Development of standards for data management is planned for the 2nd quarter of 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.2.3.1: Support in mapping/inventory of data collected by the selected SAB in its work, which are necessary for the preparation, monitoring of implementation, reporting on implementation and evaluation of planning documents and regulations | Q1 2025 | PPS | In progress | - | Activities in mapping/inventory of data have been initiated, which are used by the PPS in its work and which are necessary for the preparation, monitoring of implementation, reporting on implementation and evaluation of the APIGP. All relevant SABs involved in the APIGP development and reporting process participate in the data mapping/inventory process. |  |  | Completion of work on mapping/inventory of data in the 1st quarter of 2025, after which development of data management standards for monitoring implementation and reporting on implementation for the APIGP will begin
1.2.3.2: Development of standards for data management required for monitoring implementation and reporting on the implementation for one planning document | Q2 2025 | ITE Office |  | - | ..
1.2.3.3: Piloting the standards for data management for monitoring implementation and reporting on the implementation for one planning document | Q3 2025 | PPS |  | - | ..
1.2.3.4: Development of report based on piloted standards for monitoring implementation and reporting on the implementation for one planning document | Q4 2025 | ITE Office |  | - | ..
.
Measure 1.2.4: Providing analytical foundations for public policy making
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of research conducted for the purpose of making public policies (Number (cumulative)) |  |  | 0 (2020) |  | 3 | 24
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.2.4.1: Development and activation of the "Policy Club" internet platform, as well as its promotion in order to form a network of experts and establish a database of their works and analyses of importance for making the public policies | Q4 2022 | PPS | Completed | - | ..
1.2.4.2: Analysis of problems in the implementation of public policies and definition of challenges and specific needs of the SABs, taking into account the priorities from the APIGP | Q4 2025 | PPS | In progress | - | Situation analyses (diagnostics) were conducted in the following areas: energy, agriculture, construction, environmental protection and culture in order to define challenges and formulate results for the new APIGP 2024-2027. |  |  | Preparation of analyses according to the specific needs of the SABs.
1.2.4.3: Preparation of analyses with the aim of implementing the reform priorities of the Government of the RS in order to improve the business environment and presenting the results | Q3 2025 | PPS | In progress | - | Within component 3: Flexible Technical Support Instrument, EU4BE project, seven projects were prepared in 2024, the implementation of which has begun (Regulatory impact assessment related to environment affecting business of the SMEЕ sector, with the aim of improving the system of payment of eco-taxes, municipal waste fees, etc. with recommendations and proposal for future measures; Analysis of the institutional framework in the field of public administration service delivery; Analysis and survey for calculating the share of administrative costs in GDP for 2023; Analysis of technical possibilities for the reform of electronic payment of parafiscal obligations with recommendations for improving existing technical solutions and developing new solutions; Survey of 1000 enterprises 2024; Support for the preparation of 5 necessary analyses of different trade sectors, for further development of the Trade Development Strategy and Action Plan for the period of 2025 to 2027; Analysis of the required capacities of the Republic Inspectorates with an action plan for employment and revision of salary bands) Also, during 2024, the implementation of projects that began in the previous year continued (Analysis and Action Plan 2024 -2026. AI Strategies of Serbia; Impact analysis of implementation of the Programme for Simplified Administrative Procedures and Regulations "e-Paper" for the period 2019-2023; four projects in the field of Quality Infrastructure-Metrology)." |  |  | Further implementation of selected projects.
1.2.4.4: Development of a calculator for calculating the costs of implementing the planning documents | Q4 2025 | PPS | In progress | - | Based on developed ToR, the selection of a consultant is underway to develop a technical specification for a calculator for calculating the costs of implementing the planning documents within the framework of the Operation "Improving Public Finance Management for the Green Transition". |  |  | Development of a technical specification on the basis of which the calculator will be developed.
1.2.4.5: Improvement of the LSGU Business Information System (LSGU Analytical Service and LSGU Analytical Reporting System) - database at the LSGU level | Q4 2025 | PPS | In progress | - | Data for 2023 was collected from relevant institutions, for 519 indicators from eight areas defined in the LSGU Business Information System, processed and entered into the LSGU database.
.
Measure 1.2.5: Improving existing and initiating and creating innovative solutions in public policies based on data and research on end-user needs
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of piloted innovative solutions in public policy making (Number (cumulative)) |  |  | 0 (2020) |  | 5 | 4 | The start of the project with UNICEF has been postponed to 2025.
Number of tested innovative ideas for improving existing public services (Number (cumulative)) |  |  | 0 (2020) |  | 3 | 3
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.2.5.1: Two innovative solutions designed and piloted in different areas of public policies | Q4 2022 -> Q4 2025 | PPS | In progress | - | Two innovative solutions have been designed: online tickets for museums in the field of culture and a group ticket for 4 museums. Negotiations with a potential donor and partner on UNICEF project are still underway, so the start of the activity has been postponed to 2025. |  |  | UNICEF's response is awaited in order to take the next steps.
1.2.5.2: Research and analysis of existing public services and testing of one innovative idea/solution with the aim of improving it | Q4 2022 -> Q4 2025 | PPS | In progress | - | An analysis of services and cooperation with the TOS and TO Soko Banja and Kragujevac was conducted in order to create new services for tourist organisations.
1.2.5.3: Promotion of innovative solutions and new approaches in creating public policies on the PPS website and through social networks, as well as through the organisation of annual conferences and networking with all stakeholders | Q4 2025 | PPS | In progress | - | A conference was held in September 2024 at which the solution of a unified ticket for four museums was promoted. The news about the unified ticket was published on the websites of the museums, the Ministry of Culture and PPS. The Ethnographic Museum has introduced the possibility of online ticket purchase, as well as cashless payment (by card) for tickets.
1.2.5.4: Implementation of training for employees of the PPS on the application of new methods in creating public policies | Q3 2022 | PPS | Completed | - | ..
1.2.5.5: Preparation of training programmes for the creation and implementation of innovative solutions in public policies | Q4 2022 | NAPA | Completed | - | ..
1.2.5.6: Training of civil servants for the creation and implementation of innovative solutions in public policies | Q4 2025 | NAPA | In progress | - | One training course entitled "Application of design thinking methodology in public policies" was held, attended by 9 participants, of which 3 were managers in 2024. |  |  | Training.
.
Specific objective 1.3: Effective coordination of public policies
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Total number of planning areas with revised and optimised planning framework (clear hierarchical structure of PPDs established within planning areas) (Number) |  |  | 1 (2020) |  | 12 | 4 | The following areas have been optimised: public administration, education, public information and youth.
.
Measure 1.3.1: Creating a planning framework and public policies in order to achieve the Government's priorities and sustainable development goals
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Regulation on the Methodology for Drafting Public Policy Documents adopted (0 - no, 1- yes) |  |  | 0 (2023) |  | 1 | 0 | Through the developed Proposal of the Regulation on the Methodology for Drafting Public Policy Documents, 23 planning areas were established, which expressed the real needs and coverage of each of them. Adoption of the Regulation is expected during the first quarter of 2025.
Adopted Regulation on the Procedure for Preparing the Development Plan of the Republic of Serbia (0 - no, 1- yes) |  |  | 0 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.3.1.1: Prioritisation of recommendations from the ex-post analysis of the implementation of regulations for public policy and regulatory reform management | Q4 2021 | PPS | Completed | - | ..
1.3.1.2: Development of the Proposal of the Regulation on the Methodology for Drafting Public Policy Document | Q1 2025 | PPS | Completed | - | Proposal of the Regulation was prepared during 2024.
1.3.1.3: Revision of handbooks developed for comprehensive public policy and regulatory reform management | Q4 2025 | PPS | not started | - | .. |  | The activity could not be started before the adoption of new regulations. | The activity will be implemented during 2025, with the support of the EU4PAR project.
1.3.1.4: Expanding data visualisation on the PPS website related to the Sustainable Development Goals and PPDs | Q2 2025 | PPS | In progress | - | In order to review the contribution of public policy documents to the achievement of sustainable development goals, a mapping of public policy documents was carried out in relation to the goals and targets of sustainable development, based on the indicators of the goals of the applicable PPDs. A visual representation of these connections was developed in a test environment by the end of 2024, through an interactive scheme, and infographics were also developed that show the interconnections between public policy documents, which in synergy contribute to certain sustainable development goals. |  |  | The production version of the interactive scheme and infographics showing the contribution of public policy documents to the achievement of sustainable development goals will be available on the website of the Public Policy Secretariat of the Republic of Serbia from February 2025. The scheme will then be regularly updated, linking newly adopted documents to sustainable development targets.
1.3.1.5: Analysis of selected composite indicators with the aim of improving the position of the Republic of Serbia in international rankings | Q3 2024 | PPS | Completed | - | Data for composite indicators from 29 international surveys were collected, processed and entered into the SQL database. A detailed analysis, which also contains recommendations for improving the position of the Republic of Serbia in international rankings, covered six international surveys. Some of the recommendations from this analysis have been implemented in the APIGP for the period 2024-2027.
1.3.1.6: Activities to secure donor support for the engagement of experts, as well as coordination of activities in the field of project management during the work of experts on development of preparatory material that should support the bodies and structures responsible for the preparation of initial analytics | Q2 2024 -> Q2 2025 | MEI | In progress | - | Bearing in mind the importance of the preparation and adoption of the Development Plan of the Republic of Serbia from the point of view of the EU integration process, in the previous period (starting from November 2023), as part of its competences which concern EU coordination and development aid, MEI provided support to the Public Policy Secretariat in securing EU financial support for the engagement of experts who worked on the preparation of the initial analytics as well as on its management. Expert support was officially initiated in November 2023, when the preparation of documents, defined as the necessary initial analyses for the process of drafting the Development Plan, began. Preparation of the consolidated report "Analytical Support for the Drafting of the Development Plan of the Republic of Serbia", was finalised in May 2024. The report contains analytics in the following areas: Serbia's position in world trade and multilateral economic cooperation, global economic scenarios and a presentation of the basic scenario for the needs of the Development Plan, Serbia's growth model for the period 2010-2022, analysis of the level of development of Serbia in key areas, analysis in the context of defining a development strategy for the upcoming period, proposal and explanation of potential priority goals in accordance with the produced analytics. The report prepared as part of the initial analysis in the identified areas also contains expert recommendations, as well as a proposal for the structure of the Development Plan. This report, among other things, served as a basis for defining areas for which additional in-depth analyses will be conducted, as part of the new expert support. |  | The reason for deviation from full implementation of the activity in the previous deadline is the decision to implement the proposed activity through a new project proposal, which would be nominated for financial support from the EU through unallocated funds. | Approval of the new project proposal by the Unallocated Funds and Project Contracting Group.
1.3.1.7: Preparation of summaries of existing documents proposed under Article 2 of the Regulation on the Procedure for Preparing the Development Plan | Q2 2025 | SAB |  | - | ..
1.3.1.8: Preparation of parts of the analyses provided for in Art. 2 and Art. 4 of the Regulation on the Procedure for Preparing the Draft Development Plan (analysis of the development potential of the RS, international economic trends and assumed obligations) | Q3 2025 | SAB |  | - | ..
1.3.1.9: Development of the Report on the Existing Situation in order to develop Draft Development Plan of the Republic of Serbia | Q4 2025 | PPS | In progress | - | Amendments to the Regulation on the Procedure for Preparing the Draft Development Plan of the Republic of Serbia are currently being prepared, after which the implementation of this activity will begin.
1.3.1.10: Preparation of the baseline based on previous analyses and development of a roadmap for the preparation of the Development Plan of the Republic of Serbia | Q3 2024 -> Q4 2025 | PPS | In progress | - | Drafts of initial analyses in the field of economic movements and trends have been prepared. Also, needs for support for the preparation of sectoral analyses are being identified. MEI and PPS have agreed on a proposed roadmap for the preparation of the Draft Development Plan of the RS. |  | During 2024, activities were slowed down due to the duration of the process of forming a new Government. | Continuation of activities on the preparation of the Draft Development Plan of the RS, after the establishment of the management structure.
.
Measure 1.3.2: Improvement of the areas of planning and implementation of public policies
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Support provided for the optimisation of planning frameworks (0 - no, 1- yes) |  |  | 0 (2023) |  | 1 | 1 | Amendment to the prescribed areas of planning and implementation of public policies is envisaged within the framework of the Regulation on the Methodology for Drafting Public Policy Documents.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.3.2.1: Preparation of a proposal for the Government act on the repeal of planning documents (PPDs without AP, indefinite PPDs, not in compliance with the LPS, etc.) | Q4 2021 | PPS | Completed | - | ..
1.3.2.2: Amendments to the prescribed areas of planning and implementation of public policies within the framework of the Regulation on the Methodology for Drafting Public Policy Documents | Q1 2025 | PPS |  | - | ..
.
Measure 1.3.3: Improvement of the planning compliance at the central level (APIGP, GAWP, NPAA)
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Mechanism for checking compliance of documents at the central level established (0 - no, 1- yes) |  |  | 0 (2020) |  | 1 | 0 | The achieved value of this indicator will be reported in 2025, given that activities are planned for 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.3.3.1: Linking the APIGP with the NPAA in terms of regulations and deadlines for their adoption | Q1 2025 | PPS |  | - | ..
1.3.3.2: Strengthening the technical capacities of the MEI for the preparation and monitoring of the NPAA in the context of harmonising the NPAA and the Government Work Plan (PRGW) | Q4 2025 | MEI | In progress | - | During 2024, the Ministry of European Integration, with technical support (Project "Support to Public Administration Reform in the EU Accession Process", GIZ), developed a new application, as an IT tool, for the preparation and monitoring of the implementation of the NPAA. The application became functional in June 2024, and the new National Programme for the Adoption of the Acquis for the period 2024-2027 was adopted on 24 October 2024. At the proposal of the Ministry of European Integration, the Government adopted the reports on the implementation of the NPAA for the third and fourth quarters of 2024, while the preparation of the report for the first quarter of 2025 is underway. The plan is to revise the deadlines in line with the commitment to implement the most important obligations from the negotiation process by the end of 2026. In cooperation with the General Secretariat of the Government, connection of the new IT solution with the application used for the preparation of the Government's annual work plans has been enabled, with the aim of improving the planning of legislative activities in the process of harmonising legislation and the consistency of the NPAA and the Government Work Plan. At the same time, the new NPAA application enables the improvement of the system for monitoring the implementation of NPAA by the Ministry of European Integration, as well as the reporting structure on the implementation of the NPAA. |  | The Ministry of European Integration continues, with technical support (Project "Support to Public Administration Reform in the EU Accession Process", GIZ), with the development of the NPAA application during 2025. Further development of the application in the part of ​​monitoring and reporting on the implementation of the NPAA is planned. Also, within the framework of the aforementioned technical support, activities are underway aimed at further improving the alignment of the NPAA and the Government's work plan.
1.3.3.3: Adoption of initial criteria for publishing the Conclusions of the Government of the RS on the website of the Government of the Republic of Serbia | Q4 2025 | GENSEC |  | - | ..
.
Measure 1.3.4: Improving monitoring of implementation and reporting on the results of public policies and transparent presentation to the public
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of annual reports on the implementation of AP PPDs entered in UIS in relation to the number of valid AP PPDs entered in UIS that should have been reported for the previous year (%) |  |  | 37.1 (2023) |  | 40 | 43.2 | Out of 37 valid AP PPDs entered in UIS, 16 state administration bodies published annual reports on the implementation of AP PPDs entered in UIS.
Percentage of published Reports on the Implementation of Medium-Term Plans prepared in UIS (%) |  |  | 40 (2023) |  | 50 - 64 | 50 | Out of a total of 46 medium-term planning obliged entities, 24 obliged entities entered medium-term plans for the period 2023-2025 into UIS, and 23 Reports for 2023 on the Implementation of Medium-Term Plans for the period 2023-2025 were prepared and published through UIS.
A report on progress in achieving the goals of public policy documents and their contribution to achieving the sustainable development goals of the UN Agenda 2030 was prepared and published (0 - no, 1- yes) |  |  | 0 (2023) |  | 1 | 0 | Preparation of the Report is in progress.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.3.4.1: Adapting the UIS module for APIGP to the new APIGP format | Q4 2022 | PPS | Completed | - | ..
1.3.4.2: Training for SAB in order to develop and monitor implementation of APIGP | Q1 2022 | PPS | Completed | - | ..
1.3.4.3: Improving the functionality of UIS for the purpose of reporting on PPDs contribution to achievement of sustainable development goals | Q4 2025 | PPS |  | - | ..
1.3.4.4: Development of the report on progress in achieving the goals of public policy documents and their contribution to achieving the sustainable development goals of the UN Agenda 2030 | Q2 2025 | PPS | In progress | - | For the purposes of preparing a report on achieving the goals of the public policy document in the context of the sustainable development goals, the indicators of the public policy documents were systematised and mapped in relation to the indicators of the sustainable development goals, and available data was collected from various relevant sources on the achieved values ​​of the indicators (annual reports on the implementation of action plans for 2023, data directly submitted by the proposers of the public policy documents, data from the SSO, Eurostat, etc.). |  |  | In the coming period, based on the collected data, the first pilot report will be prepared as an incentive for proposers to prepare and publish reports on the implementation of public policy documents within the legally established deadlines.
1.3.4.5: Start of upgrading the UIS with an online monitoring tool (OMT) for the purpose of easily accessible, uniform and transparent electronic reporting to the public on the achieved results of the implementation of public policies | Q1 2025 | PPS |  | - | ..
1.3.4.6: Expanding the functionality of UIS to generate various presentations of reports and statistics on progress in the implementation of public policy documents and medium-term plans | Q4 2025 | PPS |  | - | ..
.
Specific objective 1.4: Increasing the level of participation of civil society, business and other stakeholders in the early stages of preparation of public policies and regulations
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Share of adopted PPDs during the preparation of which a consultative process was carried out in accordance with the LPS in the total number of adopted PPDs in the calendar year (%) |  |  | 100 (2020) |  | 100 | 100 | Out of a total of 14 adopted PPDs by the Government for which it was necessary to conduct consultations in 2024, consultations were conducted for all 14 PPDs (100%).
Share of adopted laws during the preparation of which a consultative process was carried out in accordance with the LPS in the total number of adopted laws in the calendar year (%) |  |  | 35.71 (2020) |  | 75 | 58.3 | In 2024, the National Assembly did not pass laws in the first two quarters, so laws were prepared and passed in a short period of time, which affected the value of the performance indicator. After a decline in 2022 (29%), the value of the indicator has been increasing for the last two years (52.9% and 58.3%).
Share of adopted regulations during the preparation of which a consultative process was carried out in accordance with the LPS in the total number of adopted regulations in the calendar year (%) |  |  | 11.46 (2020) |  | 29 - 31 | 29.7
.
Measure 1.4.1: Establishing and implementing appropriate mechanisms for controlling the quality of consultations and public debates and the efficiency and use of the electronic consultation portal
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of participants who submitted comments via the e-Consultation portal in one calendar year (Number) |  |  | 5 (2023) |  | 10 | 50
Number of comments submitted via the e-Consultation portal in one calendar year (Number) |  |  | 5 (2023) |  | 50 | 204
Share of published reports on consultations conducted on the e-Consultations portal for adopted regulations and PPDs in relation to the total number of adopted regulations and PPDs published on the portal during the calendar year (%) |  |  | 0 (2023) |  | 5 | 6
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.4.1.1: Preparing the amendments to the legal framework for consultations and public debates | Q4 2025 | PPS | In progress | - | The Government adopted the Decision on the Management and Use of the "e-Consultation" Portal and the Conclusion by which, among other things, the PPS is obliged to form a Working Group for amending the legal framework of consultations and public debates. In accordance with the Government Conclusion No.: 030-8354/2024 of 5 September 2024, by the Decision by the managing director of the PPS of 1 November 2024, a Working Group was formed to prepare amendments to the legal framework of consultations and public debates, which will begin work in the first quarter of 2025. |  |  | Holding meetings of the Working Group.
1.4.1.2: Development of a special technical instruction on the method of using the e-Consultation Portal and submission to state bodies | Q4 2021 | ITE Office | Completed | - | ..
1.4.1.3: Training of SABs on the use of the e-Consultation platform | Q4 2021 | ITE Office | Completed | - | ..
1.4.1.4: Regular training of SABs on the use of the e-Consultation platform | Q4 2025 | NAPA | Completed | - | Training sessions are held within the framework of the General Programme for Training Civil Servants, NAPA - Public Participation in the Process of Drafting Regulations and Public Policy Documents.
1.4.1.5: Establishing a system for conducting and monitoring the quality of consultations and public debates (e-Consultations) | Q1 2022 | PPS | Completed | - | ..
1.4.1.6: Preparation of a report on the implementation of the consultation process via the e-Consultation portal as an integral part of the Government Work Report | Q4 2025 | GENSEC |  | - | ..
1.4.1.7: Analysis of the needs for improving the e-Consultation portal | Q4 2023 | PPS | Completed | - | ..
.
Measure 1.4.2: Strengthening the capacity of civil society to participate in the adoption of regulations and planning documents
Institution in charge: MINISTRY OF HUMAN AND MINORITY RIGHTS AND SOCIAL DIALOGUE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024 | Note
Number of departments in whose competence there were topics covered by social dialogue during the calendar year (Number) |  |  |  |  | 16 | 24 | In 2024, the number of departments whose competence included topics covered by social dialogue was exceeded, given that the achieved result was 24, and the planned 16. Deviation from the target value is the outcome of a larger number of dialogues that were not foreseen by the PPDs but were initiated during the year by authorised proposers, on topics of wider social importance and with the participation of a larger number of departments.
Number of CSOs included as members of working groups for development of public policy documents, regulations and temporary bodies (Number) |  |  |  |  | 30 | 365 | Based on the data collected by the Ministry of Human and Minority Rights and Social Dialogue from state administration bodies, the total number of CSOs included in the work of working groups for development of public policy documents and proposals of regulations in 2024 is 201, of which 49 CSOs were included through the public invitation procedure, defined by the Guidelines for the Inclusion of Civil Society Organisations in Working Groups for Development of Public Policy Documents and Drafts, or Proposals of Regulations, and 152 CSOs were included in the working groups by direct invitation. Based on the data provided, the total number of civil society organisations included in the work of temporary working bodies (temporary working bodies whose mandate is ongoing), which were established by the Decision of the Government of the Republic of Serbia and in accordance with Article 22 of the Rules of Procedure of the Government (“Official Gazette of the Republic of Serbia” No. 61/2006 – consolidated text, 69/2008, 88/2009, 33/2010, 69/2010, 20/2011, 37/2011, 30/2013, 76/2014 and 8/2019 – other regulation) at the proposal of the relevant state administration body is 155 CSOs. We note that some organisations participated in several working groups, and that this is not an absolute number of CSOs.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Execution of funds (%) | Explanation of progress |  | Reasons for deviation and measures taken | Future steps for implementation
1.4.2.1: Training of CSOs for participation in the process of adopting regulations and public policy documents, including presenting the importance of the e-Consultation portal | Q4 2025 | MHMRSD | In progress | - | ..
1.4.2.2: Social dialogue (organisation of meetings with various participants: CSOs, academy, international organisations and other social actors depending on the area) | Q4 2025 | MHMRSD | In progress | - | During 2024, 15 social dialogues were held with participation of representatives of state bodies, LSGUs, embassies and international organisations, national minorities, the academic community and CSOs. Dialogues were held in Belgrade, Novi Sad, Kragujevac, Niš, Kruševac and Sjenica.
1.4.2.3: Development of the capacity of civil society for inclusion in the process of preparing PPDs and regulations and monitoring the implementation of PPDs and regulations | Q4 2025 | MHMRSD |  | - | ..