## Sve aktivnosti export_1
Annual Report on the Implementation of the 2024 Action Plan for the: |  |  |  |  | ACTION PLAN FOR 2024 -2025 FOR THE IMPLEMENTATION OF THE PROGRAMME FOR THE REFORM OF THE LOCAL SELF-GOVERNMENT SYSTEM IN THE REPUBLIC SERBIA FOR THE 2021 -2025 PERIOD
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | Programme for the Reform of the Local Self-Government System in the Republic of Serbia for the 2021–2025 period
Overall objective 1: Establishing a local self-government system that enables efficient and sustainable exercise of citizens’ rights to local self-government
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Compliance of the local self-government system with the key principles of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 3- 4 | 3
Proportion of LSG expenses in consolidated public expenditure in the Republic of Serbia (%) |  |  | 14.75 (2019) |  | 16- 17 | 11.7 | In 2024, higher‑than‑planned expenditure execution at the national level (primarily on capital investment projects realisation etc.) led to the share of local government expenditure being lower than expected.
LSGU capacity to apply the principles of good governance (%) |  |  | 39 (2018) |  | - | -
Availability and quality of providing the priority public services of local self-government (Composite scale (1–10)) |  |  | 0 (2020) |  | - | -
.
Specific objective 1: Improving the position and responsibilities of the local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Degree of ratification of the ECLS (Scale (1-5)) |  |  | 3 (2020) |  | 3- 4 | 3
Average value of the Good Governance Index in selected areas: 1) accountability; 2) transparency, openness and participation (%) |  |  | 43 (2018) |  | - | -
Share of adopted laws in relation to the total number of adopted laws which largely relate to LSG, in the preparation of which the LSGUs participated (Composite scale (1–5)) |  |  | 3 (2020) |  | - | -
.
Measure 1.1.1: Continuing harmonisation of the legal framework of the Republic of Serbia for local self-government with the principles of the European Charter of Local Self-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Amendments to the Law on Ratification of the European Charter of Local Self‑Government (ECLS) adopted and a higher level of ECLS acceptance by the Republic of Serbia (0 – no, 1 – yes). |  |  | 0 (2020) |  | 1 | 0 | A Draft Law amending the Law on Ratification of the European Charter of Local Self‑Government has been prepared and transmitted to the Government, which endorsed the draft and forwarded it to the National Assembly of the Republic of Serbia.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.1.1: Preparation of the Draft Law amending the Law on Ratification of the European Charter of Local Self‑Government, and its submission to the Government so it can endorse the draft. | Q4 2024 | MPALSG | Completed | - | A Draft Law amending the Law on Ratification of the European Charter of Local Self‑Government has been prepared and transmitted to the Government, which endorsed the draft and forwarded it to the National Assembly of the Republic of Serbia... |  |  | Adoption of the Law
1.1.1.2: Development of an analysis on the need to align systemic and sector‑specific legislation with the ratified principles of the ECLS. | Q4 2024 -> Q4 2025 | MPALSG | Has not commenced | - | A Draft Law amending the Law on Ratification of the European Charter of Local Self‑Government has been prepared and transmitted to the Government, which endorsed the draft and forwarded it to the National Assembly of the Republic of Serbia... |  | A prerequisite for implementation is the adoption of the Law amending the Law on Ratification of the European Charter of Local Self‑Government. | Adoption of the Law
.
Measure 1.1.2: Improving the electoral system and strengthening the capacity of local administration to conduct local elections
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Proportion of MEC/CEC presidents and secretaries certified to conduct local election procedures (%) |  |  | 0 (2020) |  | 50 | 0 | The indicator has not been achieved because implementation requires amendments to the legal framework that would regulate the issuance of certificates.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.2.1: Development of an analysis to establish the legal framework for implementing mandatory professional training for the leadership of local electoral commissions (primarily the presidents and secretaries of local electoral commissions). | Q4 2024 -> Q4 2025 | MPALSG | Has not commenced | - | .. |  | The activity has not been realised because implementation requires amendments to the legal framework that would regulate the issuance of certificates. | Amending the legal framework to regulate the issuance of certificates.
1.1.2.2: Development of a Handbook for Conducting Local Elections. | Q4 2024 -> Q4 2025 | MPALSG | Completed | - | Amendments to the legislative framework for conducting local elections were adopted only on 23 April 2024, a mere three days before the elections were announced; consequently, drafting the Handbook for Conducting Local Elections was not feasible. Instead of the handbook, the SCTM prepared 56 model acts for conducting local elections—envisaged as integral parts of the planned handbook—which it sent to its members on 26 April, the day the elections were announced. |  | Because the amendments to the legal framework were adopted only on 23 April 2024, just three days prior to the calling of the local elections, preparation of the handbook proved impossible, and guidance materials were therefore delivered in the form of model local documents. | In earlier years the SCTM had published a Handbook for Local Elections in the period immediately preceding elections, once any relevant legal framework modifications had entered into force. In that same vein, the SCTM will embark on drafting a new handbook after any future amendments to the Local Elections Act that may precede the 2028 local elections.
1.1.2.3: Analysis of the possibilities for implementing mandatory professional training for the leadership of local electoral commissions and issuing certificates. | Q3 2024 -> Q4 2025 | MPALSG | Has not commenced | - | .. |  | The Analysis was not conducted due to the lack of funds. | Provision of funds and development of analysis.
1.1.2.4: Development and implementation of a national e‑training programme for obtaining certificates for the conduct of local electoral procedures (primarily for the permanent membership of electoral commissions). | Q4 2024 -> Q4 2025 | MPALSG | Has not commenced | - | .. |  | The activity has not been realised because implementation requires amendments to the legal framework that would regulate the issuance of certificates. | Amending the legal framework to regulate the issuance of certificates.
.
Measure 1.1.3: Improving the legal framework and procedures for direct participation of citizens in local self-government management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Share of towns, municipalities, and urban municipalities in the total number of towns, municipalities, and urban municipalities whose employees are trained to apply the new legal framework in the field of referendum and people’s initiative (%) |  |  | 0 (2020) |  | 50 | 19.65 | During 2024, referendum‑related training was delivered by the MPALSG, while the training sessions planned to be implemented by the SCTM have been postponed to 2025, when a higher indicator value is expected. The training was attended by 58 officials from 34 local self‑government units.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.3.1: Preparing a guide/handbook for conducting a referendum and people’s initiative (with forms of legal acts and documents to be used) | Q2 2024 | MPALSG | Completed | 100% | A Handbook has been prepared that elaborates questions concerning referenda and citizens’ initiatives and provides clarifications regarding the regulatory framework (the Law on Referendum and Citizens’ Initiative and the Decree on the Electronic Citizens’ Initiative), i.e. the procedural and process steps involved. Also, the Handbook contains the following models: - Decision establishing an initiative committee for collecting citizens’ signatures to call a referendum - Submission of a proposal to implement a citizens’ initiative - Submission of a proposal for the electronic implementation of a citizens’ initiative - Notification that the conditions for verifying the proposal have not been met, with an additional deadline to remedy deficiencies - Remedy of deficiencies in the submitted proposal / Notification from the initiative committee that it maintains the submitted proposal, appointing a representative of the proposer - Notification of the locations where citizens’ signatures will be collected for the citizens’ initiative - List of voters who support the citizens’ initiative with their signatures - List of voters who support the citizens’ initiative to call a referendum with their signatures - Voter’s declaration of support for the citizens’ initiative - Request to collect electronically submitted signatures - Authorisation for the person submitting the list of signatories to the assembly…
1.1.3.2: Training of local self‑government staff on referendum and citizens’ initiative procedures (two annual seminars for heads of administrations; 8 regional training sessions for local‑administration employees) | Q2 2025 | MPALSG | In progress | 100% | During 2024, referendum‑related training was delivered by the MPALSG, while the training sessions planned to be implemented by the SCTM have been postponed to 2025, when a higher indicator value is expected. The training was attended by 58 officials from 34 local self‑government units. |  |  | Eight regional seminars on conducting referenda and citizens’ initiatives for local‑government employees will be held during 2025.
1.1.3.3: Conducting an analysis of the status of city municipalities—covering the precise conditions or obligations for establishing city municipalities, their organisation and roles, citizen participation, and the financing of city municipalities, while applying a differentiated approach based on population, geographical and economic criteria. | Q4 2024 | MPALSG | Completed | 100% | The recommendations stemming from this analysis can help create efficient and functional city municipalities that respond better to citizens’ needs and foster sustainable local development, taking into account the capacity to manage resources effectively and provide public services. The criteria proposed in the analysis may be divided into: mandatory (citizen participation), and optional (political will and local consensus). The optional criteria include: demographic, geographic and administrative, economic, and services & infrastructure. Before an initiative to establish a new city municipality—or to modify an existing one—is submitted, an analysis must be prepared using the above criteria to determine needs and capacities. The results of the analysis should demonstrate that, in addition to meeting the mandatory criteria, the optional criteria are also aligned, with particular emphasis on citizens’ need for easier communication and the reliable provision of public services.
.
Measure 1.1.4: Improving the participation of local self-government in the process of developing national regulations and public policies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Improved legal framework towards greater participation of local authorities in the process of preparation of public policies and general acts governing local self-government issues (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The indicator has not been met because its implementation depends on amending the Law on Local Self‑Government.
Share of laws related to LSGUs on which information was submitted through the SCTM system for informing the LSG, in relation to the total number of laws related to LSGUs (%) |  |  | 65 (2020) |  | 90 | 100
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.4.1: Determination of the Draft Law on Amendments to the Law on Local Self‑Government by the Working Group, with the aim of introducing a mandatory obligation to involve local self‑government units—or the national association of local authorities—in the preparation of draft public‑policy documents, laws and other general acts regulating matters of local government interest, and its subsequent referral to the Government for adoption as a Bill. | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | Working group has not been established. | Set up a working group for the purpose of drafting the law.
1.1.4.2: Continually and regularly informing the local authorities about the adopted amendments to the legal framework (Law Alert system of the SCTM) | Q4 2025 | MPALSG | In progress | - | During 2024, six laws were adopted whose provisions are largely relevant to local self‑government units These are: the Law Amending and Supplementing the Budget System Law; the Law Amending and Supplementing the Property Taxes Law; the Law Amending and Supplementing the Tax Procedure and Tax Administration Law; the Law Amending and Supplementing the Utility Services Law; the Law on Environmental Impact Assessment; and the Law on Strategic Environmental Impact Assessment. All key amendments and supplements affecting local self‑government units—as well as the most important provisions of the law—were communicated to them in a timely manner through the SCTM “Legal News” bulletin. |  |  | Legislative activity will continue to be monitored in 2025, with local authorities receiving continuous, regular updates on adopted changes to the legal framework.
.
Measure 1.1.5: Further development of local self-government capacity for applying the principles of good governance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of local officers trained to apply good‑governance principles (cumulative) (Number) |  |  | 831 (2020) |  | 2,200 | 2,748 | A total of 89 local officials were trained in 2024.
Percentage of the overall number of cities, municipalities and city municipalities that have adopted a new Code of Ethics (%) |  |  | 7 (2020) |  | 50 | 35.3 | Local elections were held in all LSGUs at the end of 2023 and in mid‑2024. Because a Code of Ethics for local officers must be adopted by the local assembly, only a very small number of LSGUs adopted this document during 2024 (five LSGUs in total).
Number of cities, municipalities and city municipalities that have received an award for applying good‑governance principles (cumulative) (Number) |  |  | 8 (2020) |  | 24 | 28
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.5.1: Implementation of a Support Package to Improve Accountability and Apply Anti‑Corruption Policies at the Local Level in Five LSGUs | Q4 2025 | MPALSG | In progress | - | The support package is being implemented in the municipalities of Vlasotince, Vrbas, Vrnjačka Banja, Lebane and the City of Subotica. Its focus is to enhance implementation of Local Anti‑Corruption Plans (LAPs) / integrity plans and to improve the local legislative framework and practices relevant to preventing and combating corruption in selected areas, such as: adoption of general acts and citizen participation; financial management; management of conflicts of interest; whistle‑blower protection; allocation of LSGU budget funds for activities of public interest to the local community; application of the Code of Conduct for employees and the Ethical Code for LSG officials. During 2024, advisory support was provided in all 5 LSGUs to establish procedures and internal mechanisms for managing, coordinating, applying rules and reporting on conflicts of interest among LSGU staff, through the adoption of a Rulebook on the Management of Conflict of Interest for Employees; Procedures were set up for appointing members of the management and/or supervisory boards of services, institutions, enterprises and other organisations founded, fully or partly financed, or controlled by the LSGU; Support was given for adopting an Ethical Code for Local Self‑Government Officials and for establishing Councils to monitor implementation of the Code. The Municipal Assembly of Vrbas adopted an Ethical Code and a Rulebook on the Management of Conflict of Interest at the end of 2024. In 2024 Vrbas hosted a training course on conducting public hearings with seven participants. |  |  | The support package will continue in the same five LSGUs, focusing on establishing mechanisms to eliminate undue influence on LSGU work through donations, by defining internal procedures for donations management, and training designated staff to improve procedures for effective donations oversight; sdopting and implementing the Ethical Code for local officials; delivering training for authorised persons responsible for applying conflict‑of‑interest rules for employees in LSG bodies, and general staff training on conflict‑of‑interest management; improving procedures for appointing members of management and/or supervisory boards of services, institutions, enterprises and other organisations founded, funded (in whole or in part) or controlled by the LSGU. Three LSGUs will receive assistance to adopt an act on promotion of co‑financing or topping‑up programmes of public interest implemented by associations, together with accompanying documents for calls, monitoring and evaluation; training will be delivered to personnel responsible for funding association programmes on defining public interest priorities for financing. Two LSGUs will receive support to define procedures and adopt acts on internal whistle‑blowing and on handling citizen complaints about LSGU services and bodies, and conduct training on applying the legal framework and best practice in whistle‑blowing and whistle‑blower protection.
1.1.5.2: Monitoring the implementation of the training programme on good governance from the Sectoral Programme of Continuous Professional Development of employees in LSGUs | Q4 2025 | NAPA | In progress | 100% | During 2024 the SCTM ran six two‑day regional accredited training courses entitled “Involving the Local Community in the Preparation of General Acts” (part of the Sectoral Programme of Professional Development for Local‑Self‑Government Employees for 2024) which were attended by 89 participants, and 77 employees obtained a certificate from the National Academy for Public Administration (NAPA). Although the subject matter is closely related, this training is not formally classified under the Good Governance area of the Sectoral Programme of Professional Development, but under another thematic area. We nonetheless considered it appropriate to report on the training here. A course on “Exercising the Right of Access to Information of Public Importance” had also been scheduled for 2024, but—because local elections were being held—it was decided to postpone its delivery until 2025. |  |  | SCTM will continue in 2025 to deliver accredited training courses in the Good Governance area under the Sectoral Programme of Professional Development for Local‑Self‑Government Employees for 2025.
1.1.5.3: Promoting the Code of Ethics of local self-government officials (online conferences, organising workshops, organising national, regional and local events, distributing a guide and posters with quotes from the Code of Ethics, etc.) | Q4 2025 | MPALSG | In progress | 100% | In March 2024, two regional presentations of the Code of Ethics of Local‑Self‑Government Officials were held (Vrnjačka Banja and Zrenjanin). |  |  | In 2025 the 6th edition of the Guide for Implementing the Code of Ethics for Local‑Self‑Government Officials will be published, in a print run of 10,000 copies.
1.1.5.4: Е-training for officials on the application of the Code of Ethics of local self-government officials | Q4 2025 | MPALSG | Has not commenced | - | .. |  | Due to the local elections it was not purposeful to deliver this training during 2024, especially given the specific target group (local officials). | The e‑training course entitled “Code of Ethics for Local‑Self‑Government Officials” will be held in 2025.
1.1.5.5: Enhancing the culture of managerial accountability in five LSGUs by improving the Code of Ethics and the Integrity Plan and ensuring their implementation. | Q3 2025 | Selected LSGUs |  | - | ..
1.1.5.6: Developing the fourth analysis of the local self-government performance assessment pertaining to good governance, based on the SCTM Good Governance Index (on a sample of 60 LSGUs) | Q4 2025 | MPALSG |  | - | ..
1.1.5.7: Implementation of a support package to improve transparency and public participation in five LSGUs (assisting citizen involvement in the budget‑adoption process and increasing the transparency of budgeting procedures). | Q4 2025 | MPALSG | In progress | 100% | The support package is being implemented in the municipalities of Bogatić, Boljevac, Kuršumlija, Mionica and the City Municipality of Pantelej. During 2024, in all 5 LSGUs, assistance was provided to regulate the procedure for conducting public consultations at the local level; draw up an activity plan for involving citizens in the budget‑preparation process; organise and carry out citizen participation in selecting local funding priorities; and organise and conduct the public debate process on the Draft LSGU Budget Decision. Accordingly, every LSGU: completed a participatory process for proposing capital projects; and held a public debate on the Draft Budget Decision for 2025. Each of the five LSGUs produced a Citizens’ Guide to the 2023 Final Account Decision, and a Citizens’ Guide to the Draft Budget Decision for 2025. Also, the capacities of staff and decision‑makers in the 5 LSGU were strengthened with regard to planning and setting gender‑responsive goals and indicators in the 2025 budget. In this respect, 10 training sessions on the concept of gender‑responsive budgeting were held, with a total of 80 participants. All 5LSGUs adopted a Plan for the Gradual Introduction of Gender‑Responsive Budgeting, although only 3 LSGUs actually incorporated gender‑responsive goals and indicators into their 2025 programme budget. |  |  | During 2025, Citizens’ Guides to the 2025 Budget Decision will be prepared for all 5 LSGUs. Support will continue for establishing the transparent online publication of relevant budget documentation and data on municipal websites. A major focus will be the transparent financing of civil‑society organisations (CSOs), through analysing strategic documents, local acts and current programme financing practice; assisting in drafting or improving a Decision on the Manner and Criteria for Allocating Municipal Budget Funds to CSO Projects, together with all accompanying acts; support for building LSGU capacity to finance public‑interest programmes implemented by CSOs; and supporting the entire CSO programme funding process so that it is carried out in line with the applicable regulatory framework.
1.1.5.8: Organising a public call for annual awards for the best municipal/town administration in applying the principle of good governance | Q4 2025 | MPALSG | In progress | 100% | The Public Call for the Annual Award for Applying Good Governance Principles in 2023 was announced at the beginning of February 2024. In addition to the RSD 8.36 million fund secured by the MPALSG under the Rulebook on the Manner and Criteria for Allocating Funds to Finance Programmes Supporting the Development and Functioning of the Local Self‑Government System (“Official Gazette RS”, Nos. 101/21 and 69/24), the winners of the Good Governance awards in four categories were also presented with sets of technical equipment worth a further RSD 5 million, provided by the SCTM. The MPALSG Commission selected 4 LSGUs: Ada (Transparency and public participation), Pećinci (Equality and anti‑discrimination), Niš (Efficiency and effectiveness), and Bosilegrad (Accountability and the rule of law)... |  |  | In 2025, MPALSG will announce a new Public Call for the Best Local Self‑Government in 2024. The SCTM will also support the implementation of this Public Call and will provide an award fund for the 4selected LSGUs, financed from the resources of the Partnership for Good Local Self‑Government Programme.
1.1.5.9: Implementing the package of support to local self-government (for developing / revising and implementing multiannual action plans for the implementation of participatory process for making decisions about spending LSG’s own revenues; support to local communities in applying participatory mechanisms being developed and in applying their own development programmes and financial plans) | Q1 2025 | MPALSG | In progress | - | The 2024 Support Package was implemented according to planned activities, focusing on the final steps in providing assistance to the councils of 30 local communities across 15 local self-government units (LSGUs). Technical assistance (TA) and advisory services from the project team remained the key mechanism of support, enabling guidance for citizen-participation activities at the local level. In the final phase, TA was directed towards finalizing Action Plans for Citizen Participation in local communities, creating standardized document templates, providing targeted advisory services, and conducting on-site visits. Additionally, support was provided to implement co-financing mechanisms, improve communication processes with citizens, and strengthen the capacities of local community councils to ensure their sustainable functioning. Following an analysis of reports from public debates held as part of the budget consultation process for 2024, a final comparative evaluation report was prepared for the 30 local communities. This report compared citizen participation outcomes in budget processes to those of 2023 and included recommendations for further strengthening local communities as key stakeholders in local-level decision-making. |  |  | Implementation of these final activities is planned to continue during 2025.
1.1.5.10: Preparation and implementation of a funding programme supporting the development and implementation of participatory models for spending own local self-government revenues in 14 LSGUs | Q4 2024 -> Q4 2025 | MPALSG | In progress | - | Experiences gained during 2023 significantly contributed to enhancing participatory decision-making processes on involving citizens in the 2024 budget cycle. Insights into previous challenges and successful practices enabled 14 local self-government units to more effectively design and implement public calls for co-financing small-scale civic projects. Based on 2023 experiences, local working groups tasked with action plans for citizen participation significantly broadened consultation opportunities, adjusting them to various target groups. Special attention was given to organizations supporting vulnerable population groups, apartment building managers in urban settings, and residents of rural communities, enabling more inclusive citizen participation. This comprehensive approach resulted in increased engagement from informal citizen groups, which applied for funding in higher numbers compared to the previous year. Due to these improvements, a total of nearly one million euros was contracted to finance citizen-led projects across the 14 LSGUs, while the project's own financial contribution exceeded 290,000 euros. This support model, enhanced by lessons learned in 2023, demonstrated significant potential for strengthening active civic engagement and sustainability of local initiatives. |  | Although originally planned for implementation during 2023 and 2024, some activities involving project works in specific LSGUs experienced delays due to public procurement processes. | The final implementation activities are planned to continue into 2025.
1.1.5.11: Development and promotion of innovative e-models for citizen participation in decision-making related to the expenditure of local self-government own revenues | Q1 2025 | MPALSG | Completed | - | During 2024, all activities aimed at improving the eConsultation Portal were successfully completed, implemented in collaboration with GIZ and the Public Policy Secretariat. The project was conducted in two phases. Following successful completion of the first phase, the second phase commenced with support from the MED Programme. Under this second phase, all local self-government units (LSGUs) gained the ability to publish their public policy documents on the Portal and conduct consultations with citizens. After an evaluation process, the tender was awarded to eSmart Systems, which responsibly carried out project implementation. The Portal has been tested and is fully functional. To ensure its effective use, training for LSGU representatives was organized at the National Academy for Public Administration (NAPA). The training was delivered in cooperation with the Public Policy Secretariat, enabling participants to acquire the necessary knowledge and skills to use the eConsultation Portal effectively as a mechanism for conducting open and transparent public consultations.
1.1.5.12: Establishing and Developing Capacities of Local Centres for Good Governance | Q4 2025 | MPALSG | In progress | 100% | In order to establish and strengthen capacities of local Centres for Good Governance, three training sessions on the practical application of good governance principles were held during 2024, covering the topics of citizen participation, non-discrimination and equality, and efficiency and effectiveness, for representatives of 22 LSGUs involved in this activity. The activity continues in 2025, when the final training session and a training for trainers workshop are planned. Additionally, within the training programme for already established Centres, the first of three planned sessions for developing supplementary skills for representatives of the 22 LSGUs was held during 2024. The topics covered included communication, negotiation, conflict management, advocacy and representation. The remaining two training sessions are scheduled for 2025. |  | The activity is being implemented according to plan and will run until the fourth quarter of 2025. | Establishing Local Centres for Good Governance.
.
Measure 1.1.6: Improvement of vertical and horizontal supervision in performing original and entrusted tasks of LSGUs
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Improved legal framework governing the oversight function of municipal/city assemblies (reporting by executive bodies to assemblies, councilors’ questions—interpellations, strengthening the role of working bodies—submission of proposals for legal acts, etc.) (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The indicator has not been met because its implementation depends on amending the Law on Local Self‑Government.
Improved legal framework governing the functioning of administrative districts (strengthening the coordination role of administrative districts and their supervisory function regarding the execution of local self-government activities in local units at the level of administrative districts) (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The indicator has not been met because its implementation depends on amending the Law on Public Administration.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.6.1: Determination of the Draft Law on Amendments to the Law on Local Self-Government by the Working Group (enhancing the oversight function of local assemblies—provisions related to reporting by executive bodies to assemblies, introducing interpellation, strengthening the role of working bodies in proposing acts, introducing the obligation for LSGU to make regulations within their competence available electronically, and establishing a second-instance body for original administrative procedures), and submission to the Government for adoption as a Bill. | Q4 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | Working group has not been established. | Set up a working group for the purpose of drafting the law.
1.1.6.2: Preparation of model local acts for implementing the amendments to the Law on LSG concerning enhancement of the oversight function of the municipal/city assembly, strengthening the position of assembly working bodies and introduction of the obligation for LSGUs to publish their applicable regulations (Rules of Procedure of the Assembly, model executive reports, model Decision on Publishing LSGU Legal Acts, etc.). | Q2 2025 | MPALSG |  | - | ..
1.1.6.3: Preparation of model local acts for implementing the amendments to the Law on LSG that introduce a second‑instance (appellate) body for decisions in administrative proceedings (including amendments to the model statute; a model procedure for selecting members of the appellate body; the Rules of Procedure of the appellate body). | Q2 2025 | MPALSG |  | - | ..
1.1.6.4: Development and delivery of training for assembly secretaries to support implementation of the new provisions of tje Law on LSG that strengthen the functions of the municipal/city assembly. | Q4 2025 | NAPA |  | - | ..
1.1.6.5: Design and implementation of a training programme for persons engaged in the work of the second‑instance body that decides in administrative proceedings. | Q4 2025 | MPALSG |  | - | ..
1.1.6.6: Preparation of amendments to the Law on State Administration—namely: defining final deadlines for state administration bodies to issue approvals, opinions or adopt acts that form part of procedures conducted by LSGUs, as well as final deadlines for providing information requested by LSGUs that falls within the competence of state administration bodies; redefining and expanding the functions of Administrative Districts; strengthening the coordination role of Administrative Districts and their supervisory function over the performance of local self‑government tasks, with particular emphasis on their preventive and advisory functions in areas subject to oversight by state bodies—and subsequent referral to the Government for adoption as a Bill. | Q4 2025 | MPALSG |  | - | ..
1.1.6.7: Development of a plan to implement the new functional framework and to build the capacities of the Administrative Districts for carrying out the districts’ new functions and those of the regional units of the competent line ministries. | Q4 2024 -> Q4 2025 | MPALSG | Has not commenced | - | .. |  | A prerequisite for implementing this activity is the amendment of the Law on State Administration. | Adoption of the amendments to the Law on State Administration.
.
Specific objective 1.2: Improving the local self-government financing system
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Share of LSG tax revenues in total tax revenues in the Republic of Serbia (%) |  |  | 10.12( 2020) |  | 11.64- 11.7 | 10.3 | Tax revenues of LSGUs constitute their own revenues, i.e. revenues for which the LSGUs independently set the rates. Problems have been identified both in planning these revenues and in collecting them. Support is required in this area to improve the situation.
Share of capital expenditure in total local government expenditure (%) |  |  | 15.54( 2019) |  | 17.11- 17.2 | 18
Share of LSGUs with an Adopted Medium-Term Plan (%) |  |  | 0 (2020) |  | 27- 30 | 12.4 | For the 2024–2026 medium-term planning cycle, 18 LSGUs adopted their medium-term plans, representing a weaker outcome compared to the previous 2023–2025 cycle, during which 27 LSGUs adopted medium-term plans. This decline underscores the need for continued support and additional efforts to address the challenges of aligning medium-term planning with programme-based budgeting at the local level.
.
Measure 1.2.1: Reform of the local self-government financing system and support for the development of fiscal decentralisation
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Systemic legal framework reformed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | In 2024, steps were undertaken to enable the reform of the legal framework. Integrating local self-government units into the SPIRI and ISKRA systems, and amending the Budget System Law to enhance the financial discipline of local self-government units in the course of budget decision-making.
Share of property tax revenues in total budget revenues of the LSG (%) |  |  | 15.8( 2019) |  | 17 | 15.3 | Tax revenues of LSGUs)constitute their own revenues, i.e. revenues for which the LSGUs independently set the rates. Problems have been identified both in planning these revenues and in collecting them. Support is required in this area to improve the situation.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.1.1: Continual work of the Commission for Financing Local Self-Government within its purview as defined in the Law on Financing Local Self-Government | Q4 2025 | MoF | In progress | - | During November 2021, the work of the Commission for Local Government Financing was relaunched. It was agreed that, based on an analysis to be prepared by the Ministry of Finance, a proposal to improve the system of financing of local self-governments would be drafted. |  | By the end of 2024, all LSGUs were integrated into the SPIRI and ISKRA information systems. On the basis of reports generated by these two systems, a proposal to enhance the local government financing system is expected to be developed, and the Commission for Local Financing will resume its activities. | An update of the existing analysis of the local government financing system will be undertaken, drawing on the SPIRI and ISKRA reports.
1.2.1.2: Improving the financing system in line with the findings of the local self-government financing system analysis (application and effects of the systemic legal framework, LSGU revenues/income and expenditures/expenses structure; planning and generation of revenues, and execution of expenditure and expenses; LSGUs’ aligning with the MoF instructions) | Q4 2025 | MoF | Has not commenced | - | The Ministry of Finance has arried out an analysis of the financing of local self-government units, on the basis of which a proposal to improve the financing of local authorities is to be drafted. |  | Owing to the integration of local authorities into the SPIRI and ISKRA information systems, it was decided that, based on the reports generated by those systems, the existing analysis of local government financing will be updated and a proposal for improving local-government financing will be prepared. | The existing analysis of the local-government financing system, on the basis of which the Commission is to formulate its proposal for improving the financing of local self-government units, will be updated.
1.2.1.3: Supporting further capacity building of local tax administrations (LTAs) (inter-connecting/networking and knowledge sharing between LTAs, implementing annual training programmes and workshops, advisory support, direct technical assistance to specific LSGUs, etc.) | Q4 2025 | MoF | In progress | 100% | During 2024, two cycles of regional thematic meetings for all local tax administrations (LTAs) were held under the SCTM LTA Network, in cooperation between the SCTM (through its SDC Programme) and the MED III Programme “Responsible Local Finance and Citizen Engagement” (implemented by Helvetas), as follows: – First half of 2024 (in partnership with the Mihailo Pupin Institute): Topic: fees for environmental protection and improvement – application of new sub‑legal acts (the Regulation and Rulebook), changes in the LTA information system (ISKRA) concerning public‑space usage fees, notarial data, and issuance of tax certificates. One‑day regional network meetings were held in Belgrade, Novi Sad, and Vrnjačka Banja, attended by 198 representatives from 99 LSG. Second cycle of regional workshops in the second half of 2024 under the SCTM LTA Network (in cooperation with the Office for Information Technology and e‑Governance and the Mihailo Pupin Institute): –The topic of these of regional workshops was: “e‑Services from the Taxpayer’s Perspective.” Four one‑day workshops were organized in Belgrade and Kragujevac, with 220 participants from 97 LSGUs. Throughout 2024 SCTM also provided continuous advisory support via its e‑Question service. Also the administrative‑procedure models used by LTAs were updated. Under the MED III Programme additional LTA workshops were held during the year, and support continued for hiring extra staff within LTAs. According to November 2024 data, property tax revenue collections continued their upward trend, rising by 12.87 percent compared with the same period in 2023. This growth reflects both the multi‑year support of the MED III Programme and the sustained efforts of LTA in administering this tax. In 2024, following the public consultation on Draft Law on Amendments to the Law on Property Taxes and the Law on Tax Procedure and Tax Administration, proposals, comments, and suggestions from LTA representatives were collected. A consolidated list of these recommendations was prepared and submitted to the Ministry of Finance. |  |  | This is an ongoing activity, implemented annually, and remains planned for 2025. It is carried out under the MED Programme funded by Swiss development cooperation Helvetas (through 2025), in partnership with SCTM’s SDC‑funded “Partnership for Good Local Self‑Government” Programme.
.
Measure 1.2.2: Support to LSGUs to improve the budget planning process
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Average capacity of LSGUs to apply the principles of good governance in accordance with the Good Governance Index in LSGUs in the field of accountability (%) |  |  | 45 (2018) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.1: Providing general support to LSGs for the development of medium-term plans (advisory support to all LSGs, developing models and instructions, and information exchange with all LSGs) | Q4 2025 | PPS | In progress | 100% | During 2024, continuous advisory support was provided for the development of local self-government units’ (LSGUs’) medium-term plans at the request of the LSGUs themselves. Also, in coordination between the EU Exchange 6 Programme and the Swiss development cooperation “Partnership for Good Local Government” Programme, SCTM conducted an annual cycle of seminars to support LSGUs in drafting their 2025 budgets, which included dedicated sessions on LSGUs’ medium-term planning. Four seminars and two webinars were held, attended by 272 representatives from 95 LSGUs. |  |  | Support for LSGUs in preparing their medium-term plans will continue in 2025.
1.2.2.2: Implementing 10 support packages to municipalities for developing LSGU medium-term plans | Q4 2024 | PPS | Completed | 100% | SCTM provided expert support, through the EU Exchange 6 Programme, for the preparation of 11 medium-term plans. Of these, 10 LSGUs were selected under the second programme call in 2023, and one additional LSGU received support.
1.2.2.3: Implementing 11 support packages to municipalities for preparing capital budget | Q4 2024 | MoF | Completed | 100% | Under the EU Exchange 6 Programme in 2024, SCTM completed support packages for capital budgeting in 11 beneficiary LSGUs, including the preparation of implementation reports for one exemplar capital project from each LSGU’s 2024 budget. Drawing on lessons learned from those support packages, SCTM prepared guidelines and model materials for LSGUs to implement the full cycle of capital project management for projects below the regulatory threshold (i.e., those not subject to the Capital Projects Regulation). Additionally, in cooperation with the Ministry of Finance, SCTM harmonized document templates for the establishment and operation of local Capital Investment Commissions—responsible for local projects exceeding €2 million in estimated value under the Regulation—and distributed these templates to all LSGUs in mid-2024.
1.2.2.4: Development, preparation and monitoring of the implementation of the professional development programme for LSG employees, focused on programme and capital budgeting and their alignment with the local development planning (developing an LSGU’s medium-term plan and linking it to the LSGU’s programme and capital budget), gender and participatory budgeting | Q4 2025 | NAPA | In progress | 100% | Council for Professional Development of Local-Government Employees (CPD-LSGE), in collaboration with the National Academy for Public Administration (NAPA), prepares and develops the Sectoral Programme of Continuous Professional Development. To fulfil this mandate, CPD-LSGE established a Working Group to coordinate the process and draft the Sectoral Programme for Continuous Professional Development for 2024. Its members included representatives of NAJU, the Ministry of State Administration and Local Self-Government, SCTM, and the project team. WG members included representatives of NAPA, the Ministry of Public Administration and Local Self-Government, SCTM, and the project team. Acting under its mandate, the Working Group prepared the draft Sectoral Programme for Continuous Professional Development in local self-government units for 2024. This draft was submitted to CPD-LSGE for comment and thereafter incorporated into the General Training Programme for Local-Government Employees for 2024. The NAPA Programme Council then endorsed the proposed General Training Programme for Local-Government Employees, which the Government adopted in its session of 14 December 2023 upon NAPA’s recommendation. During 2024, a new cycle of programme development for 2025 was carried out, and on 30 January 2025 the Government adopted the General Training Programme for Local-Government Employees for 2025, again on NAPA’s proposal. According to SCTM’s information, and in collaboration with NAPA colleagues via formal calls to SCTM, annual plans are reviewed each year for the professional development programme of professional development of LSGU employees covering programme budgeting, capital budgeting, and medium-term planning. With regard to delivery under the 2024 Training Programme for LSG units, SCTM delivered two sets of accredited courses as follows: February–March 2024 (under EU Exchange 6): eight regional accredited trainings on “Capital Budgeting in LSGU.” Seven were held in person and the final session was delivered as a webinar. At the trainings held in Belgrade (2), Vrnjačka Banja, Niš (2), and Novi Sad (2) and the webinar, a total of 131 participants attended, of whom 104 obtained a NAPA certificate. In the second half of September 2024 two accredited trainings on gender-responsive budgeting were held (at Sombor and Šabac), attended by 30 participants, of whom 26 received NAPA certificates. |  |  | Updating the professional development programme for local government employees is an ongoing, annual activity, coordinated with NAPA and relevant line institutions, and is planned again for 2025. Regarding capital-budgeting training for LSGU, the content of 2025’s courses will be enriched by materials that SCTM is preparing in the first half of the year—together with the Ministry of Finance—to provide supplementary guidance on applying the Capital Projects Regulation at the local level, accompanied by model document templates. This support is delivered through both EU Exchange 6 and the SDC–SCTM “Partnership for Good Local Governance” Programme.
1.2.2.5: Exploration of the possibility of modifying the structure of the programme budget to better align it with the needs of development and public policies. | Q4 2025 | MoF | In progress | 100% | In accordance with the agreements reached during the preparation of the Action Plan for the Partnership for Good Local Self-Government (AP PGLSG) for 2024–2025 and the approved Addendum under the EU Exchange 6 Programme, SCTM began in the second half of 2024 to draft proposals for possible changes to the structure of LSU programme budgets. The aim was to better align them with the needs of development and public policies (by linking development and medium-term planning with programme budgeting), in line with the mandated activity. A first draft proposal was prepared at the end of the fifth phase of the Exchange Programme; during 2024 it was updated on the basis of analyses conducted while supporting LSGUs in medium-term planning under the sixth phase of Exchange. The first draft of the analysis, complete with recommendations for improvement, was released in November and presented at the workshop “Planning and Budgeting in Local Self-Government Units – Challenges and Proposals for Improvement” held on 26 November 2024. The workshop brought together 39 representatives from 23 LSGUs—those supported under EU Exchange 6 in drafting medium-term plans and reporting on development plan performance—as well as 9 representatives from national institutions and partner project teams (the Ministry of Finance, Public Policy Secretariat, State Audit Institution, Fiscal Council and RELOF 3). Based on the outcomes of the workshop discussion, a final version of the analysis—assessing the alignment of medium-term planning processes with programme budgeting at the local level and offering recommendations for further enhancement—will be prepared during the first quarter of 2025. |  |  | In early 2025, SCTM will finalize the analysis of alignment of medium-term planning processes with programme budgeting at the local level with recommendations for further improvement. The material will also be submited to the relevant national institutions (in particular, the Ministry of Finance and the PPS) for review. It will also serve as the basis for continued consultations under this activity through the end of 2025.
.
Measure 1.2.3: Improving transparency of the local finance system
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
A public electronic display has been established for displaying and monitoring the state of local budgets (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 0 | -
Share of LSGs which have publicly available budget portals (%) |  |  | 1.7( 2020) |  | 18 | 21 | The indicator value refers to 36 LSGU (out of a reference total of 170) that have publicly accessible budget portals at the time of the reporting.
Share of LSGs which publish monthly reports (or cumulative monthly reports) on budget execution on their website (%) |  |  | 9.4( 2020) |  | 30 | 12.4 | This figure is based on data from the Local Transparency Index (LTI) maintained by Transparency Serbia (https://www.transparentnost.org.rs/sr/istraživanja-o-korupciji/lti). The data derive from the 2024 report, and the indicator is measured against the total number of LSGUs (170). Achievement of this indicator is slightly weaker compared to the previous year (13.5% in 2023). Publication rates of monthly budget execution reports by LSGUs remain very low—well below the target—but it is noteworthy from a transparency standpoint that the publication of six-month and nine-month budget-execution reports stands at a significantly better level - 44.1% for 2024 (per the same source).
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.3.1: Forming a public electronic display of the local authorities’ budget (planning and the execution of each LSG’s budget revenues and expenditure) | Q4 2024 -> Q4 2026 | MoF | Has not commenced | - | The Ministry of Finance has worked on developing the SPIRI and ISKRA information systems, into which local self-government units were integrated at the end of 2024. |  |  | During 2025, the possibility of creating a public display of local government budgets will be considered.
1.2.3.2: Developing 20 LSG budget portals | Q4 2024 | MoF | Completed | 100% | The introduction of budget portals (BPs) refers to the establishment of a software-based application/platform that enables an advanced system of electronic reporting for financial documentation, facilitates financial management and coordination within the LSGU, and improves communication with interested stakeholders (in the case of publicly accessible portals). This entails installing the appropriate software, procuring and delivering accompanying computer hardware, providing training for portal users and administrators, and offering technical support for system use and maintenance. Having supported over 20 local self-government units in previous years—using funds from Swedish and Swiss development cooperation—support for an additional 21 units was made available under the EU Exchange 6 Programme (exclusively for public budget portals; 20 in line with the initial plan, plus one extra unit upon justified request). The bulk of activities and training sessions for establishing public budget portals in the new beneficiary units was completed by the end of 2024, so this activity is recorded as finalized for the purposes of this report. SCTM continues to liaise with beneficiary units regarding technical support and advice to enhance their use of the public budget-portal functionalities.
1.2.3.3: Monitoring the implementation of the training programme on participative budgeting from the Sectoral Programme of Continuous Professional Development of employees in LSGUs | Q4 2025 | NAPA |  | - | ..
.
Measure 1.2.4: Measure 2.4: Intensive development of the public internal financial control system (PIFC) at the local level
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
% of certified internal auditors in local self-government units (%) |  |  | 64 (2019) |  | 70 | - | The value of this indicator will be determined after the adoption of the 2024 Annual Report of the Internal Audit Units (KJS) and the 2024 Consolidated Annual Report.
LSGUs included in the system of reporting on their FMC systems (%) |  |  | 55.86( 2019) |  | 100 | - | The value of this indicator will be determined after the adoption of the 2024 Annual Report of the Internal Audit Units (KJS) and the 2024 Consolidated Annual Report.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.4.1: Establishing and/or further developing the functions of internal audit, financial management and control, and managerial accountability at the local level, with LSGUs reporting on the PIFC (advisory support, training, (inter-)connecting the LSG) | Q4 2025 | MoF | In progress | 100% | Within the scope of this activity, horizontal support for LSGUs was provided throughout 2024 in coordination with the Ministry of Finance/Central Harmonization Unit (MoF/CHU) together with SCTM (under the EU Exchange 6 Programme) and the partner RELOF 3 Programme (Swiss development cooperation). The emphasis was on internal audit (IA), in light of the legal framework adjustments initiated in this domain (amendments to the IA Rulebook in 2023). Accordingly, in June 2024 a joint workshop was held on the organizational setup of IA and on improving the material conditions of internal auditors in LSGUs (particularly given the expanded IA scope under the amended Rulebook) Participants discussed the employment law, organizational and material status of IA in LSGUs, reviewing current legislation and diverse LSGU practices. The workshop in Belgrade was attended by 60 representatives from 50 LSGUs plus colleagues from the MPALSG. During summer 2024 a report was drafted containing key conclusions and recommendations for action. On that basis, consultations continued in autumn between the competent institutions to identify priority provisions for amendment in order to address the problems highlighted and implement the proposed solutions Thanks to the advocacy of MoF/CHU, certain proposals—particularly those clarifying the organizational independence of IA in LSGUs and establishing direct accountability to the mayor or municipal president—were incorporated into the amendments to the Budget System Law. Support for LSGUs in operationalizing these amendments will commence in early 2025. |  |  | The activities described are ongoing and will continue through 2025. Specifically, to assist LSGUs in putting the Budget System Law changes on IA into practice, guidelines and a model Assembly Decision on establishing IA will be prepared in early 2025 (with advisory assistance available as needed, including drafting any accompanying documents and amending LSGU statutes). Capacity building for LSGUs in IA—and in financial management and control (FMC)—will also continue, with a full cycle of workshops planned for the first quarter of 2025.
1.2.4.2: Direct support to LSGUs for establishing and/or further developing the functions of internal audit and financial management and control. | Q4 2024 | Selected LSGUs | Completed | 100% | During 2024, direct support activities for LSGUs in the domains o FMC and IA under the EU Exchange 6 Programme—implemented via the SCTM—were carried out continuously on the basis of Cooperation Agreements concluded with ten beneficiary LSGUs in 2023, amounting to 11distinct expert-support engagements (5 in FMC, 6 in IA, with one LSGU receiving support in both areas). Expert support on both topics in the beneficiary LSGUs was delivered in accordance with the legal framework and with the methodological materials, templates and guidelines published and maintained by the MoF/CHU. This encompassed both organizational and coordination aspects and the development or refinement of the documentary framework for FMC systems and for IA functions. Furthermore, thanks to the amendments to the IA Rulebook at the end of 2023, MoF/CHU and SCTM agreed to provide parallel, joint support—leveraging EU Exchange 6 expertise—including mentorship for the internal auditors in the beneficiary LSGUs. Under this arrangement, CHU mentors, together with the programme’s technical support and in line with the activity plan, conducted official mentorship audits through late 2024, after which the LSGU internal auditors sat examinations administered by MoF/CHU and attained the status of certified IA. Most of the direct-support work under this activity was completed by the end of 2024, and the activity is therefore recorded as finalized. SCTM will, however, continue—through the remainder of the EU Exchange 6 Programme and thereafter using other available resources—to monitor and support the beneficiary LSGUs in the areas of FMC and IA, drawing on the lessons learned during the delivery of direct support to the ten LSGUs.
1.2.4.3: Capacity building in 10 LSG systems for implementing external audit findings | Q3 2025 | Selected LSGUs | Has not commenced | - | ..
1.2.4.4: Introduction and enhancement of internal audit in 10 LSG systems, including the implementation of a joint internal audit function. | Q3 2025 | Selected LSGUs | In progress | 100% | In April, a masterclass was held for 36 internal auditors. In June 2024, a workshop on the organisational positioning of internal audit within LSGU—organised jointly by the CHU, MPALSG, SCTM, and RELOF 3—brought together 71 internal auditors. As a result of this collaborative work on the legal framework, the Budget System Law was amended in November 2024 to reflect those improvements. Support was provided to the internal auditors from Babušnica and Raška, who passed their certification exams and received their certificates. A training session on internal audit as a tool of good governance was delivered to managers of public enterprises and budgetary organisations in nine LSGUs, with 133 participants. New internal audit planning and execution tools were developed and presented at two regional workshops in Niš and Novi Sad, attended by 50 internal auditors. The internal audit planning tool was piloted with 17 internal auditors during December 2024. |  |  | Direct support to internal auditors will continue, including further piloting of the developed tools, additional training, and policy-dialogue activities.
1.2.4.5: Introduction/Enhancement of the Financial Management and Control (FMC) System in 10 LSGU | Q3 2025 | Selected LSGUs | In progress | 100% | Support was provided in 5 LSGUs. In 4 LSGUs, work focused on introducing/enhancing the FMC system within the local government itself, while in 1 LSGU support covered all budgetary organisations. Five trainings on introducing the FMC system were held, attended by 97 participants, and a risk management training was delivered in 3 LSGUs for 41 participants. |  |  | Support for the FMC rollout continues, with a particular emphasis on public enterprises and budgetary organisations.
.
Specific objective 1.3: Improved organisation and capacities of local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Capacity of LSGU for HR management in local administration (%) |  |  | 51 (2020) |  | - | -
Share of LSGUs which have established inter-municipal cooperation in the total number of LSGUs (%) |  |  | 27 (2020) |  | 33- 42 | 61
.
Measure 1.3.1: nhancement of the HR management function in local administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Capacity of LSGU for HR management in local administration (average value of the SCTM index for HRM in local self-government units in the selected areas: organization and planning of human resources; filling of positions, employee appraisal, disciplinary liability and appeal procedures, communication, ethics, values and organizational culture (Index – composite indicators) |  |  | 58 (2020) |  | 0 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.10: Monitoring the implementation of regional accredited trainings on “Regulations and Procedures in the Recruitment Process” for HRM officers and members of recruitment commissions. | Q2 2024 | NAPA | Completed | 100% | SCTM conducted eight regional training sessions between March and April, held in: Šabac, Novi Sad, Belgrade (two sessions), Užice, Svilajnac, and Niš (two sessions). These trainings were designed for officers responsible for HRM to ensure the correct application of the new Regulation on conducting internal and public competitions for filling vacancies in the bodies of autonomous provinces and LSGU. A total of 136 officers were trained. SCTM note: 156 participants / 136 received NAPA certificate.
1.3.1.11: Monitoring the implementation of regional accredited trainings on “Methods and Techniques in the Recruitment Process” for HRM officers and members of recruitment commissions. | Q2 2024 | NAPA | Completed | 100% | SCTM conducted eight regional training sessions between March and April, held in: Šabac, Novi Sad, Belgrade (two sessions), Užice, Svilajnac, and Niš (two sessions). These trainings were designed for officers responsible for HRM and for members of recruitment commissions, to ensure the correct application of the new Regulation on conducting internal and public competitions for filling vacancies in the bodies of autonomous provinces and LSGU, as well as for training in the application of methods and techniques for candidate selection. A total of 128 officers were trained.
1.3.1.12: Monitoring the implementation of the training programme on “The Role and Activities of the Human Resource Management Unit in Conducting Recruitment Procedures and vis-à-vis Recruitment Commissions” | Q2 2024 | NAPA | Completed | 100% | SCTM delivered training aimed at officers in the bodies of LSGU responsible for human resource management. The objective was to clarify the role of the HR unit in the recruitment process relative to other actors in the process, particularly the recruitment commissions. Three webinars were held: on 4 July 2024, 8 July 2024, and 26 September 2024—with 99 officers participating from 71 LSGUs.
1.3.1.13: Monitoring the delivery of 9 regional accredited trainings on “Conducting Competency-Based Interviews” for LSG officers | Q1 2024 | NAPA | In progress | 100% | SCTM conducted a total of 10 regional accredited trainings on the topic “Conducting Competency-Based Interviews.” Six regional sessions were held during January and February, in: Užice, Šabac, Novi Sad, Svilajnac, Niš, and Belgrade. Subsequently, three additional regional trainings took place in May in Čačak, Belgrade, and Niš. Finally, in December another supplementary session was delivered in Belgrade. These trainings were designed for LSGU officers seeking instruction in assessing behavioral competencies through competency-based interviews. Under the new Regulation on Recruitment Procedures in LSGUs, only individuals who have completed this specific training programme are authorised to conduct such competency assessments. A total of 192 officers were trained.
.
Measure 1.3.2: Improving the process of professional development of employees in LSGUs
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Capacity of LSGU for professional development in local administration (average value of the SCTM index for HRM in local self-government units in the selected areas: Professional development and training of employees (Index – composite indicators) |  |  | 30 (2020) |  | 0 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.11: Monitoring the delivery of e-training on professional development in LSGUs | Q4 2025 | NAPA |  | - | ..
.
Measure 1.3.3: Support to the organisational and functional transformation of local self-government and to unification of organisational forms established by LSGU for implementation of their competencies and tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Alignment of the organizational structure of local administration (average ratio of core to auxiliary functions in local administration) (%) |  |  | 0.6( 2020) |  | 1 | 1.7 | An analysis of the job descriptions for all systematized positions was conducted across 13 LSGUs, with each activity categorized individually for every position. For each LSGU, the percentage ratio of core versus auxiliary functions was determined for the baseline year (2020) and the target year (2024). Finally, the average ratio of core to auxiliary functions across all 13 LSGUs was calculated for both periods (see Table 68). Baseline (2020) was 40 % core : 60 % auxiliary; 2024 measurement: 63 % core : 37 % auxiliary—therefore the indicator was not met, as the intended 50 %/50 % balance was not achieved.
Harmonisation of the organisational forms of LSGUs with basic typology of organisational forms which can be established by LSGUs (%) |  |  | 0 (2020) |  | 35 | 0 | The indicator has not been met because its implementation depends on amending the Law on Local Self‑Government.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.1: Determination of the Draft Law on Amendments to the Law on Local Self‑Government by the working group, with the aim of regulating the organisational forms of local self‑government units in line with the nature of the tasks they perform, and its subsequent referral to the Government so that it may adopt the Bill. | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | Working group has not been established. | Set up a working group for the purpose of drafting the law.
1.3.3.2: Development of Functional Analyses in 15 LSGUs | Q4 2024 | MPALSG | Completed | 100% | The purpose of a functional analysis is to identify shortcomings in the functioning of existing local government structures, as well as structural weaknesses in local-level staffing controls. It determines the causes and consequences of an inappropriate number of employees, a mismatch between managerial and staff numbers, an imbalance between staffing in core and auxiliary functions that drives up public-sector costs, and it identifies new needs imposed by changes in the legal framework and operating environment. To ensure a representative cross-section of contexts, 15 LSGUs of varying status, structure, size and administrative complexity were selected for the analysis. Drawing on the findings and the applicable legislative and institutional framework, tailored functional-organisational models and concrete recommendations were developed for each LSGU. The analysis was based on the principles of good governance—economy, efficiency, accountability for results and transparency. Key expected benefits from implementing these recommendations across the 15 local governments include: • Creating the preconditions for adopting organisational improvements and fostering a shift in management and staff mindsets in the LSGU. • Aligning organisational structures with the actual functions performed, or required, by each administrative body. • Enhancing operational efficiency and strengthening governance processes in the LSGU. • Rationalising financial and human resources by eliminating redundant functions or duplicated tasks and refining the scope of oversight. • Defining new functions and competences—including those not currently performed by the LSGU but necessary to achieve new general and specific policy objectives.
1.3.3.3: Implementing financial support (fund) for the application of functional and organisational models in local government, and technical support in applying the model | Q4 2025 | MPALSG |  | - | ..
1.3.3.4: Development of functional analyses to assess the organisational and functional changes achieved in pilot local administrations | Q4 2025 | MPALSG |  | - | ..
1.3.3.5: Drafting recommendations to align sectoral laws and subordinate legislation with the basic typology of organisational forms which can be established by LSGUs | Q4 2024 | MPALSG | Completed | 100% | An Analysis of sectoral laws and subordinate acts using guidelines for establishing new organisational forms was conducted. To prevent the proliferation of small entities with unclear remits, the analysis prioritises clear definition and specification of each organisational form, together with mandatory criteria for founding a new body. By applying these criteria, all necessary operational elements of a new organisation are clearly delineated, helping to identify the most effective and efficient organisational structure. This document contains a preliminary analysis of existing organisational forms in LSGUs, examining the key criteria that determine which type of organisation belongs to each form of administrative structure. Current sectoral regulations do not always clearly indicate which organisational form applies to which type of entity. To determine whether an existing form is the most effective, efficient and economical, it is necessary to introduce binding criteria for LSGUs when founding new bodies. These additional criteria must establish and harmonise the obligations of the LSGU as the proposer, ensuring precise conditions for the creation of a new organisational form, thereby: curbing the establishment of organisations with very few employees and/or narrow competences; eliminating duplication and overlap of functions and competences among different bodies (or avoiding excessive functional synergy); streamlining and standardising the preparation and review of proposals for new organisations across different LSGUs; and securing future supervision and coordination of all bodies founded by LSGUs. The recommendations include proposed amendments to: the Law on Local Self-Government, and relevant sectoral laws. A draft outline is also provided for a future subordinate act that would establish the procedure for founding organisational forms within local self-government units.
1.3.3.6: Support for transforming the organisational forms of LSGUs in accordance with the subordinate legal framework—including the preparation of a handbook and model local acts for transforming organisational structures, and the provision of continuous advisory support to LSGUs. | Q4 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | A prerequisite for implementation is the amendment of the Law on Local Self-Government. | Set up a working group for the purpose of drafting the law.
1.3.3.7: Conducting an analysis of opportunities to strengthen the role and responsibilities of LSGUs in the field of civil protection, with the aim of enhancing LSG capacities in civil protection through the establishment of general-purpose civil protection units and alert-response units in all LSGUs. | Q4 2024 | MoI | Completed | - | Six LSGUs (Novi Pazar, Gornji Milanovac, Lučani, Čačak, Ivanjica and Golubac) have established, equipped and trained general-purpose civil protection units. In April 2024 the Emergency Situations Sector of the Ministry of Interior organised a workshop entitled “Development of Civil Protection at the Local Self-Government Level.” Fifty-seven municipalities participated. The 3-day workshop focused on sharing experiences and best practices for engaging civil protection units formed by local governments as auxiliary forces for emergency response, protection and rescue. The emphasis was placed on the training, staffing, capacity-building and equipping of civil protection units, as well as on their mobilization, deployment and financing, by familiarizing participants with existing solutions and the legal framework in the Republic of Serbia. |  |  | Through enhanced inspection oversight, the supervisory control of municipal operations will be strengthened.
.
Measure 1.3.4: Continuing development of inter-municipal cooperation in the implementation of local self-government competencies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Established and functional national financial mechanism for supporting inter-municipal cooperation* (Number) |  |  | 4 (2020) |  | 22 | 0 | Under the “Local Self-Government for the 21st Century” project, supported by the Government of the Swiss Confederation, no public call was issued under the Inter-Municipal Cooperation Fund—because local elections were held in the beneficiary municipalities, which would have affected the project timeline and, in particular, the adoption of the mandatory inter-municipal cooperation agreements.
Improved basic and sectoral legal framework for the development of inter-municipal cooperation: (0 - No, 1 - Yes) |  |  | 0 (2020) |  | 1 | 0 | The indicator has not been met because its implementation depends on amending the Law on Local Self‑Government.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.4.1: Provision of advisory (professional and technical) support to municipalities in establishing inter-municipal cooperation, and continuous development of tools to facilitate it (model inter-municipal agreements, guidelines for concluding and implementing the cooperation process, etc.). | Q4 2025 | MPALSG | In progress | 100% | In 2024 the SCTM prepared and published a Proposal on Possible Directions for Regulating Human Resource Management in inter‑municipal bodies, services, institutions and organisations.
1.3.4.2: Funding of inter-municipal cooperation projects | Q4 2025 | MPALSG | Completed | 100% | During 2024 four inter‑municipal‑cooperation (IMC) projects were completed: 1) The Cities of Belgrade and Novi Sad, together with the Belgrade city municipalities of Vračar and Savski Venac. The project strengthened IMC in improving accessibility and applying universal design in the delivery of services and information for persons with disabilities, while broadly promoting the partnership so it can be expanded. 2) Establishment of a joint Local Ombudsman Office for the City of Niš and the Municipality of Gadžin Han. 3) The Municipalities of Ruma, Stara Pazova and Irig established IMC to design, construct and manage the “Eastern Srem” regional water‑supply system; and 4) The Municipalities of Šid, Irig and Pećinci formed IMC to upgrade public lighting in the partner LSGUs through remote control technology.
1.3.4.3: Determination of the Draft Law on Amendments to the Law on Local Self‑Government by the working group, with the aim of regulating the possibility of introducing mandatory forms of inter‑municipal cooperation for exercising local‑government competences, and its subsequent referral to the Government so that it may adopt the Bill. | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | Working group has not been established. | Set up a working group for the purpose of drafting the law.
1.3.4.4: Alignment of sectoral regulations to intensify inter‑municipal cooperation in specific fields (e.g., the Public Enterprises Act, Communal Services Act, Passenger Transport Act, Water Act, etc.) | Q4 2025 | MPALSG |  | - | ..
1.3.4.5: Development of an analysis and of draft legislative measures and other administrative actions aimed at enhancing the role of administrative district councils in fostering inter‑municipal cooperation | Q4 2024 | MPALSG | Completed | 100% | The analysis first reviews the fundamental features of the concept and forms of inter‑municipal cooperation, the current regulatory framework, and the practical experience gained so far in its implementation. It then examines the basic characteristics of the status, role and real‑world functioning of administrative district councils. Finally, it identifies the key issues and the ways in which district councils can stimulate inter‑municipal cooperation, as well as the legislative measures and other administrative steps that could be taken to strengthen the councils’ role in this area.
1.3.4.6: Development of an online course on inter‑municipal cooperation | Q4 2024 | Selected LSGUs | Completed | 78.33% | During 2024 the course content on inter‑municipal cooperation was drafted and—after approval by the NAPA—was uploaded to NAPA’s e‑learning platform in December 2024.
.
Measure 1.3.5: Improving the local self-government development planning system
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Share of LSGUs which have adopted development plans in the total number of LSGUs (%) |  |  | 4.1( 2020) |  | 70 | 82.1 | Out of a total of 145 LSGUs, 119 had adopted development plans that remained in force during 2024.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.5.1: Consultations were held with representatives of local authorities and with the proposers of special regulations that govern the development of sectoral planning documents at the local level and are not aligned with the Law on the Planning System of the Republic of Serbia, and recommendations were prepared. | Q1 2025 | PPS |  | - | ..
1.3.5.2: Support to LSGUs for Drafting, Monitoring and Reporting on Development Plans (advisory support, guidance, coordination and experience sharing, etc) | Q4 2025 | PPS | In progress | 100% | During 2024, PPS and SCTM continued to provide ongoing advisory support to LSGUs for drafting Development Plans. Also, under the EU Exchange 6 Programme, a pilot process for reporting on development‑plan performance was carried out in three LSGUs selected through the 2024 call for proposals. |  |  | Based on the pilot reports, guidelines will be prepared for drafting performance implementation reports, and support will be offered to all LSGUs that are required to submit such reports in 2025.
1.3.5.3: Supporting LSGUs in drafting/revising their Development Plans (direct technical support for 8 LSGUs). | Q4 2024 | PPS | Completed | 100% | Through EU Exchange 6 (2023 call), eight LSGUs received assistance in preparing their development plans during 2024. In addition—resources permitting—support was extended to one additional municipality.
1.3.5.4: Monitoring of implementation of training programmes on applying the national planning system at local level within the Sectoral Continuous Professional Development Programme for LSGUs. | Q4 2025 | NAPA |  | - | ..
1.3.5.5: Promotion of the LSGU Business Information System (comprising the LSGU Analytical Service and the LSGU Analytical‑Reporting System) | Q4 2024 | PPS | Completed | 100% | Panel discussion “LSGU Analytical Service”: The conference “Compass for Strategic Decisions – From Data to Good Governance” was held on 30 October 2024 in Belgrade as part of the project “Local Self‑Government for the 21st Century,” supported by the Government of the Swiss Confederation. Details about the event are available on both the website and YouTube channel of the PP s and on the portals of other media outlets.
.
Specific objective 1.4: Improving the quality and availability of services of local government bodies, utilities and services of public institutions
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Baseline values for improving user satisfaction with local services established (0 – no, 1 – yes) |  |  |  |  | 1 | 0 | A survey was conducted, but no funds were subsequently secured to calculate the baseline values, i.e., to construct the composite scale needed for this indicator.
.
Measure 1.4.1: Development and improvement of the basic methodology and tools for monitoring the exercise of local self‑government competences and tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Analyses of the degree of established tasks in the priority areas of local self-government have been performed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 1
Percentage of administrative tasks from the Unified List of LSGU Tasks (tasks of administrative bodies) performed by LSGUs (number) |  |  | 0 (2020) |  | 80 | - | The indicator was not calculated in the analysis because the data are unreliable with respect to whether the relevant tasks are actually carried out in local self‑government units. In the coming period, either a different methodology or renewed data collection will be considered.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.1: Development of a Draft Law on Amendments to the Law on Local Self‑Government by a working group, with the aim of developing new modalities for managing the delegation of competences to local self‑government units in line with the Constitution and statutory possibilities, and referral of the draft to the Government for adoption as a Bill. | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | During 2024 a preliminary version of the Draft Law on Amendments to the Law on Local Self‑Government was prepared. |  | Working group has not been established. | Set up a working group for the purpose of drafting the law.
1.4.1.2: Updating the list of competencies and tasks at all levels of government and updating the Unified List of Tasks at the Local Level | Q4 2025 | MPALSG | In progress | 100% | During 2024 the list of tasks was updated—covering the period up to 30 September 2024—for the following fields: health, social welfare, education, economy, agriculture, regional development, urban planning, spatial planning, youth, sport, culture and information, telecommunications, science and technological development, veterinary and plant health, environmental protection, energy, mining, civil status, public property relations, general administration, construction and infrastructure, labour relations, employment, veteran and social issues, transport, finance, trade, tourism and hospitality, communal services, housing, local self‑government, development planning, and anti‑corruption at all levels of government. In addition, the report tracked all amendments to regulations and updated the Unified List at local level—again up to 30 September 2024—which now encompasses: finance; construction and infrastructure; spatial planning; public property; public information; public transport; communal services; culture; science and technological development; education; youth; general administration; agriculture, water management and forestry; economy and regional development; labour relations; employment; veteran issues; mining and geological exploration; transport; local self‑government; civil status of citizens (including civil registers and electoral rights); social welfare; sport; housing; trade, tourism and hospitality; telecommunications; veterinary and plant health; health; environmental protection; energy; inspection oversight and administrative inspections; defence; emergency situations and data secrecy; public procurement; development planning; and anti‑corruption. |  |  | Given that this is an ongoing activity, further updates of the list of tasks are planned.
1.4.1.3: Developing an analysis/verifying the degree of instituted tasks in priority areas from the Unified List of Tasks on a sample of 45 LSGUs | Q4 2024 | MPALSG | Completed | 100% | An analysis of task performance in a sample of 46 areas from the Unified List of Tasks was carried out in 45 LSGUs. Arandjelovac, Apatin, Bajina Bašta, Bečej, Bojnik, Bor, Boljevac, Čajetina, Golubac, Gornji Milanovac, Inđija, Kanjiža, Knjaževac, Kovin, Krupanj, Kula, Kuršumlija, Loznica, Lučani, Ljubovija, Majdanpek, Mionica, Negotin, Nova Varoš, Novi Pazar, Osečina, Petrovac na Mlavi, Požarevac, Ražanj, Rekovac, Senta, Sjenica, Smederevo, Sokobanja, Sombor, Sremska Mitrovica, Subotica, Šabac, Topola, Trstenik, Užice, Valjevo, Vladičin Han, Vladimirci and Žitište. The tasks were analysed in 46 areas, namely: culture, education, agriculture, water management and forestry, social welfare, housing, environmental protection, finance, construction and infrastructure, spatial planning, public information, public transport, communal services, science and technological development, youth, general administration, economy and regional development, labour relations, employment, veteran affairs, mining and geological exploration, transport, local self‑government, civil status of citizens, maintenance of civil registers and electoral rights, sport, trade, tourism and hospitality, telecommunications, veterinary and plant health, health care, energy, inspection, administrative inspections, defence, emergency situations and data secrecy, public procurement, and public property. The review showed that the execution of tasks across these 46 areas is highly uneven, reflecting the specific characteristics of each LSGU. The data also revealed that a significant number of tasks are not performed owing to a lack of human, financial and technical capacity. Moreover, many LSGUs emphasised the need for inter‑municipal cooperation.
1.4.1.4: Development of a cost‑and‑capacity analysis—covering financial, human, material and other resources—in the priority domains of local self‑government, for carrying out a selected sample of the key competences identified in the Unified List of LSGU Tasks. | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.4.2: Improving the capacity of local self-government to provide administrative services
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of LSGUs which have a one-stop shop in place (Number) |  |  | 14 (2020) |  | 34 | 65 | According to the records, 16 one-stop shops were established/opened in 2024, bringing the total number of one-stop shop opened by the end of 2024 to 65, while a further 4 one-stop shops are being implemented.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.2.1: Support to ministries for recording delegated administrative procedures of LSGUs in the National Register of Administrative Procedures, and capacity‑building of LSGUs for using their own Local Registers of Administrative Procedures | Q4 2025 | PPS | In progress | 100% | 17 training sessions were delivered for LSGU employees, attended by about 2,800 participants (of which 14 webinars were organised with Swiss support under the SDC–SCTM “Partnership for Good Local Governance” Programme). 16 local registers were published, covering a total of 775 procedures. |  |  | During 2025, support to LSGUs will continue—through mentoring and peer exchange—to publish procedures from their original competences.
1.4.2.3: Preparation of a capacity analysis of LSGUs for introducing e‑government, with a view to establishing inter‑municipal ICT centres to support, coordinate and enhance e-government | Q3 2025 | MPALSG |  | - | ..
1.4.2.4: Support for piloting an inter‑municipal ICT centre to coordinate and enhance e‑government. | Q4 2025 | MPALSG |  | - | ..
1.4.2.5: Support for establishing a one-stop shop / integrating administrative procedures in 10 LSGUs. | Q4 2025 | MPALSG |  | - | ..
1.4.2.6: Implementation of a support package to improve the efficiency of administrative services in 5 LSGUs. | Q4 2025 | MPALSG | In progress | 100% | The support package is being delivered in the municipalities of Arilje, Veliko Gradište, Kosjerić, Temerin and Ćuprija. During 2024, in those 5 LSGUs support was provided for organisational development to establish a one-stop shop (single administrative point), through identification of the possible procedures and bodies whose proceedings could be included by organising a one-stop shop within the local self-government, including a draft decision on establishing the one-stop shop, a draft cooperation agreement, and procedures for communication and exchange of data/documentation with other bodies; organising trainings and workshops; and providing other forms of advisory support for establishing the one-stop shop, including adapting procedures to the tested models. In total, 41 one-stop shops were established, namely: Arilje established 6 one-stop shops, Veliko Gradište – 10, Kosjerić – 8, Temerin – 7 and Ćuprija – 10. In these 5 LSGUs a total of 5 trainings on the concept of one stop shop were held, attended by 52 participants, and 5 trainings on models of one-stop shop and the method of linking procedures, attended by 45 participants. For these 5 LSGUs support was provided for organisational development for full implementation of the Law on the Register of Administrative Procedures through holding 2 trainings related to entering procedures into the Register of Administrative Procedures, attended by 50 participants. Inthese 5 LSGUs employees’ knowledge was enhanced through conducting 5 trainings to improve internal communication among employees, attended by 63 participants, and 5 trainings to improve external communication, attended by 75 participants. |  |  | During 2025 support will be focused on improving efficiency and effectiveness by standardising administrative procedures and processes through adapting administrative proceedings in accordance with models of administrative procedures and the requirements prescribed by the Law on the Register of Administrative Procedures; optimising work processes; improving record-keeping; monitoring deadlines in proceedings, including the new institutes of the Law on General Administrative Procedure (objections, responses to appeals, etc.); support for introducing and maintaining an electronic database/list of procedures and office proceedings; improving transparency and awareness of parties and citizens regarding the administrative procedures carried out in the selected municipalities.
1.4.2.7: Support for establishing youth offices at the level of all LSGUs, either individually or through inter-municipal cooperation. | Q4 2025 | MTY | In progress | - | The Ministry of Tourism and Youth continuously advocates that local self-government units establish youth offices in order to ensure the active inclusion of young people in the life and work of the community, the empowerment of young people, and the provision of support for organizing various social activities of young people. After the establishment of a youth office in a LSG unit, the Ministry provides support through a public call for proposals to assist local self-government units in implementing youth policy at the local level.
1.4.2.8: Development of online trainings for LSG heads in the area of performance management and lines of accountability | Q4 2025 | NAPA |  | - | ..
1.4.2.9: Support for strengthening managerial accountability in local self‐government units | Q4 2025 | MPALSG | In progress | 100% | 119 mentoring sessions were held, as well as 50 trainings on the topic of managerial accountability in LSGUs (“Introduction to managerial accountability,” “Annual administrative work plan,” “Delegation,” “Ethics and integrity,” “Organizational culture of accountability”) and 2 peer‐learning workshops. A total of 503 participants attended the trainings and workshops. |  | Due to local elections held in two cycles, some project activities were postponed to 2025, while activities on this topic were moved forward. | Mentoring and training on drafting an administrative work plan and reporting on its implementation, as well as training and mentoring on performance management.
.
Measure 1.4.3: Initiation of systemic reforms of utility activities and services
Institution in charge: MINISTRY OF CONSTRUCTION, TRANSPORT AND INFRASTRUCTURE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Basic legal framework in the area of performing utility activities and delivery of utility services has been improved (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 1
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.3.1: Submitting the draft Law on amendments to the Law on Utility Activities to the Government for review and approval of the legislative proposal (Bill) | Q3 2024 | MCTI | Completed | - | The Law was adopted by the National Assembly. |  |  | Enactment of the by‐laws prescribed by this Law.
1.4.3.2: Drafting of a bylaw regulating the methodology for setting prices of communal services | Q4 2025 | MCTI | Has not commenced | - | .. |  | Given that the Law on Communal Services was adopted in December 2024, a working group for drafting the bylaw has not yet been formed. | Formation of a working group for drafting the by‐law.
1.4.3.3: Preparation of models of local acts for the implementation of the new Law on Communal Services. | Q2 2025 | MCTI | Has not commenced | - | .. |  | SCTM has not yet undertaken the drafting of model acts, since the Law on Communal Services was adopted at the end of 2024. | This activity will be implemented during 2025.
1.4.3.4: Organisation of training for the implementation of the new Law on Communal Services. | Q2 2025 | MCTI | Has not commenced | - | ..
1.4.3.5: Developing an electronic portal for reporting on the performance of communal services | Q4 2025 | MCTI | Has not commenced | - | Developing an electronic portal for reporting on the performance of communal services will contribute to the digitalization of the process, reduce human error when manually entering incoming data, enable access to up-to-date information, and allow the database to be refreshed in real time… |  | Given that the Law on Communal Services was adopted in December 2024, a working group for drafting the layout of the reporting forms has not yet been formed. | Establishing a special working group to draft the layout of the reporting forms for the performance of communal services and developing a digital platform for reporting on the status of communal services.
1.4.3.6: Formation of a commission to propose measures and define guidelines for the development of communal enterprises. | Q4 2024 -> Q4 2025 | MCTI | Has not commenced | - | .. |  | The Government is in a technical mandate. | Final deadlines will be determined upon the adoption of the new 2024–2025 Action Plan.
1.4.3.7: Establishment of an obligation for all LSGUs to conduct regular evaluations of the operations of local enterprises and to inform the competent ministry, in order to prepare recommendations for improving their performance | Q4 2024 -> Q4 2025 | Ministry of Economy | In progress | - | A cooperation has been established with SCTM and RELOF in order to prepare a comprehensive review of public enterprises and capital company entities founded by autonomous provinces, local self-government units, and city municipalities in accordance with the law, as part of the project, and perform their full evaluation. |  | It is necessary to carry out a complete analysis of public utility enterprises and LSGUs and their current status. Article 49 of the Law on Public Enterprises and Capital Companies defines the obligation of the Ministry, and the law has been in force since September 2024. | The first version of the evaluation methodology has been drafted; visits to selected LSGUs were conducted, and the state-of-play and collected data were analysed to define the best approaches for implementing the activities.
1.4.3.8: Trainings and mentoring for indirect budget users from 10 LSGUs on strengthening managerial accountability | Q4 2025 | Ministry of Economy | In progress | 100% | A total of 40 trainings were held on managerial accountability: “Introduction to managerial accountability,” “Delegation,” “Ethics and integrity,” and “Organizational culture of accountability.” A total of 176 participants attended the trainings. Additionally, 152 participants were trained on oversight of budgetary organizations. 2 peer-learning workshops were held with 64 participants. |  | Due to local elections held in two cycles, some project activities were postponed to 2025, while activities on this topic were moved forward. | Mentoring on drafting the budgetary organization’s work plan and reporting on its implementation.
1.4.3.9: Trainings and mentoring for public and other enterprises founded by the 10 LSGUs on strengthening managerial accountability | Q4 2025 | Ministry of Economy | Completed | 100% | A total of 40 trainings were held on managerial accountability: “Introduction to managerial accountability,” “Delegation,” “Ethics and integrity,” and “Organizational culture of accountability.” A total of 111 participants attended the trainings. |  | Due to local elections held in two cycles, some project activities were postponed to 2025, while activities on this topic were moved forward.
1.4.3.10: Trainings and mentoring for public and other enterprises founded by the 10 LSGUs on the topic of lines of accountability | Q4 2025 | Ministry of Economy | In progress | 74% | Ten workshops were held on Key Performance Indicators (KPIs), and 158 mentoring sessions were conducted on the same topic. Additionally, two peer-learning workshops took place, with 40 participants. |  | No deviation | Trainings and mentoring were provided to strengthen specific aspects of lines of accountability that were identified as weak links through the 2024 RELOF Index measurements.
1.4.3.11: Trainings and mentoring for public and other enterprises founded by the 10 LSGUs on the topic of corporate governance | Q4 2025 | Ministry of Economy | Completed | 98% | 48 participants were trained on oversight of public enterprises at the local level, and 13 participants were trained on improving reporting quality through software tools.
.
Measure 1.4.4: Improvement of local public services through local economic development and implementation of public-private partnership models
Institution in charge: MINISTRY OF ECONOMY
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Improved legal framework governing LSGU actions in the field of local economic development (LED) (0 - No, 1 - Yes). |  |  | 0 (2020) |  | 1 | 1 | Enhanced the Investment Law as it pertains to the actions of LSGUs in the field of local economic development (LED). It was determined that, in addition to the Law on Local Self-Government (specifically Article 20 paragraph 1 item 7 and Article 32 item 4), all existing investment promotion programmes governed by current Government regulations provide a sufficient instrument for attracting investors to projects of local importance—this serving as the direct legal basis for municipal and city authorities to act in the area of LED.
Percentage of total number of LSGUs which have adopted a LED programme (%) |  |  | 5 (2019) |  | 20 | 30 | The adoption of a LED Programme is regulated under the Law on Local Self-Government
Percentage of LSGUs which have PPP projects (%) |  |  | 48 (2020) |  | 58 | 71 | Planned target value has been achieved
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.4.1: Preparing the proposed amendments to provisions of the Law on Investments relating to the adoption of programmes for LED, which would define a set of LSGU activities in the area of LED and LSGU services for businesses | Q4 2025 | Ministry of Economy | This initiative has been abandoned. | - | .. |  | Additional amendments to the Investment Law have been abandoned. Article 20 of the Investment Law regulates the unit for local economic development. No further regulation of the position and work of that unit is necessary. Moreover, Articles 20 and 32 of the Law on Local Self-Government regulate these matters.
1.4.4.2: Support to LSGUs in implementing LED activities (advisory and mentoring support, networking and knowledge sharing, regional workshops, drafting instructional materials, expert support for drafting a programme for LED, etc.) | Q4 2025 | Ministry of Economy | In progress | 100% | Under the SDC–SCTM “Partnership for Good Local Governance” Programme, the following instructional material has been produced: Handbook for LSGUs on Controlling and Monitoring Investments of Local Importance Supported by Incentive Funds from the Municipal Budget; Knowledge‑sharing was enabled through the round table “Presentation of the Analysis of Local‑Level Incentive Policies for the Economy and Opportunities for Enhanced Action by LSGUs in this Field,” held in February 2024. The event included experience from three LSGUs in designing local incentive systems, and proposals from business entities located in those three LSGUs on how to improve the local business environment; To foster networking, two meetings of the Local Economic Development (LED) Network were held; In addition, under the SIDA–SCTM project, expert and technical support was provided to the cities/municipalities of Niš and Preševo in drafting their LED Programmes. Support in the field of LED and women’s entrepreneurship was also provided to the City of Zrenjanin and the Municipality of Žagubica. |  |  | Planned activities for 2025 include two online workshops on local‑level incentive policy; a round table on the future directions of LED and 2 further meetings of the LED Network.
1.4.4.3: Monitoring the delivery of trainings in the area of local economic development | Q4 2025 | NAPA | In progress | 100% | During 2024, two accredited trainings on “Application of State Aid Control Rules at the Local Level” were conducted, and a third will be delivered at the beginning of 2025. |  |  | During 2025, the delivery of the accredited training “Application of State Aid Control Rules at the Local Level” will be completed, and an accredited training on “Instruments for Stimulating Economic Development and Supporting the Economy” will be conducted.
1.4.4.4: Drafting amendments to the Law on PPP (based on the needs and the findings of the situation analysis) | Q4 2025 | Ministry of Economy | In progress | - | A working group has been formed to draft amendments to the Law on Public–Private Partnership (PPP). The working group is tasked with aligning the provisions of the law with EU Directives Nos. 23 and 24 |  |  | During 2025, a Draft Law on Public–Private Partnership will be prepared.
1.4.4.5: Support to LSGUs in the process of selecting a private partner, implementing potential PPP projects, and overseeing their execution (advisory and mentoring support, direct technical assistance, etc.). | Q4 2025 | Ministry of Economy | In progress | - | Regular meetings have been held with LSGUs to provide support at all stages of PPP project preparation and implementation. The Commission has produced a Handbook to inform and facilitate the implementation of PPP projects. The Handbook is publicly available on the website of the Public–Private Partnership Commission. |  |  | Advisory activities and support for LSGUs in selecting private partners and carrying out PPP projects will continue for all interested LSGUs.
.
Measure 1.4.5: Measure 4.5: Development of methodological and analytical tools for monitoring LSGU services and citizens' satisfaction with their quality
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Survey on the availability and quality of priority services delivered by LSGUs has been conducted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 0 | -
Survey on the users’ satisfaction with the services delivered by LSGUs has been conducted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 0 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.5.1: Conducting the survey and measuring the accessibility and quality of priority services provided by LSGUs. | Q4 2025 | MPALSG |  | - | ..
1.4.5.2: Conducting a survey of citizens’ satisfaction with LSGU services | Q3 2024 | MPALSG | Completed | 100% | After the survey was carried out at the end of 2023 on a sample of 50 LSGUs, the collected data were analysed and a report was prepared. The survey findings were presented to representatives of the MPALSG and to local self-governments at four regional presentations held during June 2023 in Kraljevo, Leskovac, Zaječar and Šabac. Each LSGU received its individual findings, and the report at the level of the 50-unit sample is available on the PRO – Local Governance for People and Nature programme website.
1.4.5.3: Development of a methodology for measuring the quality and accessibility of LSGU services in the field of citizens’ civil status affairs, with guidelines for improving the situation of vulnerable categories and a survey of those citizens’ satisfaction with the services provided | Q4 2024 | MPALSG | Completed | 100% | The objective is to conduct field research on satisfaction with the quality and accessibility of LSGU services in the area of citizens’ civil status affairs and to measure their satisfaction—i.e, to gather relevant information that will most effectively identify and recognise persons at risk of statelessness in the LSGUs surveyed, and the barriers that exist so that this risk can be eliminated. The survey was conducted in substandard settlements in 38 LSGUs in Central Serbia. The conclusions indicate that the number of persons without any documents or a regularised civil status record has decreased several-fold compared to the previous period, and that certain mechanisms and activities by the competent ministry and the local self-government units have yielded satisfactory results in combating statelessness. The conclusions also show that only a negligible number of persons lack complete information or support from LSGUs regarding the regularisation of their civil status records.