## Sve aktivnosti export_1
Annual Report on the Implementation of the 2024 Action Plan for the: |  |  |  |  | Implementation of the e-Government Development Programme of the Republic of Serbia 2023−2025
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | e-Government Development Programme of the Republic of Serbia 2023−2025 with its Action Plan.
Overall objective 1: Development of an efficient and user-centric administration in a digital environment
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Overall result of Serbia from the EU eGovernment Benchmark Report: (%) |  |  | 48.6 (2022) |  | 56 | 61.5
.
Specific objective 1: Development of e-Government infrastructure and ensuring interoperability
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
The number of government bodies, APs and LSGUs which in the state data management centres and storage centres keep its registers and other software solutions (Number) |  |  | 36 (2022) |  | 50 | 68
The number of bodies downloading data from the Central Population Register, Real-Estate Cadastre, Register of Businesses and Address Register through the service bus. (Number) |  |  | 435 (2022) |  | 500 | 500 | Integration of the CPR and the SBRA through the Register Office covered more than 400 bodies.
The percentage of health institutions connected the Unified Information-Communication Network of e-Government (%) |  |  | 0 (2022) |  | 2.5 | 8.06 | The Office started the project of connecting and migration of local health and laboratory systems into the State Data Centre in Kragujevac, and the first 30 health institutions have successfully been connected to the new e-Health Network.
.
Measure 1.1.1: Improvement of state data management and storage centres in Belgrade and Kragujevac
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
The number of registers and other software solutions which are kept in state data management and storage centres (Number) |  |  | 83 (2022) |  | 105 | 330 | The number of software solutions which are kept in the State Cloud is 330. This number does not cover software solutions which are kept in the state data management and storage centres through the collocation service. Nineteen state bodies are using collocation service.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.1.1: Furnishing of the Data Centre Kragujevac with ICT equipment | Q3 2023 | ITE Office | Completed | - | ..
1.1.1.2: Improvement of cloud platform in the Data Centre in Kragujevac | Q4 2023 | ITE Office | Completed | - | ..
1.1.1.3: Implementation of the NOC System (Network Operation Centre) on the entire UIC | Q4 2024 | ITE Office | Completed | - | ..
1.1.1.4: Construction of the Facility 3 of the Data Centre in Kragujevac | Q4 2025 | ITE Office | In progress | 100% | Preparatory works have been completed. Phases 1 and 2 of the construction are ongoing. The completion of the first phase 2 is expected by the end of 2025. |  | No deviation. | It is necessary to sign the contract for realization of other construction phases.
1.1.1.5: Migration of software solutions of the bodies into the cloud (data centres) | Q4 2025 | ITE Office | In progress | 100% | The activity is a continuous one. During 2024, 13 software solutions were migrated into the cloud. |  |  | The activity is realized in accordance with the planned dynamics.
1.1.1.6: Integration of health institutions in the Unified ICT Network of the Government Bodies | Q4 2025 | ITE Office | In progress | 100% | During 2024, 12 integrations of health institutions in the Unified ICT Network of the Government Bodies have been accomplished. |  |  | The activity is realized in accordance with the planned dynamics.
.
Measure 1.1.2: Improvement of the electronic procedures of the bodies through use of eID system, eRegistry, ePayment and eArchive
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of bodies** which conduct their office procedure exclusively through Registry (Number) |  |  | 0 (2022) |  | 350 | 220 | Instances have been launched for 400 bodies.
Number of institutions which have connected the existing software solutions to the e-Register Office and e-Archive (Number) |  |  | 0 (2022) |  | 5 | 5
Number of government bodies using collaboration services (Number) |  |  | 21 (2022) |  | 28 | 28
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.2.1: Improvement of functionalities of the ePay system on the eGovernment Portal (for payment of all fees, that is, all levies, which are paid as one unfed bill in the course of the service provision, for which only one transaction fee is charged. | Q3 2023 | ITE Office | Completed | - | ..
1.1.2.2: Issuing of a certificate on facts for which there is an official record in accordance with the deadlines for creation of technical and personal conditions - I phase: Establishment of the information System “VOJEVID” (main project and software - module Military Service Obligation), securing hardware and network infrastructure. | Q3 2023 | MD |  | - | ..
1.1.2.3: Establishment of eArchive | Q4 2023 -> Q4 2024 -> Q4 2025 | ITE Office | In progress | - | The contract for the mentioned activity is being implemented. To set up the system, it is necessary to procure additional hardware components. |  | Impossibility of implementing the addendum to the contract in the sense of procuring additional hardware before the process of Project restructuring comes to an end. Project restructured in June 2024. Addendum to the Contract approved by the World Bank in January 2025. | A new deadline for completion has been set: Q2 2025 Finalization of all remaining phases of the activities and full implementation of the system.
1.1.2.4: Issuing of a certificate on facts for which an official record is kept, in accordance with the deadlines for creation of technical and personal conditions - II phase: Setting up of a software: module compulsory labour and requisition | Q3 2024 | MD |  | - | ..
1.1.2.5: Preparing draft amendments to the Law on electronic government in view of its alignment with the Directive EU 2019/1024 | Q4 2025 | MPALSG | Completed | - | ..
1.1.2.6: Issuing of a certificate on facts for which an official record is kept, in accordance with the deadlines for creation of technical and personal conditions - III phase: Development of the application for issuing certificates for the eGovernment Portal and for connection to the databases of government bodies | Q4 2025 | MD |  | - | ..
1.1.2.7: Promotional and educational activities within the administration for purpose of terminating the obligation of submitting the evidence on payment in procedures where ePayment system is used. | Q4 2025 | ITE Office | Completed | - | ..
.
Measure 1.1.3: Establishing new and improving existing registers and records in electronic form to support the development of e-Government services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of established and improved records in electronic format (registers) (Number) |  |  | 35 (2022) |  | 37 | 37 | Cumulative number of established and improved records in electronic format (registers)
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.3.1: Establishment and development of the Geodetic Cadastral Information System (GCIS). Development of Integrated System for Real-Estate Cadastre and Registration of Rights - ISREC | Q4 2023 | RGA | Completed | 30.75% | All funds approved for extension of the previous project financed through the loans of the World Bank (REMP 1) (until July 2024), and intended for realization of the development and implementation of the ISREC system in the selected real-estate cadastre services, have been executed in accordance with agreed deadlines and in compliance with the required quality of works and results.The continuation of the activities regarding implementation of the ISREC within the framework of the Second project for improvement of real estate management (REMP 2) is planned for Q1 2025. |  |  | In view of continuing initiated activities regarding introduction of integrated GCIS, RGA was approved a new project financed through the loans of the World Bank, REMP 2, wherein one of the components will be continuation of the implementation of the ISREC on the entire territory of the Republic of Serbia, in all remaining real-estate cadastre services.
1.1.3.2: Establishment of the system of electronic registration on the status registers of the SBRA (replacement of the CORE system for registration procedure, migration of existing and implementation of new registers, integration with other systems of eGovernment and improvement of interoperability). | Q4 2024 -> Q4 2025 | SBRA |  | 99.67% | ..
1.1.3.3: Improvement of the system of distribution of geospatial data - GeoSerbia 2.0 | Q4 2023 | RGA | Completed | - | All funds approved for the extension of the previous project financed through the loans of the World Bank (REMP 1) (until July 2024), and intended for realization of improvement of the system of distribution of geospatial data GeoSerbia 2.0, have been executed in accordance with the agreed deadlines and in compliance with the required quality of works and final results. Continuation of activities regarding improvement of the system of distribution of geospatial data through further improvement of the RGA services for Web and mobile applications within the framework of the Second project for improvement of real estate management (REMP 2) is planned for Q4 2025. |  |  | In view of continuing initiated activities on implementation of GCIS, the RGA was approved a new project financed through the loans of the World Bank REMP 2, wherein one of the components will be the continuation of the development of the functionality of the GeoSerbia 2.0 platform in so as to improve the distribution of geospatial data through creation of new services for Web and mobile applications.
1.1.3.4: Establishing the Metaregister; Ensuring interoperability in e-Government | Q2 2024 -> Q4 2025 | ITE Office | In progress | 100% | Interoperable platform is successfully implemented. |  | Reduced level of responsiveness in the departments for implementation of system components. In order to accelerate implementation, the Project is hiring additional consultants for purpose of creation of missing catalogues. | A new deadline for completion has been set: Q4 2025
1.1.3.5: Creation of systems for external support to social welfare institutions (CALL desk for social welfare) | Q4 2024 -> Q4 2026 | MLEVSA | In progress | - | Public procurement has been initiated and the contract concluded in December 2024.
1.1.3.6: Improvement of the Social Card Register | Q4 2024 -> Q4 2026 | MLEVSA | In progress | 100% | Public procurement has been initiated and the contract concluded in December 2024. |  |  | Realization of the phases referred to in the Contract with the deadline until 20th February 2026.
1.1.3.7: Improvement of the Social Welfare IS - SOZIS | Q4 2024 -> Q4 2026 | MLEVSA | In progress | - | Public procurement has been initiated and the contract concluded in December 2024. |  |  | Realization of the phases referred to in the Contract with the deadline until 30th November 2026..
1.1.3.8: sSpace | Q4 2025 | MCTI | Has not started | - | Re-establishment of the Central Register of Planning Documents as an integral part of the eSpace and ePlan. |  |  | Adoption of the by-laws relevant for eSpace.
1.1.3.9: Digitalization of two registers selected on the basis of a previously conducted analysis in order to determine the priorities in digitalization of basic registers | Q1 2025 | ITE Office | aborted | - | The activity has been abandoned. |  | The activity has been abandoned. | The activity has been abandoned.
1.1.3.10: Improvement of the child and family protection IS | Q4 2025 | MLEVSA | In progress | 100% | The supplier has fulfilled contractual obligations. |  |  | Initiation of a new annual contract for 2025.
1.1.3.11: Improvement of the veteran-disability protection IS; | Q4 2025 | MLEVSA | Has not started | - | There was no need for improvement of the information system in 2024. |  |  | Initiation of a new annual contract for 2025.
1.1.3.12: Establishment of the IS in the residential social welfare institutions | Q4 2025 -> Q4 2026 | MLEVSA | In progress | 79.92% | Public procurement has been initiated and the contract concluded in October 2024. The first phase of the contract realized. |  |  | Realization of the remaining second phase referred to in the Contract with the deadline until 1st June 2025.
1.1.3.13: Establishment and development of the geodetic cadastral information system (GCIS) IS for the cadastre of infrastructure and underground facilities (software) | Q4 2025 | RGA | Completed | 89.55% | All funds approved for extension of the previous project financed through loans of the World Bank (REMP 1) (until July 2024), and intended for realization of the activities of development of the Utility Cadastre IS (which is a subsystem of the IS of Cadastre of Infrastructure and Underground Facilities), have been executed in accordance with the agreed deadlines and in compliance with the required quality of works and final results. The continuation of the activity regarding development and implementation of the IS for Cadastre of Infrastructure and Underground Facilities within the framework of the Second project for improvement of real estate management (REMP 2) planned for Q3 2025. |  |  | In view of continuing initiated activities on implementation of the GCIS, the RGA has been approved a new project to be financed through the loans of the WB - REMP 2, wherein one of the components relates to further development and implementation of the IS for the Cadastre of Infrastructure and Underground Facilities. Furthermore, the activities related to development of this IS will be supported through the funds for the implementation of the Reform Agenda of the Republic of Serbia.
1.1.3.14: Development of the Disaster Risk Register | Q4 2025 | RGA | In progress | 60% | The tender procedure has been conducted and the phase of development of the technological solution for the Disaster Risk Register has been completed during 2024. In accordance with the AP of the project, previously set deadline (Q4 2025) has been moved to Q2 2025. |  |  | Within further activities related to implementation of the second phase of the Disaster Risk Register, the activities related to testing of the developed solution, training of the system users, drafting of the documentation for users, entry of new sets of data and development of the tool for entry of documentation related to risks, have been planed in 2025. Furthermore, considering the recognized needs for new functionalities in the IS for disaster risk reduction (DRR), by means of introduction of procedural solutions as well as entry of key data for all identified risks, RGA will, in cooperation with the UNDP, initiate a new project which will represent the third phase of system improvement.
1.1.3.15: Establishment and development of the geodetic cadastral information system (GCIS) IS for Land Management | Q4 2024 | RGA | Has not started | - | Considering that the RGA has not been approved a new project to be funded through the loans of the WB as it was initially planned, the funds needed for development of the IS for Land Management have not been secured. The beginning of the activities regarding development and establishment of the IS for Land Management within the framework of the Second project for improvement of real estate management (REMP 2) are planned for Q1 2026. |  |  | In view of continuing initiated activities on implementation of the GCIS, the RGA has been approved a new project to be financed through the loans of the WB - REMP 2, wherein one of the components relates to development and implementation of the IS for Land Management. Furthermore, the activities related to development of this IS will be supported through the funds for the implementation of the Reform Agenda of the Republic of Serbia.
1.1.3.16: Establishment of the Smart Spatial Data Infrastructure (Smart SDI) | Q4 2025 | RGA | In progress | 46% | The tender has been conducted and the contract signed for the establishment of the Smart Land Parcel System until the end of 2024, which obligates the selected contractor to develop and implement the agreed solution until November 2025. Moreover, during 2024, the concept and technical specification for a solution for management of RGA portfolio was prepared, whereas only concept solution has been prepared for new RGA Intranet and the drafting of the technical specification for the tender is ongoing. |  |  | During 2025, the implementation of the Smart Land Parcel System, priority module of the new Intranet solution (eLearning) and the testing of the concept and software solution for implementation of portfolio management system is expected, thus executing the remaining funds from the received donation. Additionally, in accordance with the procedure of the SIDA, the RGA will ask for extension of the project as well as the additional funds so that the previously initiated project activities could be completed during 2026, especially related to inclusion of all stakeholders (government entities on local and other levels) into new Smart Land Parcel System intended for sustainable use and management of the land in the Republic of Serbia.
1.1.3.17: Digitalization of the Agricultural Farms Register (development of the eAgrar software solution) | Q4 2025 | MAFWM | In progress | 44% | eAgrar software solution has integrated the Agricultural Farms Register, Animal Cadastre and the Land Cadastre through application (in the part referring to land parcels). The platform has been divided to eAgrar (Agricultural Farms Register) and eIncentives (incentives for agriculture and rural development). eAgrar contains connected data on animals and land parcels for each farm. Digitalization of all farms has been accomplished. Earlier the data on those farms have been kept in paper form. All changes in the data, registration of new crops or animals, restoration or registration of a new farm is exclusively done electronically. |  |  | In 2025, the software solution will restore all registered farms and regularly update its data which will serve as a basis for applications for the incentives as well as evidence of a farm status and as such it represents an electronic register of all farms on the territory of Serbia and will serve for further development of digitalization in the agriculture.
1.1.3.18: Establishment and development of the geodetic cadastral information system (GCIS) IS for mass evaluation of real-estate value and determining the housing units price index. | Q4 2025 | RGA | Has not started | - | The funds of the previous project financed through the loans of the World Bank (REMP 1) were used for preparation of the technical specification of the future IS, whereas its development and implementation will be part of the approved new project, the so-called Second project for improvement of real estate management (REMP 2). The activities of the IS development are expected to start in Q3 2025. |  |  | In view of continuing initiated activities on implementation of the GCIS, the RGA has been approved a new project to be financed through the loans of the WB - REMP 2, wherein one of the components relates to development and implementation of the IS for mass evaluation of real-estate value.
.
Measure 1.1.4: Improving public administration human resources to establish and apply information technologies in e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of heads employed on job posts for IT officers (Number) |  |  | 6,402 (2022) |  | 6,600 | -
Number of officers trained to work in digital environment as per authorities and local self-government units in which they are employed (Number) |  |  | 1,200 (2022) |  | 1200 | -
Number of heads employed on job posts for IT officers in the public administration authorities (Number) |  |  | 610 (2022) |  | 655 | -
Number of heads employed on job posts for IT officers in the local self-government units (Number) |  |  | 470 (2022) |  | 500 | -
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.4.1: Improvement of the capacities of the organizational units in charge of eGovernment affairs for purpose of implementation of the Law on eGovernment | Q1 2024 | MPALSG | Has not started | - | .. |  | After the adoption of the budget for 2024, realization of this activity has not started.
1.1.4.2: Delivery of trainings for the public administration officers related to definition of procedures and control of enforcement of regulations on information security prescribed by the Regulation on security and protection of personal data in turn prescribed by the Law on Protection on Personal Data. | Q1 2024 | ITE Office | Completed | 100% | ..
1.1.4.3: Drafting of the analysis of the needs in the public administration for IT profiles and staff in charge of IT projects management as well as the proposals for sustainable scheme for managing such personnel in the public administration and the LSGUs. | Q2 2025 | MPALSG |  | - | ..
1.1.4.4: Drafting of the on-line courses in the area of eGovernment for civil servants and officers in the LSGUs on the platform of the National Academy for Public Administration (NAPA). | Q4 2025 | NAPA | In progress | - | During 2024, 134 trainees have finished on-line training in the area of Electronic Office Operations. The following on-line trainings have been published in view of strengthening eGovernment - the Work and Communication with Service Users, Electronic Business Communication, New Technologies, Strategic Planning in the eGovernment and Transformation/Re-engineering of Business Processes, Whole-of-Government (WoG) Approach, Digital Transformation, eGovernment and Change Management, Training for Civil Servants Awareness Raising regarding Information Security and the Metaregister and Interoperability, which were completed by 2837 trainees.
1.1.4.5: Delivery of training for the employees in the authorities in charge of provision of electronic services in the public administration through use of software solutions. | Q4 2025 -> Q4 2026 | ITE Office | Has not started | - | Training for employees in the public administration bodies relating to use of software solutions for provision of electronic services, will be organized after the completion of the digitalization of services. This approach ensures that the employees are appropriately prepared for efficient use of newly established digital tools and systems. |  | The training for employees in the public administration bodies could not have been delivered in the planned deadline because they were conditional upon completion of the digitalization of services. This sequence is necessary for trainings to be efficient and based on the final version of digital solutions. As a measure, the training will be organized soon after the successful implementation, in order to ensure for the employees to be fully prepared to work with new systems. | Carrying out the process of digital services implementation.
1.1.4.6: Drafting of the analysis for improvement of LSGUs capacities for introduction of eGovernment in view of establishing ICT service/coordination centres for support to the establishment and improvement of eGovernment for the group of local self-government units. | Q4 2025 | MPALSG |  | - | ..
.
Measure 1.1.5: Improving information security and standards
Institution in charge: MINISTRY OF INFORMATION AND TELECOMMUNICATIONS
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Share of institutions which have an established and functional information security system and which meet information security standards (ISO 27001 and ISO 20000 adopted the Regulation on information security) compared to the implemented regular and extraordinary inspections in one calendar year (Number) |  |  | 95 (2022) |  | 100 | 100
Share of institutions which have an established and functional information security system and which meet information security standards (adopted Disaster recovery plan) compared to the implemented regular and extraordinary inspections in one calendar year (%) |  |  | 90 (2022) |  | 100 | 100
Number of civil servants that have completed cyber exercises (Number) |  |  | 150 (2022) |  | 210 | 210
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.5.1: Informing the public on use of electronic identification scheme and qualified trusted services in electronic administrative procedure | Q4 2023 | MIT | Completed | - | Ministry of Information and Telecommunications has conducted activities related to informing the public on use of electronic identification scheme and qualified trusted services in electronic administrative procedure. The public was informed on importance of these services for safe and efficient electronic operations with the public administration authorities through different communication channels. Furthermore, the Ministry has participated in the analysis of existing regulations and offered support to improvement of regulatory framework in this area. To this effect, the drafting of the amendments to the Law on Electronic Document, Electronic Identification and Trusted Services in Electronic Operations is ongoing. These activities are aimed at user awareness raising and improvement of the use of digital services in the public administration. |  |  | Future steps in the area of informing the public on use of electronic identification scheme and qualified trusted services in electronic administrative procedure include continuation of user awareness raising and improvement of information availability. It is planned to use different communication channels to continue promoting importance of electronic identification and safe digital services. Furthermore, the possibility to improve regulatory framework in this area will be taken into consideration in accordance with European standards and requirements of digital transformation. In cooperation with relevant institutions, further development and implementation of mechanisms to support the users of these services will be undertaken. In parallel, the Ministry will continue with the activities on drafting and adopting amendments to the Law on Electronic Document, Electronic Identification and Trusted Services in Electronic Operations, so as to ensure more efficient application of these solutions. These activities aim at further strengthening of electronic government and raising the level of digital literacy in the population and business community.
1.1.5.2: Informing and education of civil servants on the regulations and their practical application in the area of electronic identification scheme and qualified trusted services. | Q4 2023 | MIT | Completed | - | Ministry of Information and Telecommunications has conducted activities of informing and education of civil servants on the regulations and their practical application in the area of electronic identification scheme and qualified trusted services. Within these activities, the civil servants were informed about the relevant legal framework, obligations of the public administration bodies as well as on practical aspects of the application of these solutions in the electronic administrative procedure. Moreover, in cooperation with competent institutions, the possibilities for improvement of the enforcement of existing regulations and their alignment with the modern technological and regulatory requirements were considered. |  |  | Future steps in terms of informing and education of civil servants on electronic identification schemes and qualified trusted services include continuation of awareness raising and improvement of the knowledge on enforcement of regulations in this area. Further education and training has been planned to be delivered through different formats, including workshops, webinars, technical guidelines so as to ensure efficient enforcement of the regulations in the practice. In addition, in view of improvement of regulatory framework, the work on the analysis of the needs of public authorities and possibilities for additional support in application of electronic identification and trusted services will continue.
1.1.5.3: Establishing a Security Operation Centre (SOC) and a Computer Emergency Response Team (CERT) | Q4 2023 | ITE Office | Completed | - | ..
1.1.5.4: Establishing the laboratory for information security and the training centre for testing of information security of the ICT. | Q4 2025 | ITE Office | aborted | - | The activity has been abandoned. |  | The activity has been abandoned. | The activity has been abandoned.
1.1.5.5: Drafting of the plan and organizing cyber exercises in view of improvement of the ICT security. | Q4 2025 | ITE Office | aborted | - | The activity has been abandoned. |  | The activity has been abandoned. | The activity has been abandoned.
1.1.5.6: Raising of the capacities of the PA and LSG bodies in drafting and application of the plan of verification of compliance with the Regulation on Information Security. | Q4 2025 | MIT | In progress | - | Ministry of Information and Telecommunications conducts activities aimed at strengthening capacities of public administration and local self-government authorities in the area of information security in view of improvement of enforcement of regulations and increase of resilience of institutions against cyber threats. To that effect, in cooperation with National CERT of Serbia under the RATEL and other relevant actors, training courses have been delivered for IT administrators and heads of administration, focused on raising awareness of risks and obligations arising from the Law on information Security. During the training courses, the participants had a chance to get acquainted with the work of the National CERT, the most common cyber threats and prevention methods as well as practices for risk management and improvement of ICT system protection. Moreover, the importance of consistent enforcement of the Law on Information Security was emphasised, including the obligation of adoption and enforcement of the Regulation on Security of ICT System. Bearing in mind that strengthening capacities of the public administration and local self-government authorities is crucial for efficient implementation of protection measures, additional activities have been planned for the fourth quarter aimed at improvement of the application of the plan for verification of the compliance with the Regulation on Information Security. These activities will encompass new education, drafting of the guidelines and tools for compliance self-assessment as well as strengthening cooperation with relevant institutions in view of improving protection of critical and important infrastructure. Ministry continues to work on raising awareness and improvement of capacities of public institutions and local self-government units so as to ensure consistent enforcement of regulations and establishment of sustainable system of information security.
.
Specific objective 1.2: Improvement of legal certainty in use of electronic government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of enactments arising from the work of inspection bodies in the software solution eInspector delivered to the Unique Electronic Inbox of the user of services of electronic government (Number) |  |  | 17,532 (2022) |  | 30000 | 0 | During 2024, there was no delivery of enactments from the eInspector to the unique electronic inboxes (25 attempts have been made, but were not realized). In 2023, old eDelivery was shut down, and in May 2024, the new eDelivery was launched. It turned out that certain changes have been implemented in the new version of eDelivery, which led to malfunctioning of the connection between eInspector and eDelivery.
Percentage of cases handled only in electronic form in comparison with all cases in the calendar year (%). |  |  | 0 (2022) |  | 25 | 26
.
Measure 1.2.1: Ensuring efficient protection of the rights of eGovernment users
Institution in charge: MINISTRY OF JUSTICE
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Further expansion of the possibility of electronic initiation and conduct of court cases for participants in the procedure by means of application eCourt (Number) |  |  | 1 (2022) |  | 16 | 0
Percentage of judges in the RS having undergone trainings of the Judicial Academy related to work in the digital environment in comparison to the total number of judges in the RS (%) |  |  | 15 (2022) |  | 28.5- 30 | 0
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.1.1: Sustainable development of the register of wills - judicial professions | Q4 2025 | MoJ |  | - | ..
1.2.1.2: Sustainable development of the register of revoked powers of attorney - judicial professions | Q4 2025 | MoJ |  | - | ..
1.2.1.3: Development and implementation of the application Super SAPS for case management | Q4 2025 | MoJ |  | - | ..
1.2.1.4: Sustainable development of the platform eAuction for electronic sale of moveable and immoveable by means of public auction in the enforcement procedure (entirely electronic process of announcing auction, bidding, closing of the sale and automatic determination of the most favourable bid). | Q4 2025 | MoJ |  | - | ..
1.2.1.5: Sustainable development of the ESB infrastructure platform for interoperability of the system, eCourt and maintenance and improvement of the service of centralized electronic bulletin board of courts | Q4 2025 | MoJ |  | - | ..
1.2.1.6: Delivery of training for employees in the judiciary related to work with electronic documents and data in electronic records as well as work with systems utilized for electronic procedures | Q4 2025 | Judicial Academy (JA) | In progress | - | Annual Training Programme of the Judicial Academy is in the process of alignment with new applications and electronic records Renovation of the new building of the Judicial Academy is completed and will soon be moved in. New building is equipped with modern classrooms allowing training for work with electronic documents and in accordance with electronic procedures Necessary computer, server and audio-visual equipment have been procured. |  | The project of renovation of the new building of the Judicial Academy has been extended by two years in relation to the original date for completion of works, which has affected the realization of training requiring use of computers and work in digital environment. Moreover, there is a significant delay in the development of the document management system in the judiciary SSAP (via EU project) which is supposed to digitalize work processes in the judiciary and allow for widespread use of digital documents as well as electronic communication with the court.
1.2.1.7: Delivery of trainings relevant for digital literacy in accordance with the annual training programme of the Judicial Academy. | Q4 2025 | Judicial Academy (JA) | In progress | - | The centre for user support within the Judicial Academy has been set, which centre, continuously, in direct contact solves problems that the users are facing and trains them to use information system correctly. - users of training courses of the Judicial Academy from the courts and public prosecutor's offices are trained and educated to work in digital environment. |  | The Judicial Academy has fully transferred to electronic training management system including electronic registration of users, electronic certificate issuing as well as possibility to attend the training through the distance learning platform. All training users are trained to work in digital environment and are successfully using the system. Currently, 6000 users from the ranks of judges, prosecutors and judicial administration are registered.
.
Measure 1.2.2: Improvement of delivery in electronic government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of bodies who deliver their writs into the Unique Electronic Inbox (Number) |  |  | 13 (2022) |  | 95- 100 | 95 | eDelivery has in total 26 users. One of them is the Registry. All bodies actively using the Registry are users of eDelivery. 200 out of 400 bodies is currently active. In addition to the Registry, the LSGUs (162 municipalities) are one of the external users of eDelivery
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.1: Organizing the training for all employees in the PA for use of the Registry in accordance with the Law on Electronic Government and the Regulation on Office Operations. | Q4 2025 | NAPA | In progress | - | On-line training Electronic Office Operations has been completed by 134 trainees in 2024. 285 civil servants have attended the consultations in view of successful application of acquired knowledge on the on-line training, 13 of such consultations have been organized.
1.2.2.2: Promotion of electronic administrative procedure including eDelivery for citizens and businesses. | Q4 2024 -> Q4 2025 | ITE Office | Completed | - | Activity - Communication and User Experience of Citizens is finalized with the finalization of the procurement contract, in December 2024. |  |  | The Activity - Communication and User Experience of Citizens encompassed the promotion of all services to citizens, available on the eGovernment Portal.
1.2.2.3: Integration of eInspector software with the eRegistry | Q4 2025 | ITE Office | In progress | 100% | Activity is in progress. |  |  | Activity is in progress.
1.2.2.4: Cloud - signing and logging in via certificate | Q4 2025 | ITE Office | Completed | 100% | During 2024, in total of 87,326 qualified electronic certificates in cloud have been activated.
1.2.2.5: Descending the contact centre to the level of inspections within LSGUs | Q4 2025 | MPALSG |  | - | ..
.
Specific objective 1.3: Increasing the availability of electronic government for the citizens and industry through improvement of user services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
EU eGovernment Benchmark - dimension Key Enablers (Index points) |  |  | 54 (2022) |  | 57- 60 | 63 | When it comes to indexes from EU benchmark, the target values have been exceeded, 63 for key enablers and 89 for user orientation https://digital-strategy.ec.europa.eu/en/library/digital-decade-2024-egovernment-benchmark
EU eGovernment Benchmark - dimension User Orientation (Index points) |  |  | 77 (2022) |  | 85 | 89.4 | When it comes to indexes from EU benchmark, the target values have been exceeded, 63 for key enablers and 89.40 for user orientation https://digital-strategy.ec.europa.eu/en/library/digital-decade-2024-egovernment-benchmark
Local eGovernment Index (LEI) (Number) |  |  | 25 (2022) |  | 34- 35 | - | Data have been collected but the report will not be published before second or third quarter.
.
Measure 1.3.1: Improvement of the eGovernment Portal and other software solutions
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of submissions through eGovernment Portal in one calendar year (Number) |  |  | 1,215,767 (2022) |  | 1890000- 1800000 | 2971767
Percentage of alignment of functionalities of eGovernment Portal with accessibility standards (%) |  |  | 75 (2022) |  | 88.2- 90 | 89
Number of realized services through eGovernment Portal in one calendar year (Number) |  |  | 210 (2022) |  | 209- 220 | 340 | 340 is a total number of services which were active on eGovernment Portal in the course of previous calendar year. Their number varies because some were active for as long as certain process is active, such as enrolment into the kindergartens, elementary schools and the like.
Percentage of users evaluating positively user experience for eGovernment services (%) |  |  | 0 (2022) |  | 28.5- 30 | 95 | Percentage of users evaluating positively user experience for eGovernment services is 95%. To question “How satisfied were your with the eGovernment Portal in relation with the last service you used for business needs?” the answers were: “Very satisfied” 72%, “somewhat satisfied” 23%, “somewhat dissatisfied” 3% and “very dissatisfied” 2%.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.1: Establishment of mechanisms for measuring user experience on eGovernment Portal | Q2 2023 | ITE Office | Completed | - | ..
1.3.1.2: Redesign of the Portal in view of ensuring evaluation-collection of user experience and recognizing the needs of end users | Q2 2024 | ITE Office | Completed | 100% | ..
1.3.1.3: Connecting other authentication systems (Tax Administration, SBRA, CROSO, portals in the judiciary and other systems of public institutions, but also systems used in private sector - for instance, banks) with the Identity Management Systems (identity federation) | Q3 2025 | ITE Office | In progress | - | In total 68 connected systems. Numerous external systems introduce unique registration as a new method of registration.
.
Measure 1.3.2: Providing support to electronic government users
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of services that have user support via contact centre (Number) |  |  | 250 (2022) |  | 285- 300 | 358 | Support is secured via contact centre for all existing services on the eGovernment portal. Moreover, contact centre provides support to users who register to other systems (eInvoice, My esGradebook, eAgrar) by means of their account on eID Portal.
Number of processed user queries in the contact centre (Number). |  |  | 432,143 (2022) |  | 522500- 550000 | 680129 | Number of processed cases in 2024. - 122.232; even though some of the services are periodic in nature, CC responds to the user queries to that effect during the entire year. Total number of processed queries is cumulative and amounts to 680,129.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.1: Improvement of all capacities of the contact centre for support to citizens and industry and introduction of new channels of communication (telephone, Viber, WhatsApp) | Q4 2024 -> Q4 2025 | ITE Office | In progress | 100% | Contract for activity concluded in November 2024. Initial phase of the contract implemented. |  | It is impossible to sign contract for the activity before the process of project restructuring is finalized. | A new deadline for completion has been set: Q4 2025
1.3.2.2: Drafting of the methodology for measuring user satisfaction with the electronic public services. | Q4 2024 | ITE Office | Completed | 100% | ..
1.3.2.3: Establishment of mechanisms for measuring quality of services on eGovernment Portal | Q4 2024 | ITE Office | Completed | 100% | ..
1.3.2.4: Secure functionality of the eGovernment Portal related to tracking the status of the case by mean of Registry service. | Q4 2025 | ITE Office | Completed | 100% | Service launched in May 2024.
.
Measure 1.3.3: Promotion of the electronic government (civil servants and citizens awareness raising on the importance of digitalization and building trust in electronic services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Total number of registered users on the Portal for Electronic Identification (eid.gov.rs) (Number) |  |  | 1,405,460 (2022) |  | 2470000- 2600000 | 2437457 | During 2024, 236,993 were registered. In total 2,437,457 eCitizens were registered.
Number of issued parameters for mobile application ConsentID (number of registered users in a high level reliability scheme) (Number) |  |  | 24,280 (2022) |  | 61750- 65000 | 1128385 | During 2024, 309,877 parameters were issued for ConsentID. Total number of issued parameters is 1,128,385 eCitizens.
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.1: Promotion of the electronic government services | Q3 2023 | ITE Office | Completed | - | ..
1.3.3.2: Drafting and implementation of the methodology for change management in the domain of eGovernment | Q4 2025 | ITE Office | Completed | 100% | ..
1.3.3.3: Promotion of eStamp | Q4 2025 | MPALSG |  | - | ..
1.3.3.4: Promotion of eSignature | Q4 2025 | MIT | In progress | - | Ministry of Information and Telecommunications is conducting activities aimed at encouraging the use of eSignature in electronic operations and administrative procedures. So far, an analysis of challenges in use and application of the eSignature has been conducted as well as the possibility for its widespread use.
1.3.3.5: Promotion of the Registry | Q4 2025 | ITE Office | Completed | 100% | Promotional activities have been conducted during 2024 after launching the service.
.
Specific objective 1.4: Opening of data in public administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of resources available on the Open Data Portal (Number) |  |  | 5,995 (2022) |  | 6840- 7200 | 7149
Number of visits to the Open Data Portal (Number) |  |  | 285,795 (2022) |  | 301500- 335000 | 315799
.
Measure 1.4.1: Ensuring implementation of legislative framework for open data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of bodies* sharing/publishing open data on the Open Data Portal (Number) |  |  | 83 (2022) |  | 109.25- 115 | 111
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.1: Drafting of the methodology and standards for opening data together with defining priority data sets | Q4 2023 | ITE Office | aborted | - | This activity was aborted. |  |  | In accordance with the Regulation ЕU 2023/138, it was not necessary to draft additional methodology for standards for opening data together with defining priority data sets. The Regulation clearly prescribes data sets of high value, together with detailed information on their formats and granulation.This regulation offers comprehensive guidelines and specifications covering necessary information on priority data, eliminating the need for additional efforts in terms of defining the standards. This approach ensures consistency with the regulatory requirements and saves resources which would otherwise be utilized for this purpose.
1.4.1.2: The preparation of the Proposal of the Regulation on Open Data Portal for purpose of alignment with the Directive ЕU 219/1024 on re-use of data and precise regulation of the obligation of opening data in accordance with the methodology, introduction of the officer for open data in all institutions. | Q1 2025 | MPALSG | In progress | - | ..
1.4.1.3: Establishment and support to the Open Data Working Group for expanding open data ecosystem, opening of public administration data, monitoring realization, providing support to the institutions in opening their data. | Q4 2025 | ITE Office | Completed | 100% | New members of the working group were selected and a meeting took place. New members were presented at the meeting, priority activities for the upcoming period were considered, including support to institutions in the process of data opening, monitoring progress and improving coordination between different actors in the open data ecosystem. |  |  | Concrete tasks in view of further development and improvement of the access to data were agreed.
1.4.1.4: Delivery of training courses for civil servants regarding the opening of data in public administration. | Q4 2025 | NAPA | In progress | - | 2 training courses were realized in the webinar format whereon 118 trainees attended from 48 different bodies. 17 trainees attended the conference regarding open data organized in cooperation with the SKIP Centre and the Republic of Korea.
1.4.1.5: Improvement of software solution of the Open Data Portal in view of improving user experience | Q4 2025 | ITE Office | In progress | - | The works on comprehensive upgrade of the portal functionality are ongoing, including: • Improvement of user experience (UX/UI): Upgrade of the interface design for purpose of more intuitive and easier navigation, at the same time eliminating uncertainties in the use of the Portal. • Eliminating errors: Technical problems that might interfere with the processing of data are systematically analysed and resolved. • Increase of data capacity: The mechanisms for checking the accuracy, update and consistency of data are improved so as to offer reliable and usable information to the users. The goal of these upgrades is to make the Portal more efficient and accessible, both for the institutions publishing data and for users analysing and using them. |  |  | Future steps include development and testing of upgrade, piloting new functionalities, full launch together with the work alongside the training of users, as well as continuous monitoring and maintenance of the system
1.4.1.6: Strengthening capacities of the employees (number and skills) in the ITE in the organizational unit in charge of open data. | Q4 2025 | ITE Office | In progress | - | In order to provide more efficient support to institutions in the process of data opening, the employees are trained through training courses, and the team is complemented with new experts. These measures contribute to development of professional capacities, improvement of coordination and long-term sustainability of the open data ecosystem. |  |  | Future steps include continuation with the employee training, as well as hiring additional experts for purpose of strengthening capacity of the team and improving the support to the institutions.
.
Measure 1.4.2: Support to use of open data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of organized hackathons, datathons, open data weeks and open data challenges in one calendar year (Number) |  |  | 10 (2022) |  | 19.8- 20 | 15
Number of bodies ** which were given support to open and/or reuse open data (Number) |  |  | 28 (2022) |  | 49.5- 50 | 15
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.2.1: Providing support to open data users for projects which are based on reuse and promotion of open data (civil society organizations, universities, media, scientific-research community, start up community etc.) | Q4 2025 | ITE Office | In progress | 100% | Currently, the support is provided to entrepreneurs who received funds from the NEB, as well as entrepreneurs from Vojvodina, Agency for Environmental Protection, NAPA and the Ministry of Labour, Employment, Veteran and Social Affairs.
1.4.2.2: Conducing activity within the Open Data Challenge. | Q4 2025 | ITE Office | Has not started | - | The activity is realized in accordance with the planned dynamics. |  | The activity is realized in accordance with the planned dynamics. | The activity is realized in accordance with the planned dynamics.
1.4.2.3: Conducing activity within the Open Data Week. | Q4 2025 | ITE Office | Has not started | - | The activity is realized in accordance with the planned dynamics. |  | The activity is realized in accordance with the planned dynamics. | The activity is realized in accordance with the planned dynamics.
1.4.2.4: Delivery of education courses in view of opening and reusing data (for public, private, civil sector, academia and media). | Q4 2025 | ITE Office | In progress | 100% | So far, training for public sector has been successfully organized, with emphasis on highly valuable data (HVD) as well as for entrepreneurs, allowing for practical understanding and application of open data in business operations as well as improvement of public services. |  |  | The continuation of education for existing target groups and expansion of the programme to media, academia and civil society. Training programme is continually developing so as to respond to the needs of different sectors and to instigate active use of open data
1.4.2.5: Implementation of promotional activities (blog, “Wednesday - day for open data”, campaigns on social networks etc.); | Q4 2025 | ITE Office | In progress | 100% | Promotional activities are successfully implemented through different channels including social media, The ODH (Open Data Hub) and the official website of the Office for IT and eGovernment. regularly publish news, examples of good practice and successful application of data, which contributes to increasing the visibility of open data and engagement of wider public. Organizing campaigns such as “Wednesday - day for open data”, thematic blogs and media content, instigating dialogue and interest for open data. |  | There are no significant deviations from the planned activities. | Regular promotion of open data will continue through social media, ODH portal and thematic activities, with expansion of cooperation and adjustment of strategy in relation to feedback.
1.4.2.6: Opening of the Open Data Hub In “Ložionica” (after construction) | Q4 2025 | ITE Office | Has not started | - | The activity is realized in accordance with the planned dynamics |  | The activity is realized in accordance with the planned dynamics | The activity is realized in accordance with the planned dynamics
1.4.2.7: Support to the public administration bodies in the process of opening data through mentorship, technical assistance and targeted training based on the needs of individual bodies. | Q4 2025 | ITE Office | Has not started | - | Activity is being prepared. |  | The activity is realized in accordance with the planned dynamics | The activity is realized in accordance with the planned dynamics
.
Measure 1.4.3: Introduction of the concept of “smart work”
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2024 | Achieved value in 2024. | Note
Number of LSGUs for which the analysis of readiness for implementation of the concept “smart city” has been carried out (Number) |  |  | 0 (2022) |  | 1 | 3
.
Activity | Deadline -> New deadline | Institution in charge: | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.3.1: Drafting of the Analysis on possible ways of establishing smart cities and their networking (cloud infrastructure) together with the implementation proposal | Q2 2023 | MPALSG |  | - | ..
1.4.3.2: Implementation of at least two pilot projects for preparation of the smart city concept (in the sense of cultural, regional and other specificities) | Q2 2023 | MPALSG |  | - | ..
1.4.3.3: Regulate in the law the concept of “smart city” and envisage the legal grounds for adopting the methodology which would define criteria for smart city development | Q4 2025 | MPALSG |  | - | ..
1.4.3.4: Developing of management board and/or solutions for smart decision-making based on open data on the level of the LSGU. | Q4 2025 | ITE Office |  | - | ..