## All activities export 1
The annual report on the implementation of the Action Plan for 2025, for: |  |  |  |  | Action Plan for the Implementation of the Public Finance Management Reform Programme 2021–2025
Coordinating and reporting institution: |  |  |  |  | MINISTRY OF FINANCE
Public policy document the Action Plan pertains to: |  |  |  |  | Public Finance Management Reform Programme 2021–2025
General Objective 1: ACHIEVING A SUSTAINABLE BUDGET WITH STABLE PUBLIC DEBT COMPARED TO GDP THROUGH BETTER FINANCIAL MANAGEMENT AND CONTROL, AUDIT PROCESS AND LINKING BUDGET PLANNING WITH GOVERNMENT POLICIES
Document proposed by: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Real GDP growth (%) |  |  |  |  | 4 | 2
Share of the general government debt in GDP (%) |  |  |  |  | 50.7 | 44.4
.
Specific Objective 1.1: IMPROVED CAPACITIES FOR BUDGET PLANNING AND PUBLIC FINANCE MANAGEMENT
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Information on performance in terms of public service delivery (PEFA: 4-А, 3.5-B+, 3-B, 2.5-C+, 2-C, 1.5-D+, 1-D, 1-D*) |  |  | 2.5 (2010) |  | 3 | 3
.
Measure 1.1.1: Programme Budget improvement
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Analysis of programme budget implementation elaborated (Number) |  |  | 0.00 (2020) |  | - | -
Analysis of the uniform structure of programme budgets of local self-government units elaborated (Number) |  |  | 0.00 (2020) |  | - | -
Uniform programme structure for the organisations of mandatory social insurance and their beneficiaries established (Number) |  |  | 0.00 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.1.1: Analysis of the programme budget implementation and performance indicator use | Q4 2022 | MoF | Completed | - | The activity has been implemented.
1.1.1.2: Analysis of the uniform structure of programme budgets of local self-government units | Q4 2022 | MoF | Completed | - | The activity has been implemented.
1.1.1.3: Establishing a programme structure for the organisations of mandatory social insurance and their beneficiaries | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.1.1.4: Workshops and trainings for all beneficiaries at all levels of government | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.1.1.5: Study tour related to performance reporting improvement | Q4 2022 | MoF | Not commenced | - | The activity has not been implemented.
.
Measure 1.1.2: Capacity building related to the preparation and obligations of EU member states during the budget preparation process
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Elaborated analysis of the budget preparation process in EU member states (Number) |  |  | 0.00 (2020) |  | - | -
Number of study tours |  |  | 0.00 (2020) |  | 1.00 | 0.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.2.1: Analysis of the budget preparation process of the EU member states and obligations of the Republic of Serbia in the preparation of a budget | Q4 2023 | MoF | Completed | - | The activity has been implemented.
1.1.2.2: Training for the employees at the Ministry of Finance and in direct budget beneficiaries | Q4 2025 | MoF | Not commenced | - | The activity has not been implemented.
1.1.2.3: Study visit | Q4 2025 | MoF | Not commenced | - | The activity has not been implemented.
.
Measure 1.1.3: Improvement of medium-term planning
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of adopted medium-term plans of central-level institutions required to elaborate medium-term plans (Number) |  |  | 2.00 (2020) |  | 29.00 | 29.00
Percentage (%) of the published reports of institutions required to elaborate medium term plans on the implementation of their medium term plans, elaborated using the Unified information system for planning, implementation monitoring and coordination of public policy and reporting (UIS) (%) |  |  | 10.00 (2021) |  | 95.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.3.1: Mentor support in the elaboration of medium-term plans for institutions required to elaborate medium-term plans on the national level | Q4 2023 -> Q4 2025 | PPS | Completed | - | The activity has been implemented. In the reporting period, mentor support was provided to the central-level institutions obliged to elaborate medium-term plans, which contributed to a continued increase in the number of adopted MTPs.
1.1.3.2: Elaboration of an analysis of the compliance of medium-term plans with the public policy documents in the appropriate planning area | Q4 2025 | PPS | Completed | - | The activity has been implemented. The analysis of the compliance of medium-term plans with the public policy documents has been published: https://rsjp.gov.rs/wp-content/uploads/Анализа-усклађености-средњорочних-планова-са-документима јавних-политика.pdf
.
Measure 1.1.4: Improvement of the environment for efficient capital project management
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Capital projects included in the budget, subject to and assessed in line with the methodology regulating capital projects (%) |  |  | 0.00 (2022) |  | 60.00 | 82.00
Trainings held for civil servants from line ministries and other institutions performing project management tasks (Number) |  |  | 0.00 (2022) |  | 3.00 | 4.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.4.1: Amendments and additions to the legal framework in line with the identified practical implementation weaknesses | Q4 2022 | MoF | Completed | - | The activity has been implemented.
1.1.4.2: Elaboration of the training programme for the relevant participants in the capital project management process | Q4 2023 | MoF | Completed | - | The activity has been implemented. All necessary activities, which form the preconditions for setting up and implementing trainings at the NAPA, have been implemented.
1.1.4.3: Elaboration of a public information report on the status of capital projects monitored in line with the methodology | Q4 2025 | MoF | Not commenced | - | The activity has not been implemented.
1.1.4.4: Elaboration of the a manual on CPM (design, print preparation, proofreading, consultants’ support for the content) | Q2 2023 -> Q4 2024 -> Q4 2025 | MoF | In progress | - | The activity has not been implemented in the previous period. In line with the steps envisaged in the Reform Agenda, significant amendments to the legal framework are expected in the upcoming period, which will, inter alia, strive to improve capital project management transparency, primarily through regularly informing the public.
1.1.4.5: Elaboration of a capital project management information system | Q4 2021 | MoF | Completed | - | The activity has been implemented.
1.1.4.6: Upgrade to the capital project management information system | Q2 2024 | MoF | Completed | - | The activity has been implemented.
1.1.4.7: Improvement of staff skills in the field of project management, sustainable project management, including the elaboration and review of cost-benefit analysis | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.1.4.8: Completing the legal framework by including the aspects of capital project impacts on environment and climate change | Q1 2024 | MoF | Completed | - | The activity has been implemented.
.
Measure 1.1.5: Capacity building of the Sector for Fiscal Risk Monitoring
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Positions envisaged in the job classification for the Sector for fiscal risk monitoring filled (%) |  |  | 33.00 (2020) |  | 90.00 | 100.00
Employees in the Sector for Fiscal Risk Monitoring trained () |  |  | 0.00 (2020) |  | - | -
The Fiscal Strategy contains a section pertaining to the quantified key fiscal risks (Yes/No) |  |  | 0.00 (2022) |  | - | -
Employees in the Sector for Fiscal Risk Monitoring trained (advanced trainings) (%) |  |  | 10.00 (2023) |  | 80.00 | 100.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.5.1: Training for the employees in the Ministry of Finance | Q4 2023 | MoF | Completed | - | The activity has been implemented.
1.1.5.2: Establishing a methodology for the Fiscal Risk Monitoring Group for fiscal risks related to public sector operation | Q4 2021 | MoF | Completed | - | The activity has been implemented.
1.1.5.3: Establishing a methodology for the Fiscal Risk Monitoring Group for other fiscal risks – risks from natural disasters and court proceedings | Q4 2021 | MoF | Completed | - | The activity has been implemented.
1.1.5.4: Improvement and standardisation of fiscal risk reports | Q4 2024 | MoF | Not commenced | - | The activity has not been implemented. Due to the changes in the job classification, the report standardisation was not adopted.
1.1.5.5: Improvement of the employees’ skills in financial analysis, cost-benefit analysis and analysis in the field of monitoring the risks from climate-induced natural disasters | Q4 2024 | MoF | Completed | - | The activity has been implemented.
1.1.5.6: Familiarisation with best international practice pertaining to fiscal risks monitoring and reporting (through study tours, workshops etc.) | Q4 2024 | MoF | Completed | - | The activity has been implemented.
.
Specific Objective 1.2: EFFICIENT MOBILISATION AND MANAGEMENT OF BUDGET FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Real revenues and expenditures of the general government budget at the annual level are within 5% from those envisaged in the fiscal strategy. (%) |  |  | 5 (2019) |  | 5 | 7.1
Annual expenditures for public debt servicing (payment of interests – net amount) as % of GDP |  |  | 1.9 (2020) |  | 2.2 | 1.9
Average duration of an open procedure (Number) |  |  | 52 (2020) |  | 44 | 42
.
Measure 1.2.1: Efficient collection of budget revenue in the purview of Tax Administration
Institution in charge: MINISTRY OF FINANCE - TAX ADMINISTRATION
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The percentage of achieved collection relative to the approved budget assessment (income tax, profit tax, gross domestic VAT, gross excise taxes) (%) |  |  | 110.90 (2020) |  | 100.00 | 104.40
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.1.1: Re-engineering of basic function business processes | Q2 2022 -> Q3 2023 | MoF-TA | Completed | - | The activity has been implemented.
1.2.1.2: Introduction of a new fiscalisation system | Q3 2022 | MoF-TA | Completed | - | The activity has been implemented.
1.2.1.3: Improvement of the ICT infrastructure – COTS | Q4 2024 -> Q4 2025 | MoF-TA | In progress | - | Implementation of the activity is in progress and will be carried over into the next PFMRP 2026-2030.
1.2.1.4: Harmonisation of the legislative framework and preparation of technical specifications for the implementation of the information exchange system in line with EU standards (exchange systems related to indirect taxation and exchange systems related to direct taxation), as well as compliance with the recommendations of the Global Forum for the implementation of an international information exchange standard for information exchange on demand and for automatic exchange | Q4 2025 | MoF-TA | In progress | - | Implementation of the activity is in progress and will be carried over into the next PFMRP 2026-2030
1.2.1.5: Improvement of the human resources management function through the development of a human resources strategy and improvement of the existing human resources management information system | Q4 2024 | MoF-TA | Completed | - | Activity was implemented in 2025.
1.2.1.6: Introduction of the electronic delivery note system – analysis of the legal and administrative framework and preparation of the documentation for procurement | Q4 2023 | MoF | Completed | - | The activity has been implemented.
1.2.1.7: Introduction of the electronic delivery note system – introduction of an IT system | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.2.1.8: Elaboration of a communication strategy with regards to the PO PDV standard form (VAT calculation overview form) | Q4 2024 | MoF |  | - | ..
1.2.1.9: Elaboration of a communication strategy for the introduction of the electronic delivery notes system | Q4 2024 | MoF | Completed | - | The activity has been implemented.
.
Measure 1.2.2: Modernisation of Tobacco Administration operation
Institution in charge: MINISTRY OF FINANCE – TOBACCO ADMINISTRATION
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Unique Register System established (Number) |  |  | 0.00 (2020) |  | 0.00 | -
All employees at the Tobacco Administration trained to work in the Unique Register System (%) |  |  | 0.00 (2020) |  | - | -
Percentage of businesses operating on the tobacco and tobacco product market using electronic services of the Tobacco Administration (%) |  |  | 0.00 (2020) |  | 57-60.00 | 65.00
New functions established within the integrated information system of the Tobacco Administration (Number) |  |  | 0.00 (2024) |  | 1.00 | 1.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.2.1: Establishment of a unique register system that will unify all registers and record sheets to improve Tobacco Administration’s service delivery efficiency | Q4 2021 | MoF-Tobacco Administration | Completed | - | The activity has been implemented.
1.2.2.2: Human resources capacity building in the Tobacco Administration and other partner institutions | Q4 2021 | MoF-Tobacco Administration | Completed | - | The activity has been implemented.
1.2.2.3: Raising digital awareness among businesses operating on the tobacco and tobacco products market | Q4 2021 | MoF-Tobacco Administration | Completed | - | The activity has been implemented.
1.2.2.4: Upgrade of the Integrated Information System of the Tobacco Administration | Q4 2025 | MoF | Completed | - | The activity has been implemented.
.
Measure 1.2.3: Administrative capacity building of the Customs Administration
Institution in charge: MINISTRY OF FINANCE – CUSTOMS ADMINISTRATION
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Percentage of achieved collection of custom duties and VAT from import compared to the approved budget forecast (%) |  |  | 102.29 (2020) |  | 95-100.00 | 95.69
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.3.1: Improvement of financial security procedure for customs debt | Q4 2024 | MoF-CA | In progress | - | ..
1.2.3.2: Capacity building for full implementation of TOR EU regulations and reporting on revenues to the EU | Q4 2025 | MoF-CA | Completed | - | The activity has been implemented.
1.2.3.3: Capacity building for effective post-clearance control activities, including the determination of customs value, preferential origin, and classification of goods | Q4 2025 | MoF-CA | In progress | - | The next steps require, as a precondition, the introduction of complete automation of customs procedures (AIS-EIS), when the redistribution of employees has been envisaged, i.e., transferring a number of employees from customs offices to the Department for Post-clearance Control.
1.2.3.4: Modernisation of the customs laboratory | Q4 2025 | MoF-CA | In progress | - | In terms of space, the Ministry of Defence has granted its approval for the use of laboratory space located in the Military-Technical Institute, which would satisfy the spatial needs for the equipment that is to be procured through an IPA Project (IPA 2026). This issue is expected to be formally legally resolved soon. When it comes to the equipment, preparation of technical specifications is underway. Elaboration of ToR for technical assistance is in progress, for the introduction of new analytical methods.
1.2.3.5: Preparation activities aimed at improving the management and public sale of seized customs goods, as well as at the development of customs infrastructure related to special-purpose warehouses. | Q4 2025 | MoF-CA | Not commenced | - | The activity has not been implemented.
1.2.3.6: Implementation of automated import and export systems (AIS-AES) and management system (CDMS) | Q4 2025 | MoF-CA | In progress | - | Implementation of the project “Implementation of automated import and export systems (AIS-AES) and the customs decision management system”
1.2.3.7: Introduction of an integrated tariff management system (ITMS) | Q4 2025 | MoF-CA | In progress | - | Work on the elaboration of the ITMS has begun, the Inception Report has been elaborated and adopted, functional specifications have been elaborated for all systems (TARIC RS, TARIC CALCULATOR RS, QUOTA, SURVEILANCE, ECICS, CAVS, Communication hub), as well as the Implementation Plan and Integration Plan, and work has begun on the elaboration of the Minimum Variable Prototype (MVP) and Data Loader.
1.2.3.8: Procurement of the customs data warehouse | Q4 2024 -> Q4 2025 | MoF-CA | In progress | - | ..
.
Measure 1.2.4: Efficient public debt management
Institution in charge: MINISTRY OF FINANCE – PUBLIC DEBT ADMINISTRATION
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of debt in domestic currency in the total public debt – central government (%) |  |  | 30.50 (2020) |  | 35.00 | 22.50
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.4.1: Reinforcing the medium-term public debt management strategy by elaborating a risk management model | Q4 2022 -> Q4 2024 | MoF-PDA | In progress | - | Implementation was delayed due to a change in priorities.
1.2.4.2: Implementation of a pilot project for the introduction of a primary dealer system and further development of the domestic bond market | Q4 2024 -> Q4 2025 | MoF-PDA | Not commenced | - | Implementation was delayed due to a change in priorities.
1.2.4.3: Upgrade to the existing information system (PDMS) with the use of a business intelligence tool, to improve reporting | Q4 2025 | MoF-PDA | Not commenced | - | Implementation was delayed due to a change in priorities.
1.2.4.4: Upgrade to the existing information system (PDMS) with a developed risk management module | Q4 2024 -> Q4 2025 | MoF-PDA | Not commenced | - | Implementation was delayed due to a change in priorities.
.
Measure 1.2.5: Improvement of the electronic public procurement system
Institution in charge: OFFICE FOR PUBLIC PROCUREMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of offers per public procurement procedure (Number) |  |  | 2.50 (2020) |  | 3.10 | 2.50
Contract database on the Portal (0 - No, 1 - Yes) |  |  | 0.00 (2022) |  | 1.00 | 1.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.5.1: Upgrade of the Public Procurement Portal with new features | Q4 2025 | OPP | Completed | - | The activity has been implemented.
1.2.5.2: Elaboration of a mobile app for the Public Procurement Portal | Q4 2021 | OPP | Completed | - | The activity has been implemented.
1.2.5.3: Capacity building of the Office for Public Procurement | Q1 2021 | OPP | Completed | - | The activity has been implemented.
1.2.5.4: Organisation of trainings for contracting authorities and bidders | Q4 2025 | OPP | Completed | - | The activity has been implemented.
1.2.5.5: Elaboration and adoption of public policy documents for public procurement development for the period 2024-2028 | Q4 2023 | OPP | Completed | - | Activity was implemented in 2024.
.
Specific Objective 1.3: ENHANCEMENT OF BUDGETARY DISCIPLINE AND MORE TRANSPARENT USE OF PUBLIC FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The average number of breaches of law and irregularities, per control, related to the total number of controls performed (the general level indicator measures the efficiency of budgetary inspection, and it needs to be kept since the number of breaches of law depends solely on the budgetary inspection, while the enforcement of measures depends on other regulatory bodies (courts). (Number) |  |  | 2 (2020) |  | 1-1 | 1.58
Percentage of accepted and implemented recommendations which an audit body issues to subjects of indirect EU funds management (%) |  |  | 0 (2020) |  | 70 | 50
.
Measure 1.3.1: Establishment of a base for institutional and administrative capacity building for the Governmental Audit Office of EU Funds that will allow for effective audit of the EU control system
Institution in charge: GOVERNMENTAL AUDIT OFFICE OF EU FUNDS
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of auditor findings of the EC, relative to the number of the implemented audit recommendations (Number) |  |  | 16.00 (2020) |  | 3.06-3.00 | 3.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.1.2: Development of staff retention policies to ensure adequate and stable administrative capacities of the Office | Q4 2023 -> Q4 2025 | HRMS | Completed | - | The HRMS monitors and reports on the inflow and outflow of staff in public administration bodies, including the Office. The civil servants fluctuation rate in the Office is 3.5 % in 2025, and can be considered low and stable (it is below average for the public administration as a whole).
1.3.1.3: Capacity building for the Governmental Audit Office of EU Funds to ensure an efficient system of EU funds control and audit, in line with the EU legislative framework. | Q4 2025 | Office for Coordination of the Audit System (OCAS) | Completed | - | The activity has been implemented.
.
Measure 1.3.2: Strengthening the system for a more efficient and more effective EU funds management
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Adopted documents directed at staff retention policy (Number) |  |  | 0.00 (2020) |  | 1.00 | -
Percentage of employees trained in management, control of the use of funds, risk management and irregularities (%) |  |  | 9.50 (2020) |  | 40-50.00 | 90.00
Number of on-site checks at the premisses of public funds beneficiaries (Number) |  |  | 9.00 (2020) |  | 11.76-12.00 | 14.00
Percentage of identified irregularities at first/first instance control, relative to the total number of irregularities (%) |  |  | 75.00 (2020) |  | 77-70.00 | 93.33
Percentage of business processes supported by the IT system (%) |  |  | 0.00 (2020) |  | 54-60.00 | 100.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.2.1: Development of new operational procedures, methodological guidelines and additional auxiliary tools for the institutions charged with management and implementation of EU funds with the aim of increasing the efficiency of the performed controls and reduction of the administrative load. | Q4 2023 -> Q4 2024 | MoF | Completed | - | The activity has been implemented.
1.3.2.2: Establishment and implementation of continual professional trainings and on-site trainings related to the system management and supervision, financial management, funds use control, risk and irregularities management | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.3.2.3: Ensuring an adequate number of employees and capacity building with respect to expanding the scope and quality of on-site checks, and performance of supervision functions on the premises of public funds beneficiaries. | Q4 2025 | MoF | In progress | - | ..
1.3.2.4: Improvement of the information system intended for the support of business processes in system management, contract implementation, and use of funds | Q4 2025 | MoF | Completed | - | The activity has been implemented. Data migration was completed in 2024.
.
Measure 1.3.3: Increased efficiency and effectiveness of inspection supervision
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Percentage of planned controls, compared to the number of the received complaints, reports and requests for inspection (%) |  |  | 12.00 (2020) |  | 24-30.00 | 57.00
Total number of inspections performed (Number) |  |  | 29.00 (2020) |  | 58.00 | 188.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.3.1: Adoption of methodological instructions on the method of operation of the budgetary inspection by area of control | Q4 2021 | MoF | Completed | - | The activity has been implemented.
1.3.3.2: Professional development of budgetary inspectors and other employees in the budgetary inspection through continual training | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.3.3.3: Providing an adequate number of inspectors − 50 in 2025 | Q4 2025 | MoF | In progress | - | At the end of 2025, there was a total of 47 budgetary inspectors employed.
1.3.3.4: Amendments and additions to the Law on Budget System and bylaws of the budgetary inspection / adoption of the Law on budgetary inspection | Q1 2022 | MoF | Completed | - | The activity has been implemented.
.
Specific Objective 1.4: IMPROVEMENT OF THE APPLICATION OF THE PUBLIC INTERNAL FINANCIAL CONTROL SYSTEM
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
PIFC-related progress identified in the EC progress report on the Republic of Serbia for the particular year (EC's assessment on the General Preparedness Assessment scale: 1 – Early stage of preparedness, 2 – Some level of preparedness, 3 – Moderate preparedness, 4 – Good level of preparedness) |  |  | 0 (2020) |  | - | -
.
Measure 1.4.1: Improvement of the FMC system in public sector institutions
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Average assessment of the priority group of public funds beneficiaries (PFB) submitting reports on FMC status (%) |  |  | 91.49 (2020) |  | 95.00 | -
Percentage of priority PFBs that have developed a risk register (%) |  |  | 63.95 (2020) |  | 80.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.1.1: Cooperation with the Budget Sector regarding the improvement of organisation performance management (link to the PAR Strategy, measure 4.1.2) | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.1.2: Building the capacities of CHU employees for ISO standards and COSO. Detailed mapping and comparison of the relevant part of ISO standards and COSO models, including the implementation with conclusions in the form of a gap analysis and training for the CHU employees. | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.1.3: Improvement of risk management in the priority group of PFBs at the central level through direct support of the project | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.1.4: Elaboration of practical methodological tools/knowledge products in the area of financial management and control adapted to the specificities of individual significant groups of indirect PFBs on the central level (select sectors) | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.1.5: Support to the establishment and improvement of the FMC system at the local level | Q4 2025 | ALL LSGUs | Completed | - | The activity has been implemented.
1.4.1.6: Elaboration of a coherence analysis for the PIFC regulations with the other horizontal regulations, with a comparative analysis of the EU funds management system and national funds management system, from the viewpoint of internal controls | Q4 2022 -> Q4 2023 | MoF | Completed | - | The activity has been implemented.
.
Measure 1.4.2: Improved internal audit function in the public sector in line with international standards and principles
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Percentage of priority PFBs obliged to have an IA unit with a minimum of three employees tasked with internal audit (Number) |  |  | 0.00 (2022) |  | - | -
The number of external operation quality assessments for internal audit units within the public funds beneficiary institutions with a gradual increase in the number of peer reviews within the total number of reviews. (Number) |  |  | 8.00 (2021) |  | 12.00 | 12.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.2.1: Analysis of the implementation of the existing methodological framework and its improvement (e.g., for performance audit, information security audit, advisory services etc.) | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.2.2: Preparation and implementation of the Continual Professional Development Programme for Internal Auditors (link to 4.4.4) | Q4 2022 | MoF | Completed | - | The activity has been implemented.
1.4.2.3: Human resources capacity building of the internal audit (promotion of the profession, tools for recruitment and selection of internal auditors, proposal for the improvement of professional standing of internal auditors etc.) | Q4 2022 | MoF | Completed | - | The activity has been implemented.
1.4.2.4: Support to the establishment and improvement of the IA at the local level | Q4 2025 | ALL LSGUs | Completed | - | The activity has been implemented.
1.4.2.5: Introducing external quality assessment using the peer review method (piloting, methodology, rulebook, evaluator training and certification, adoption and implementation of the External Quality Assessment Programme) | Q2 2025 | MoF | Completed | - | The activity has been implemented.
1.4.2.6: Improvement of the existing legal framework to optimise the organisation of internal audit and IA reporting | Q4 2023 -> Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.2.7: Model framework for the improvement of the audit committees/audit commissions (study tour and model) | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.2.8: Support to networking in the form of annual meetings of Heads of IA units in ministries | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.2.9: Improvement of the employment and labour status of IA | Q4 2025 | MoF | Completed | - | The activity has been implemented.
.
Measure 1.4.3: Enhanced monitoring of internal control in the public sector (ICPS)
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Functional IT system for internal control (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 1.00 | 0.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.3.1: Improving the functionality of the application, modules for the improvement of CHU application, trainings, regulatory obligation | Q4 2025 | MoF | In progress | - | Implementation of the activity is in progress and will continue into the upcoming period.
.
Measure 1.4.4: Modernisation of the PIFC training system
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of e-learning trainings in the field of PIFC (Number) |  |  | 3.00 (2022) |  | 6.00 | 6.00
Percentage of authorised internal auditors who have collected the prescribed number of points through continual professional development (%) |  |  | 58.10 (2020) |  | 85.00 | -
Percentage of certified internal auditors in priority PFBs (%) |  |  | 80.00 (2020) |  | 85.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.4.1: Protocol on the cooperation between NAPA and CHU regarding the implementation of PIFC training | Q4 2023 | MoF | Completed | - | The activity has been implemented.
1.4.4.2: Improvement of the internal auditor certification process | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.4.3: Modernisation of PIFC trainings and training modules (expansion of the e-learning modules) | Q4 2025 | MoF | Completed | - | The activity has been implemented.
1.4.4.4: Preparation and implementation of internal auditor trainings through the Continual Professional Development Programme for Internal Auditors in the Public Sector Link to measure 4.2.2 | Q4 2025 | MoF | Completed | - | The activity has been implemented.
.
Specific Objective 1.5: IMPROVED PUBLIC SECTOR ACCOUNTING USING THE INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS (IPSAS)
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The Financial Report prepared and presented to the Ministry of Finance of the Republic of Serbia in accordance with Cash Basis IPSAS (Number) |  |  | 0 (2020) |  | 1 | 0
.
Measure 1.5.1: Baseline analysis of public sector accounting and development and implementation of the Public Sector Accounting Improvement Plan
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Public Sector Accounting Improvement Plan adopted (Number) |  |  | 0.00 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.5.1.1: Drafting of the Public Sector Accounting Improvement Plan, in phases | Q4 2021 | MoF-Treasury Administration | Completed | - | The activity has been implemented.
1.5.1.2: Preparatory activities for the establishment of a Commission for the implementation of international public sector accounting standards | Q4 2021 | MoF-Treasury Administration | Completed | - | The activity has been implemented.
1.5.1.3: Activities aimed at concluding a Contract for the translation and application of the IPSAS with the Serbian Association of Accountants and Auditors (member of IFAC) | Q4 2021 | MoF-Treasury Administration | Completed | - | The activity has been implemented.
1.5.1.4: Implementation of the Contract from the activity 5.1.3 with a view to enable the implementation of the Regulation on the application of international public sector accounting standards | Q4 2022 -> Q4 2023 | MoF-Treasury Administration | Completed | - | The activity has been implemented.
.
Measure 1.5.2: Improvement of professional competency of accountants in the public sector through adequate trainings
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of accountants in the public sector who have attended the training “Improvement of public sector accounting” (%) |  |  | 69.00 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.5.2.1: Implementation of trainings to improve the professional competency of accountants in the public sector | Q4 2022 | MoF-Treasury Administration | Completed | - | The activity has been implemented.
1.5.2.2: Preparatory activities for the introduction of professional certification for public sector accountants | Q4 2024 | MoF-TA | In progress | - | In 2025, the Rulebook on the Programme for professional training in maintaining accounting records, and the preparation and presentation of financial statements in accordance with the cash basis International Public Sector Accounting Standard was adopted. Enhancing professional competencies of public sector accountants certainly remains one of the key priorities for the improvement of the entire accounting system.
1.5.2.3: Certification of 200 accountants in the public sector | Q4 2025 | MoF-Treasury Administration | Not commenced | - | ..
.
Measure 1.5.3: Improvement of accounting data coverage through the implementation of international public sector accounting standards
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Draft Financial Statement prepared in line with the cash basis IPSAS submitted to the Government (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.5.3.1: Amendments to the relevant national regulations for their mutual harmonisation and harmonisation with the requirements for cash basis IPSAS and ESA 2010 | Q2 2022 -> Q3 2024 | MoF-Treasury Administration | In progress | - | ..
1.5.3.2: Adoption of an Accounting policy for financial reporting in line with the cash basis IPSAS | Q2 2022 -> Q4 2023 | MoF-Treasury Administration | In progress | - | ..
1.5.3.3: Preparation of the Financial Statement based on cash basis IPSAS | Q2 2024 -> Q2 2025 | MoF-Treasury Administration | In progress | - | With the start of the implementation of the Rulebook on the method of preparation, assembly and submission of financial reports for budget beneficiaries, beneficiaries of the funds of the mandatory social insurance organisations and budget funds, as well as the Rulebook on accountancy policies for financial reporting in line with cash basis IPSAS in 2025, the conditions for the implementation of this activity in 2026 are now in place.
.
Specific Objective 1.6: STRENGTHENING EXTERNAL PUBLIC FINANCE OVERSIGHT
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of reviewed audit reports (Number) |  |  | 194 (2020) |  | 245 | 5
.
Measure 1.6.1: Improving the scope, quality and impact of external oversight (in line with the State Audit Institution (SAI) Strategic Plan)
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of audit reports (Number) |  |  | 254.00 (2020) |  | 300.00 | 360.00
Number of employees (Number) |  |  | 331.00 (2020) |  | 416.00 | 330.00
Number of the following areas encompassed in performance audits: social protection, general public services, defence, public order and security, economic tasks, environment protection, housing and community affairs, healthcare, sports, culture and religion, education. (Number) |  |  | 7.00 (2020) |  | 9.00 | 9.00
Number of reviews related to quality control and quality assurance (Number) |  |  | 20.00 (2020) |  | 40.00 | 37.00
The share of performance audits (of regularity and purposefulness) in the SAI’s Annual Audit Programme (%) |  |  | 40.00 (2020) |  | 55.00 | 81.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.6.1.1: Further strengthening of external audit through continual improvement of audit procedures | Q4 2025 | SAI | Completed | - | The activity has been implemented.
1.6.1.2: Presenting the report on the published audits to the competent Committee and Subcommittee for analysis of SAI findings and recommendations and for the improvement of accountability and transparency in the use of public funds | Q4 2025 | SAI | Completed | - | The activity has been implemented.
.
Measure 1.6.2: Ensuring efficient parliamentary oversight of public finances
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Discussion of the SAI’s annual report and adoption of the conclusion proposal (0 - No, 1 - Yes) |  |  | 1.00 (2020) |  | 1.00 | 1.00
Holding a session/meeting of the Committee for the consideration of recommendations for legal amendments in the presence of SAI and the Ministry of Finance (Number) |  |  | 1.00 (2020) |  | 1.00 | 1.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.6.2.1: Strengthening the control function of the National Parliament by organising session/meetings of the Committee and Subcommittee for the consideration of reports on audits conducted by the SAI | Q4 2025 | National Parliament (NP) | Completed | - | The activity has been implemented.
1.6.2.2: Engaging experts as needed to better analyse the activities implemented by the audited organisations in line with the conclusions, findings and recommendations contained in the SAI’s audit reports | Q4 2025 | NP | Not commenced | - | There was no need to engage experts.
1.6.2.3: Organising a public hearing for the Draft Law on Budget and Draft Law on the Final Budget Account | Q4 2025 | NP | Completed | - | The activity has been implemented.