## All activities export 1
The annual report on the implementation of the Action Plan for 2025, for: |  |  |  |  | Action Plan for the implementation of the Regulatory Reform and Public Policy Management Improvement Programme for 2025, with the review of the previously implemented activities
Coordinating and reporting institution: |  |  |  |  | Public Policy Secretariat of the Republic of Serbia
Public policy document the Action Plan pertains to: |  |  |  |  | Regulatory Reform and Public Policy Management Improvement Programme (RRPPMIP) with the Action Plan for the period 2021–2025
General Objective 1: Improved quality of public policy documents and legislation
Document proposed by: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Regulatory quality indicator – World Bank ranking (perc. rank (0 to 100)) |  |  | 60.1 (2019) |  | 65 | 56.1 | The value of the indicator entered is for 2024. At the time of writing of this report, there were still no published values for 2025; these values are expected to become available towards the end of 2026.
The indicator of policy harmonisation and planning quality (Scale (1-5)) |  |  | 0 (2021) |  | 5 | 3 | It was not possible to fully calculate the achieved value for the indicator, since at the moment the report was being written, the Annual Government Work Programme (AGWP) for 2025 had not yet been adopted.
.
Specific Objective 1.1: Regulatory reform with a view of improving business environment and reducing the unnecessary burden for citizens and businesses
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of adopted laws containing complete impact assessments, relative to the total number of adopted laws requiring impact assessment, in the calendar year (%) |  |  | 30.4 (2020) |  | 52 | 42.37 | In 2025, 25 laws contained complete impact assessments, out of 59 laws that required an impact assessment. The National Parliament was in session throughout this year, which had a positive impact on the quality of legislation preparation.
The share of adopted laws containing complete impact assessments, relative to the total number of adopted laws requiring impact assessment, in the calendar year (%) |  |  | 58.3 (2020) |  | 64 | 58.54 | In 2025, 48 regulations contained complete impact assessments, out of 82 regulations that required an impact assessment. Short deadlines for the adoption of regulations had a negative impact on the quality of their preparation and adherence to the adoption procedure.
.
Measure 1.1.1: Establishment of a system for the monitoring of the change in the number of legislative acts in force on an annual level, per field, and monitoring of the adoption of bylaws in line with the prescribed deadlines for their adoption
Institution in charge: GENERAL SECRETARIAT OF THE GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Share of bylaws adopted within the time limits prescribed in the newly adopted laws during the calendar year in the total number of bylaws that needed to be adopted during that calendar year in line with the Annual Government Work Plan (0 - No, 1 - Yes) |  |  | 56.00 (2023) |  | 62.00 | 0.00 | Since there had been no activities in the aforementioned period related to capacity building of the human resources of the General Secretariat of the Government for the establishment of a mechanism for the regular annual determination of the number and reporting on bylaws that had not been adopted within the prescribed time limits through the Periodic Report on the Work of the Government (PRWG)/Report on the Work of the Government, which was the precondition for the implementation of this measure, the General Secretariat of the Government does not have the requested data for 2025.
Established mechanism for regular annual reporting on the adoption of bylaws within the prescribed time limits through the PRWG/Report on the Work of the Government (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | 0.00 | Since there had been no activities in the aforementioned period related to capacity building of the human resources of the General Secretariat of the Government for the establishment of a mechanism for the regular annual determination of the number and reporting on bylaws that had not been adopted within the prescribed time limits through the PRWG/Report on the Work of the Government, which was the precondition for the implementation of this measure, the General Secretariat of the Government does not have the requested data for 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.1.1: Development of a three-year report on the regulatory framework changes by areas and types of legislation | Q2 2025 | PPS | Completed | - | ..
1.1.1.2: Establishment of a mechanism for regular annual determination of the number and reporting on bylaws that were not adopted within the prescribed time limits through the PRWG/Report on the Work of the Government | Q4 2025 -> Q4 2027 | General Secretariat of the Government (GENSEK) | In progress | - | .. |  | The activity has not been completed and its implementation has been envisaged in the new RRPPMI Programme 2025-2030 | The defined activity within the new RRPPMIP 2026-2030: 1.1.1.1 Establishment of a mechanism for regular annual determination of the number and reporting on bylaws that were not adopted within the prescribed time limits through the PRWG/Report on the Work of the Government.
1.1.1.3: Analysis of the regulatory framework changes and the development of the recommendations with a view to achieve greater predictability of the business environment for economic operators and of living conditions for citizens | Q3 2025 | PPS | In progress | - | .. |  | The activity has not been completed and its implementation has been envisaged in the new RRPPMI Programme 2025-2030 | The defined activity within the new RRPPMIP 2026-2030: 1.1.1.3 Analysis of the regulatory framework changes and the development of the recommendations with a view to achieve greater predictability of the business environment for economic operators and of living conditions for citizens.
1.1.1.4: Capacity building for the GENSEK for the establishment of a mechanism for regular annual determination of the number and reporting on bylaws that were not adopted within the prescribed time limits through the PRWG/Report on the Work of the Government | Q4 2025 -> Q4 2027 | GENSEK | In progress | - | .. |  | The activity has not been completed and its implementation has been envisaged in the new RRPPMI Programme 2025-2030 | The defined activity within the new RRPPMIP 2026-2030: 1.1.1.2 Capacity building of the General Secretariat of the Government for the establishment of a mechanism for regular annual determination of the number and reporting on bylaws that were not adopted within the prescribed time limits through the PRWG/Report on the Work of the Government.
.
Measure 1.1.2: Improvement of the framework for systemic monitoring of legislation quality and effectiveness (ex-post evaluation)
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The Regulation on Regulatory Impact Assessment that regulates the contents of ex-post evaluations adopted (0 - No, 1 - Yes) |  |  | 0.00 (2023) |  | 0.00 | 1.00 | Regulation on Regulatory Impact Assessment was adopted in March 2025. The methodology for the ex-post impact assessment is regulated in Articles 24-27, as well as in Annex 2.
Share of the adopted legislative acts which show, as part of their report on the conducted impact assessment, a review of the results of the legislation being amended, in the total number of adopted legislative acts that require a review of the results of the legislation being changed (%) |  |  | 76.00 (2023) |  | 79.00 | 64.29 | Short time limits for the adoption of the regulations had a negative impact on the quality of their preparation and adherence to the adoption procedure.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.2.1: Improvement of the content of ex-post evaluation for legislation and supplement to the questions that the SABs answer during the preparation of the ex-ante and ex-post analyses, via amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | Regulation on Regulatory Impact Assessment was adopted in March 2025. The methodology for the ex-post evaluation of effects is regulated in Articles 24-27, as well as in Annex 2.
1.1.2.2: Established criterion and mechanism for the determination of priority legislation that must undergo an annual ex-post evaluation, regardless of whether any amendments thereto have been planned for that year, via amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | In progress | - | The Regulation on Regulatory Impact Assessment prescribes that the report on the ex-post evaluation and on regulatory performance evaluation is submitted to the Government for the purposes of informing it, for the legislation with limited period of effectiveness that eliminate the disturbances on the market of goods and services in line with the law, as well as for the legislation with significant impacts in line with the Plan adopted by the Government. The criteria for the legislation that will be encompassed by the plan need to be developed. |  | The activity has not been completed. The delay of the commencement of the EU4PAR Project, which is to provide support. | The defined activity within the new RRPPMIP 2026-2030: 1.1.2.1 Development of the criteria for the selection of legislation and preparation of a Plan for ex-post evaluation and regulatory performance evaluation.
1.1.2.3: Improvement of the Manual for public policy and regulation impact assessment in the part pertaining to ex-post evaluation, in line with the amendments to the Regulation on Regulatory Impact Assessment | Q3 2025 | PPS | In progress | - | The update process for the Manual has begun, in line with the Regulation on Regulatory Impact Assessment, on the part pertaining to ex-ante impact assessment. |  | The activity has not been completed. The activity was operationally modified to become “Development of a RIA Manual”, i.e., instead of the amendments to the existing Manual for impact assessment of public policy documents and legislation, a separate manual shall be developed solely for RIA. | The activity of Improvement of the Manual for regulation impact assessment in the part pertaining to ex-post evaluation and implementation of tests, in line with the amendments to the Regulation on Regulatory Impact Assessment, will be implemented in the next cycle. The defined activity within the new RRPPMIP 2026-2030: 1.1.2.4 in the new RRPPMIP 2026-2030: 1.1.2.5.
1.1.2.4: Establishment of a list of priority legislation that must undergo an annual ex-post evaluation, in line with the Regulation on Regulatory Impact Assessment | Q4 2025 | PPS | Not commenced | - | The implementation will commence once the criteria have been determined in detail and mechanisms have been elaborated for the selection of priority legislation for which an ex-post analysis should be made on an annual level, as well as after the trainings have been held, so that support can be provided. |  | The delay of the commencement of the EU4PAR Project that is to provide support. | The defined activity within the new RRPPMIP 2026-2030:. Development of the criteria for the selection of legislation and preparation of a Plan for ex-post evaluation and regulatory performance evaluation.
1.1.2.5: Development of a training programme for the implementation of an ex-post analysis (TOT for PPS and SABs/IPMS) and the implementation of ToT | Q3 2025 | PPS | In progress | - | Although there was a delay in the adoption of the Regulation that would define the scope and material of trainings, during the period 2021-2023, the PPS improved the methodological support to proposers by developing practical advice and tools, on the basis of the lessons learned from the previous regulation and the draft of the new one. The materials have been collected and presented on the Public Policy Management Platform. |  | The activity has not been completed. Due to delays in the adoption of the normative framework, the activity has not been implemented in the planned period and will be postponed to the next planning cycle. | The activity “Development of the training for ex-post evaluation of the effects of legislation, implementation of the “train the trainers” programme and implementation of training” will be envisaged in the next cycle.
1.1.2.6: Include trainings on ex-post evaluation of the effects of legislation in the annual plan of the NAPA | Q4 2025 | PPS | Completed | - | The training programme was included in the General Programme for the Training of Civil Servants for 2026, which was adopted by the Government on 13 November 2025. https://www.napa.gov.rs/tekst/49/godisnji-programi-obuka-naju.php |  |  | In the upcoming period, the realisation of trainings is expected with the support from the EU4PAR project, in cooperation with NAPA.
1.1.2.7: The network of experts for ex-ante and ex-post analysis from SABs (including employees in analytical units) established | Q4 2025 | PPS | Abandoned | - | .. |  | This activity requires a lot of resources, and it is questionable to what extent it could affect the regulatory impact assessment process.
1.1.2.8: Organising the annual event on the Impact Assessment | Q4 2025 | PPS | Not commenced | - | Not held in 2025 due to a lack of funds. |  | Lack of funds | The event is planned for 2026, in cooperation with the EU4PAR Project.
1.1.2.9: Upgrade to the PPS website with regards to the presentation of tools for the implementation of the Regulatory and Public Policy Impact Assessment and good practice examples | Q4 2022 | PPS | Completed | - | The activity is a continual mechanism to support the implementation of RIA. With the update to the PPS website in the period 2022-2024, access to manuals, good practice examples and Q&A materials has been provided.
.
Measure 1.1.3: Improvement of the business environment and reduction of administrative costs for businesses and citizens through systemic use of the impact assessment tool (MSME test, measuring administrative costs, and checklist of regulation impacts on competition)
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of the adopted legislation for which the administrative costs/savings and effects on MSMEs and competition have been included in the report on the conducted impact assessment relative to the total number of adopted legislation that needed to have the administrative costs, effects on MSMEs and competition assessed (%) |  |  | 6.80 (2023) |  | 13.00 | 45.45 | An extremely high value has been achieved because a certain number of legislative acts have been adopted with the aim of decreasing the administrative costs, which had not been the case in earlier years.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.3.1: The obligation of running an MSME test and presenting the results within the Regulatory Impact Assessment redefined for all legislation with an impact on the business environment, through the amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | The activity was aimed at connecting the tool for the RIA (administrative cost calculator, MSME test and gender equality test) with the standard form of the report on the implemented impact assessment, which allowed for uniform reporting without changing the methodology. Despite the delays in implementation due to several external factors, the key result was achieved in March 2025 with the adoption of a new Regulation that prescribed the obligation of conducting a MSME test for all legislative acts that affect the business environment.
1.1.3.2: Development of a web application for the MSME test | Q4 2025 | PPS | In progress | - | The specification was elaborated and work has begun on the development of a web application for the MSME test within the design of the new PPS website. |  | The activity has not been completed. There have been some delays within the D4BE Project in the first half of 2025, through which this activity was being implemented. The implementation continued in Q4 2025. | The defined activity within the new RRPPMIP 2026-2030: 1.1.2.6 Development of a web application for the Test of the impact on micro, small and medium enterprises (the MSME test)
1.1.3.3: The obligation of calculating the administrative cost and presenting the results within the Regulatory Impact Assessment redefined for all legislation with an impact on the administrative load of end users, through the amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | Regulation on Regulatory Impact Assessment was adopted in March 2025. Analysis and calculation of administrative cost were regulated in Article 11 and Annex 1.
1.1.3.4: The obligation of performing a competition impact assessment and presenting the results within the Regulatory Impact Assessment redefined for all legislation with an impact on competition, through the amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | Regulation on Regulatory Impact Assessment was adopted in March 2025. Analysis and calculation of administrative cost were regulated in Article 11 and Annex 1.
1.1.3.5: Improvement of the Manual for public policy and regulation impact assessment in the part pertaining to the implementation of tests, in line with the amendments to the Regulation on Regulatory Impact Assessment | Q3 2025 | PPS | In progress | - | The update process for the Manual has begun, in line with the Regulation on Regulatory Impact Assessment, on the part pertaining to the ex-ante impact assessment. |  | The activity has not been completed. Although this activity had been planned for 2023-2024, it was postponed several times due to delays in legal framework amendments. | The activity has been included in the new RRPPIP Programme for the period 2026-2030. The defined activity within the new RRPPMIP 2026-2030: 1.1.2.4.
1.1.3.6: Implementation of at least one electronic training for the implementation of the tools for economic impact assessment | Q4 2025 | NAPA | Completed | - | The online training Implementation of analytical reporting system for LSGUs was successfully completed by 5 participants in 2025 . The training Analytical service − Basic tool for the use of data at the LSGU level, in the form of a webinar, was completed by 25 participants.
1.1.3.7: Supporting bodies in conducting tests | Q4 2025 | PPS | Completed | - | The activity was aimed at continual support to SABs in the implementation of impact assessment tools, in particular the AC calculation and MSME tests, and the SABs were supported through trainings and consultations. |  |  | The support will intensify once the MSME test web app launches.
.
Measure 1.1.4: Improvement of legislation quality through the introduction of gender mainstreaming
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of adopted legislation for which the impacts on gender equality had been analysed within the Report on the implemented impact assessment (Number) |  |  | 0.00 (2023) |  | 2.00 | 0.00 | In the observed period, there had not been sufficient institutional interest expressed for the implementation of the pilot application of the gender equality test, despite the efforts from the PPS.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.4.1: The obligation of running a gender equality test and presenting the results within the Regulatory Impact Assessment redefined for all legislation with an impact on gender equality, through the amendments to the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | The new Regulation on RIA additionally improves the provisions prescribing the obligation of conducting a Gender Equality Test and including the results in the documentation accompanying the adoption process.
1.1.4.2: The gender equality test and the instructions for its use harmonised with the new law regulating gender equality | Q2 2022 | PPS | Completed | - | ..
1.1.4.3: Training implemented for the GE test for 20 civil servants in a particular priority area for gender equality | Q4 2022 | PPS | Completed | - | ..
1.1.4.4: The training programme for the use of the gender equality test developed | Q2 2022 | PPS | Completed | - | ..
.
Measure 1.1.5: Improvement of the use of impact assessment in the process of harmonising domestic legislation with the EU acquis
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of the legislation adapted during a calendar year, which are being harmonised with the EU acquis, for which a full impact assessment has been elaborated, containing the review of comparative practice, in the total number of the adopted legislation being harmonised with the EU acquis during the calendar year (%) |  |  | 21.70 (2023) |  | 30.00 | 12.19 | Short time limits for the adoption of the legislation for harmonisation with the EU acquis have had a negative impact on the quality of their preparation.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.5.1: Determination of impact assessment specificity for the legislation for harmonisation with the EU acquis in the Regulation on Regulatory Impact Assessment | Q1 2025 | PPS | Completed | - | Regulation on Regulatory Impact Assessment was adopted in March 2025. Specificities of impact assessment for the legislation for harmonisation with the EU acquis is regulated in Article 9, Annex 1.
1.1.5.2: Providing support to SABs during the implementation of impact assessment for at least two legislative acts for harmonisation with an EU regulation, to be commenced once the relevant legal framework is in place | Q4 2025 | MEI | In progress | - | The activity was introduced with the amendments to the Programme 2024, to provide practical support to SABs in applying the new Regulation on RIA to the legislation being harmonised with EU acquis. Within the PLAC 2024-2026 Project, technical assistance was envisaged in the preparation of the assessments for three legislative acts (consumer rights, electronic documents, digital services). |  | Within the implementation, the support beneficiary decided that the RIA for one of the legislative acts was not necessary, so the remaining two assessments will be submitted to the ministries and the PPS. | The defined activity within the new RRPPMIP 2026-2030: 1.1.2.3 Providing support to state administration bodies in the implementation of the regulatory impact assessment, for legislation for harmonisation with EU legislation, for two legislative acts in each year of the duration of the Programme
.
Specific Objective 1.2: Capacity building and application of tools for high-quality creation and enforcement monitoring of public policies and regulations
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of the PPDs adopted that contain a complete impact assessment, in the calendar year, compared to the number of PPDs adopted that require an impact assessment (%) |  |  | 50 (2020) |  | 100 | 0 | Of the total of 13 PPDs adopted by the Government in 2025, 5 PPDs required an impact assessment. Of the total of 5 PPDs, 4 PPDs had a partial impact assessment and 1 PPD had an insufficient impact assessment.
.
Measure 1.2.1: Organisational set up of Internal Planning and Management Support Units (IPMS)
Institution in charge: GENERAL SECRETARIAT OF THE GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of the ministries that have set up an internal planning and management support unit (IPMS), relative to the total number of ministries obliged to set up an internal planning and management support unit (%) |  |  | 0.00 (2020) |  | 100.00 | - | At its 62nd session on 29 January 2026, the Government adopted a Conclusion accepting the Guidelines for the establishment of analytical units in the state administration bodies as a foundation to pilot this process.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.1.1: Elaboration of an Analysis of the strategic and regulatory framework for the establishment of analytical units with a special emphasis on already established analytical units, with conclusions and recommendations for the improvement of the framework, and for facilitated establishment of completely functional analytical units | Q1 2025 | MoF | Completed | - | The analysis on the strategic and regulatory framework for the establishment of IPMS units, with emphasis on the existing practice and concrete recommendations for improvement, has been prepared. This document has become the foundation for the future elaboration of the guidelines for the establishment and operation of IPMS units.
1.2.1.2: Drafting and adoption of the Guidelines for the establishment and operation of IPMS units adopted by the Government in its act | Q1 2025 | MPALSG | In progress | - | The Draft Guidelines for the establishment and operation of IPMS units have been developed. |  | The activity has not been completed in 2025 as the Guidelines for the establishment and operation of IPMS units have not been adopted by the Government by the end of 2025. The guidelines were adopted in 2026.
1.2.1.3: Support to implementation of the guidelines in selected SABs | Q4 2025 | SAB | In progress | - | .. |  | The implementation of this activity requires the adoption of the Guidelines.
.
Measure 1.2.2: Improvement of the skills of managers and civil servants for the preparation, monitoring of implementation and reporting on implementation of planning documents and a more efficient financial management and control system
Institution in charge: NATIONAL ACADEMY OF PUBLIC ADMINISTRATION
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The training programme for managers and civil servants in data management developed (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | 1.00 | In the general training programmes for civil servants and managers in public administration bodies that NAPA has adopted for 2024, the trainings on data management are classified under a special theme area of “Data management”.
The number of managers and civil servants who have successfully completed data management trainings envisaged in the annual programme (Number per year) |  |  | 0.00 (2020) |  | 50.00 | 387.00 | There are 34 trainings within the theme area “Data management” and 387 civil servants were trained in 2025 (of which 85 were managers).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.2.1: Analysis of the necessary competences of employees in IPMS units, with recommendations | Q4 2021 | HRMS | Completed | - | ..
1.2.2.2: Harmonisation of the Regulation on the determination of competencies for the work of civil servants in line with the recommendations from the previous activity | Q4 2021 | HRMS | Completed | - | ..
1.2.2.3: Analysis of the available trainings in the annual training programmes that pertain to data management (collection, storage, analytical processing and exchange) | Q4 2021 | NAPA | Completed | - | ..
1.2.2.4: Development of training programmes for managers and civil servants on data management (collection, storage, analytical processing and exchange)(to be implemented as a complement to the activities envisaged in the Action Plan 2021-2025 for the implementation of the PARS RS for the period 2021-2030. | Q1 2022 | NAPA | Completed | - | ..
1.2.2.5: Piloting the developed training programme for managers and civil servants in data management (collection, storage, analytical processing and exchange) | Q4 2022 | NAPA | Abandoned | - | The piloting for the data management training programme is not necessary, as this training has become part of the regular trainings organised by NAPA since 2022, when it was introduced with the adoption of the general training programmes for civil servants and managers in public administration bodies.
1.2.2.6: Implementation of a minimum of 2 trainings for managers and civil servants on data management (collection, storage, analytical processing and exchange) every year, in line with the annual training programme (to be implemented as a complement to the activities envisaged in the Action Plan 2021-2025 for the implementation of the PARS RS for the period 2021-2030) | Q4 2025 | NAPA | Completed | - | Within the general training programmes for the national and local level, special theme areas for Data Management have been developed. A total of 34 trainings were held in 2025. Within this theme area, 387 participants were trained, of which 85 were managers, in 2025. For the training Data Opening alone, the training was organised 3 times with 72 participants. |  |  | In the General Training Programme for civil servants for 2026, new trainings have been envisaged: Opening and administering institutional accounts on the Open Data Portal and Management of open data, expected to be implemented in 2026.
.
Measure 1.2.3: Setting up grounds for the introduction of a systemic approach to data management
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The data management standards developed (collection, storage, analytical processing and exchange) for the data from SAB records for one planning document (0 - No, 1 - Yes) |  |  | 0.00 (2023) |  | 1.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.3.1: Support to mapping/listing data that the selected SAB is collecting in the course of their operation, which are necessary for drafting, implementation monitoring, reporting on implementation and evaluating planning documents and legislation. | Q1 2025 | PPS | Completed | - | For the purposes of elaborating an APIGP for the period 2025-2027, in cooperation with the line ministries, the PPS mapped/listed the relevant data which serve as the foundation for APGIP development. Based on the mapped data, priority results and indicators were selected for every line ministry, together with key data based on which their values are calculated, so that the achievement of results in the upcoming period can be monitored.
1.2.3.2: Elaboration of data management standards for the data needed for a planning document implementation monitoring and reporting | Q2 2025 | ITE |  | - | ..
1.2.3.3: Piloting of data management standards for the data for planning document implementation monitoring and reporting | Q3 2025 | PPS | Not commenced | - | Implementation of activities has, as its precondition, the development of data management standards.
1.2.3.4: Elaboration of a report based on the piloted data management standards for planning document implementation monitoring and reporting | Q4 2025 | ITE |  | - | ..
.
Measure 1.2.4: Providing analytical basis for public policy creation
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of surveys conducted for the purposes of public policy creation (Number (cumulative)) |  |  | 0.00 (2020) |  | 4.00 | 25.00 | During the reporting year, the impact assessment of the Draft Law on Textbooks was elaborated. (The achieved value, expressed as cumulative, far exceeded the target value, as research and analyses were conducted in 2022 (situational diagnostics), with appropriate recommendations formulated, for different areas, as a foundation to determine the priority objectives within the APIGP 2023-2025).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.4.1: Elaboration and activation of the internet platform “Policy Club” and its promotion with a view to form a network of experts and establish a database of their articles and analyses relevant for public policy creation | Q4 2022 | PPS | Completed | - | ..
1.2.4.2: Analysis of the problems in public policy implementation and definition of challenges and concrete SAB needs bearing in mind priorities from the APIGP | Q4 2025 | PPS | Completed | - | Situational analyses were performed in the following areas, for the purposes of preparing a new APIGP 2025-2027: healthcare, agriculture, energy, civil construction and transport, environment protection, culture.
1.2.4.3: Elaboration of analyses for the purposes of implementing reform priorities of the Serbian Government, with a view to improve the business environment, and presentation of the results | Q3 2025 | PPS | Abandoned | - | .. |  | “All initiatives within component 3: Instrument for flexible technical support of the EU for Better Business Environment (EU4BE) Project, that had been planned for 2025 were stopped and were not implemented (decision of the World Bank, the implementer of the project; as the project was drawing to an end, the implementation time limits were short). EU4BE project closed on 31 May 2025.”
1.2.4.4: Elaboration of the calculator for the calculation of costs of planning documents implementation | Q4 2025 | PPS | In progress | - | The technical specification for a calculator for the calculation of the costs of public policy and legislation was elaborated (April 2025), as a precondition for the preparation of the Terms of Reference for the development of the calculator. The Terms of Reference were elaborated for the calculator development and a public call was published (August 2025), based on which the consultant was selected (September 2025) and the contract was concluded (November 2025). |  | The activity has not been completed. | The activity is planned to be completed in 2026.
1.2.4.5: Upgrade of a business information system for LSGUs (analytical service of LSGUs and analytical-reporting system of LSGUs) − databases at LSGU level | Q4 2025 | PPS | Completed | - | “Classification for the comparison of the harmonisation of indicators in the LSGU analytical service (AS LSGU) with the sustainable development goals (SDGs) also follows the methodological guidelines that PPS is using when comparing indicators in public policy documents with SDG indicators. The applied classification is based on comparative experiences of other countries that, as a rule, have a three-level scale: identical, adjusted, supplementary. Of the 519 indicators in the AS LSGU, 326 (63%) have been mapped to the SDG indicators, of which 36 (7%) were identical, 163 (31%) were adjusted and 127 (25%) were supplementary, while 193 (37%) cannot be mapped (not applicable). The results of this mapping were entered in the Methodological notes for indicators in the Analytical Service of LSGUs”.
.
Measure 1.2.5: Improvement of the existing and initiation and creation of innovative public policy solutions based on the data and research of end user needs
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of innovative solutions in public policy creation (Number (cumulative)) |  |  | 0.00 (2020) |  | 6.00 | 5.00
The number of innovative ideas tested for the purposes of existing public policy improvement (Number (cumulative)) |  |  | 0.00 (2020) |  | 4.00 | 4.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.5.1: Two innovative solutions designed and piloted in different public policy areas | Q4 2022 -> Q4 2025 | PPS | Completed | - | With the support from the GIZ Project, the PPS initiated and implemented several pilot projects in healthcare, education, culture and tourism during the implementation period. The most significant results were achieved in preventative health (invitation letters and calculator for screening), as well as in education, through the pilot project “A classroom that I want”. These solutions were designed and piloted and their further implementation has been transferred to the competent institutions. In the field of culture, an online ticket sale analysis was implemented, while in tourism, a model was developed to survey visitor opinions. Most activities were implemented successfully or are in the final stages, while some segments, such as piloting in culture, were completed in 2025.
1.2.5.2: Research and analysis of the existing public services and testing one innovative idea/solution with a view to its improvement | Q4 2022 -> Q4 2025 | PPS | Completed | - | The activity has been continually implemented since 2021 in cooperation with the GIZ Project “Support to Public Administration Reform”. In the initial stages, an analysis of tour operator services accessibility was conducted, after which a pilot project “Museum 4 All” followed, which encompassed the establishment of cooperation with four museums and the development of a single electronic ticket. This pilot project now allows further interconnection between the museums, for the sale of joint tickets. In addition, service analyses and consultations were conducted with tour operators from Sokobanja and Kragujevac, for the purposes of creating new services.
1.2.5.3: Promotion of innovative solutions and new approaches in public policy creation on the PPS website and through social networks, as well as through the organisation of annual conferences and networking with all stakeholders | Q4 2025 | PPS | Completed | - | The website of the Innovation Group was launched and is being updated regularly, informative and promotional materials have been prepared, and the implemented pilot projects have been presented to the general public and potential partners. All activities were implemented, except for the annual conferences specifically intended to this activity, which was compensated through other promotional activities of the PPS.
1.2.5.4: Implementation of training for PPE employees for the implementation of new methods in public policy creation | Q3 2022 | PPS | Completed | - | ..
1.2.5.5: Preparation of training programmes for the creation and implementation of innovative public policy solutions | Q4 2022 | NAPA | Completed | - | ..
1.2.5.6: Implementation of training programmes for civil servants for the creation and implementation of innovative public policy solutions | Q4 2025 | NAPA | Completed | - | Training entitled “Application of design thinking methodology in public policy” was organised, attended by 12 participants. The online training “Creative user-oriented service and policy creation (“DESIGN THINKING”) was successfully completed by 16 participants in 2025.
.
Specific Objective 1.3: Effective public policy coordination
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The total number of planning areas with a revised and optimised planning framework (a clear hierarchical structure of PPDs established within planning areas) (number) |  |  | 1 (2020) |  | all | 6 | A total of six planning and public policy implementation areas have been optimised, namely: public administration, education, public information, employment, industry and small and medium enterprises and entrepreneurship.
.
Measure 1.3.1: Planning framework and public policy design with a view to achieve Government priorities and sustainable development goals
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Regulation on the Methodology of Public Policy Documents Drafting adopted (0 - No, 1 - Yes) |  |  | 0.00 (2023) |  | 0.00 | 1.00 | On its session held on 6 March 2025, the Government of the Republic of Serbia adopted the Regulation on the Methodology of Public Policy Documents Drafting.
The Regulation on the Development Plan Drafting Procedure adopted (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | 1.00 | On its session held on 29 June 2025, the Government of the Republic of Serbia adopted the Regulation on Drafting of the Development Plan of the Republic of Serbia.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.1.1: Prioritising recommendations from the ex-post evaluation of legislation effects for the purposes of public policy and regulatory reform management | Q4 2021 | PPS | Completed | - | ..
1.3.1.2: Drafting of the Regulation on the Methodology of Public Policy Documents Drafting | Q1 2025 | PPS | Completed | - | On its session held on 6 March 2025, the Government of the Republic of Serbia adopted the Regulation on the Methodology of Public Policy Documents Drafting.
1.3.1.3: Review of the developed manuals for comprehensive public policy and regulatory reform management | Q4 2025 | PPS | Completed | - | ..
1.3.1.4: Expansion of the visualisation of the data from the PPS’s website relating to sustainable development goals and PPDs | Q2 2025 | PPS | Completed | - | The PPD Scheme on the PPS’s website has been upgraded, related to linking and presenting objectives and sub-objectives of SDGs and PPDs.
1.3.1.5: Analysis of the selected composite indicators with a view to improve the position of the Republic of Serbia on international ranking lists | Q3 2024 | PPS | Completed | - | ..
1.3.1.6: Activities on ensuring donor support for the engagement of experts, as well as coordination of activities in the field of project management during the the expert's work on the elaboration of preparatory materials that are to support the bodies and structures in the elaboration of the initial analytics | Q2 2024 -> Q2 2025 | MEI | Completed | - | ..
1.3.1.7: Elaboration of a summary of existing documents proposed in Article 2 of the Regulation on the Procedure for the Drafting of the Development Plan | Q2 2025 | SAB | Completed | - | ..
1.3.1.8: Elaboration of parts of analyses envisaged in Art. 2 and Art. 4 of the Regulation on the Procedure for the Drafting of the Development Plan (analysis of Serbian development potentials, international economic trends and commitments undertaken) | Q3 2025 | SAB | Not commenced | - | .. |  | According to the adopted Regulation on the Procedure for the Drafting of the Development Plan, prior to commencing the drafting of analyses, the establishment of an institutional structure was envisaged to manage this process, which, in its first step, encompasses the establishment of the Expert Group for the drafting and implementation monitoring of the Development Plan for the Republic of Serbia. | Establishment of the institutional structure for the commencement of work on the drafting of the Development Plan, when the appropriate conditions arise.
1.3.1.9: Elaboration of the Report on the Existing Situation for the purposes of Drafting the Development Plan for the Republic of Serbia | Q4 2025 | PPS | Not commenced | - | .. |  | The activity was aimed at synthesising all previously performed analyses to elaborate a situational analysis envisaged in Article 4 of the Regulation on the Procedure for the Drafting of the Development Plan. Due to delays in activities that precede it, this activity was not completed in 2025.
1.3.1.10: Preparation of the baseline considerations based on prior analyses and elaboration of a roadmap for the elaboration of the Development Plan for the Republic of Serbia | Q3 2024 -> Q4 2025 | PPS | In progress | - | .. |  | The precondition for this activity is the completion of the situational analysis, so this activity has not been completed in 2025.
.
Measure 1.3.2: Improvement of planning and public policy implementation areas
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Support provided for legal framework optimisation (0 - No, 1 - Yes) |  |  | 0.00 (2023) |  | - | 1.00 | Amendments to the prescribed public policy planning and implementation areas was envisaged within the Regulation on the Methodology of Public Policy Documents Drafting
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.2.1: Drafting a Government Act on Repealing Planning Documents (PPDs without APs, PPDs with no time limits, those not harmonised with the LPS etc.) | Q4 2021 | PPS | Completed | - | ..
1.3.2.2: Amendments to the prescribed public policy planning and implementation areas within the Regulation on the Methodology of Public Policy Documents Drafting | Q1 2025 | PPS | Completed | - | ..
.
Measure 1.3.3: Improvement of planning harmonisation at the central level (APIGP, GGWP, NPAA)
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Mechanism for the verification of harmonisation of central level documents established (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | 0.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.3.1: Linking APIGP with the NPAA with regards to legislation and time limits for their adoption | Q1 2025 | PPS | Completed | - | The Activity was originally planned as the establishment of a technical mechanism (checklist) for the verification of PPD harmonisation, with the purpose of monitoring the implementation of activities and the defined time limits in documents such as APIGP, GWPG and NPAA. This activity was implemented during the elaboration of the APIGP for the period 2025-2027, when the time limits for the adoption of legislation between APIGP and NPAA were harmonised.
1.3.3.2: Strengthening technical capacities of the MEI for the preparation and monitoring of NPAA in the context of reconciliating the NPAA with the Government Working Plan (PRWG) | Q4 2025 | MEI | Completed | - | The activity was aimed at strengthening MEI capacities for regular update of the NPAA and control of harmonisation of central planning documents (NPAA, GGWP, APGIP). With support of the GIZ project, a new NPAA application was developed in June 2024, as a tool for the preparation and implementation monitoring of the NPAA, connected to the PRWG system, and user trainings were implemented.
1.3.3.3: Adoption of the starting criteria for the publication of the Conclusion of the Government of the Republic of Serbia on the website of the Serbian Government | Q4 2025 | GENSEK | Not commenced | - | ..
.
Measure 1.3.4: Improving the monitoring of implementation and result reporting for public policies and transparent presentation for the public
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of annual reports on the implementation of AP PPD entered into the UIS, relative to the number of valid AP PPDs entered into the UIS that required reporting, for the previous year (%) |  |  | 37.10 (2023) |  | 50.00 | 73.53 | Of the 34 AP PPD in force entered into the UIS, the annual implementation report on AP PPD entered into the UIS was published by 25 state administration bodies.
The percentage of published Reports on the implementation of medium-term plans developed in the UIS (%) |  |  | 40.00 (2023) |  | 70-94.00 | 95.83 | The total number of Reports on the implementation of medium-term plans for 2024-2026 is 24, while 23 Reports have been prepared through the UIS.
The Report on progress and achievement of the objectives of public policy documents and their contribution to achieving the sustainable development goals from the UN Agenda 2030 prepared and published (0 - No, 1 - Yes) |  |  | 0.00 (2023) |  | 0.00 | 1.00 | The report was prepared and published on PPS website in September 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.4.1: Adjustment of the UIS model for APIGP to the new APIGP format | Q4 2022 | PPS | Completed | - | ..
1.3.4.2: Implementation of training for SABs for the elaboration and monitoring of APIGP implementation | Q1 2022 | PPS | Completed | - | ..
1.3.4.3: Improvement of UIS functions for the reporting on PPD contribution to the achievement of sustainable development goals | Q4 2025 | PPS | Abandoned | - | .. |  | Due to a lack of funding, the implementation of this activity was abandoned.
1.3.4.4: Elaboration of the Report on progress and achievement of the objectives of public policy documents and their contribution to achieving the sustainable development goals from the UN Agenda 2030 | Q2 2025 | PPS | Completed | - | The activity was completed in September 2025, with the publication of the analysis of the achievement of PPD goals and their contribution to the achievement of SDGs. This activity represents the results of the implementation of measures/objectives from the PPD from the perspective of the UN Agenda 2030, which improves the visibility of Serbia’s results.
1.3.4.5: Beginning of the UIS upgrade with an online monitoring tool (OMT) for the purposes of easily accessible, uniform and overseeable electronic reporting to the public on the results achieved in implementation of public policy | Q1 2025 | PPS | Completed | - | ..
1.3.4.6: Extension of the UIS functions for the generation of different reports and statistics views, related to the progress in implementation of public policy documents and medium-term plans | Q4 2025 | PPS | Completed | - | In addition to the standard reports produced by UIS, the options for the elaboration of different formats of reports have been developed, as well as for the generation of visual presentations (graphs) based on the entered data. It is of particular importance that a part of the reporting system has been improved and enabled for use by numerous users.
.
Specific Objective 1.4: Increased involvement of the civil society, businesses and other stakeholders in the early stages of development of public policies and regulations
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Share of adopted PPDs that had a consultative process implemented during their drafting in line with the LPS relative to the total number of adopted PPDs in the calendar year (%) |  |  | 100 (2020) |  | 100 | 100 | Of the total of twelve PPDs adopted by the Government that required consultations, the consultation process was implemented for all twelve.
Share of adopted legislative acts that had a consultative process implemented during their drafting in line with the LPS, relative to the total number of adopted legislative acts in the calendar year (%) |  |  | 35.71 (2020) |  | 80 | 51.3
Share of adopted regulations that had a consultative process implemented during their drafting in line with the LPS relative to the total number of adopted regulations in the calendar year (%) |  |  | 11.46 (2020) |  | 34-36 | 30.1
.
Measure 1.4.1: Establishment and implementation of adequate quality control mechanisms for consultations and public debates, as well as the efficiency and use of the electronic consultations portal
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of participants who submitted comments using the e-Consultation portal in one calendar year (Number) |  |  | 5.00 (2023) |  | 15.00 | 34.00 | Share of the regulations for which consultations had been conducted using the e-Consultations portal in 2025 is 4% lower than in 2024. Consequentially, the number of participants who had the opportunity to submit their comments is smaller.
The number of comments submitted using the e-Consultation portal in one calendar year (Number) |  |  | 5.00 (2023) |  | 60.00 | 299.00 | The number of laws for which consultations had been conducted using the e-Consultations portal in 2025 is 22, which is ten more than in 2024 (12 laws). This also affected the increase in the number of the submitted comments.
Share of the reports published on the consultations conducted using the e-Consultations portal for the adopted legislation and PPDs relative to the total number of adopted legislative acts and PPDs, published on the portal during one calendar year (%) |  |  | 0.00 (2023) |  | 8.00 | 61.50 | In previous years, the reports were extremely rarely published on the Portal. PPS instructions on the need to publish reports, directed at SABs in 2025, contributed to the target values being exceeded by several factors.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.1.1: Preparation of the amendments to the legal framework on consultations and public debates | Q4 2025 | PPS | In progress | - | The Rules of Procedure of the Government have been amended, and have come into force in December 2025. |  | The activity has not been completed. The complexity of the legal framework requires a longer time period for its improvement. | The defined activity within the new RRPPMIP 2026-2030: 1.3.1.1 Amendments to the normative framework for the implementation of consultations and public debates.
1.4.1.2: Development of a special technical instruction on the manner of using the e-Consultations Portal and submission of materials to the state bodies | Q4 2021 | ITE | Completed | - | ..
1.4.1.3: Trainings for SABs for the use of the e-Consultations platform | Q4 2021 | ITE | Completed | - | ..
1.4.1.4: Regular trainings for SABs for the use of the e-Consultations platform | Q4 2025 | NAPA | Completed | - | The trainings are held within the General Programme for Civil Servants Training at NAPA − Participation of the public in the drafting procedure for legislation and public policy documents.
1.4.1.5: Establishment of a system for the implementation and quality monitoring for consultations and public debates (e-Consultations) | Q1 2022 | PPS | Completed | - | ..
1.4.1.6: Elaboration of the report on consultative process implementation using the e-Consultations Portal as an integral part of the Report on the Work of the Government | Q4 2025 -> Q4 2027 | GENSEK | In progress | - | .. |  | The activity has not been completed and its implementation has been envisaged in the new RRPPMI Programme 2025-2030 | The defined activity within the new RRPPMIP 2026-2030: 1.3.2.2. Elaboration of the report on consultative process implementation using the e-Consultations Portal as an integral part of the Report on the Work of the Government.
1.4.1.7: Analysis of the upgrade needs for the e-Consultations platform | Q4 2023 | PPS | Completed | - | ..
.
Measure 1.4.2: Strengthening civil society capacities for participating in the adoption of legislation and planning documents
Institution in charge: MINISTRY OF HUMAN AND MINORITY RIGHTS AND SOCIAL DIALOGUE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of sectors with competences over the topics encompassed by social dialogue during the calendar year (Number) |  |  |  |  | 18.00 | 24.00 | In 2025, the number of sectors with competencies over the topics encompassed by the social dialogue exceeded the target value, as the achieved result was 24, compared to the 12 sectors.
The number of CSOs involved as members in the work of working groups for the elaboration of PPDs and legislation, as well as in provisional bodies (Number) |  |  |  |  | 30.00 | 142.00 | According to the data collected by the Ministry of Human and Minority Rights and Social Dialogue from state administration bodies, the total number of CSOs involved in the work of the working groups for the elaboration of public policy documents and draft legislation in 2025 was 142, of which 26 CSOs were involved through the open call procedure, defined in the Guidelines for the involvement of civil society organisations in working groups for the drafting of public policy documents and draft laws or bills, while 116 CSOs were involved in the work of the working groups through direct invitation. Based on the submitted data, the total number of civil society organisations involved in the work of provisional bodies (provisional bodies with an ongoing mandate), which had been established through a Decision of the Government of the Republic of Serbia in line with Art. 22 of the Rules of Proceedings of the Government (“Official Gazette of the RS” no. 61/2006 – consolidated text, 69/2008, 88/2009, 33/2010, 69/2010, 20/2011, 37/2011, 30/2013, 76/2014 and 8/2019 − other regulation) at the proposal of the competent state administration body was 100 CSOs.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.2.1: Trainings for CSOs for the participation in the process of adoption of legislation and public policy documents, including presentations of the importance of the e-Consultations portal | Q4 2025 | MHMRSD | Completed | - | ..
1.4.2.2: Social dialogue (organisation of meetings with different participants: CSOs, academia, international organisations and other social actors depending on the field) | Q4 2025 | MHMRSD | Completed | - | ..
1.4.2.3: Building capacities of the civil society for involvement in the process of drafting PPDs and legislation and monitoring the implementation of PPDs and legislation | Q4 2025 | MHMRSD | Completed | - | ..