## All activities export 1
The annual Action Plan 2025 implementation report, for: |  |  |  |  | ACTION PLAN FOR THE PERIOD FROM 2024 TO 2025 FOR THE IMPLEMENTATION OF THE LOCAL SELF-GOVERNMENT SYSTEM REFORM PROGRAMME IN THE REPUBLIC OF SERBIA FOR THE PERIOD FROM 2021 TO 2025
Coordinating and reporting institution: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document the Action Plan pertains to: |  |  |  |  | The Local Self-Government System Reform Programme for the Republic of Serbia for the period 2021-2025
General Objective 1: Establishment of a system of local self-government that enables efficient and sustainable exercise of citizens' rights to local self-government
Document proposed by: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Compliance of the local self-government system with the key principles of the European Charter of Local Self-Government (composite scale 1-5) |  |  | 3 (2020) |  | 3-4 | 3 | In 2025, three additional provisions from the first section of the Charter were adopted by the Law on Supplementing the Law on the Ratification of the European Charter of Local Self-Government, adopted on 22 October 2025 (came into force eight days from the publication: “Official Gazette of the Republic of Serbia – International Agreements", number 10/2025). A total of 27 provisions of 30 have been ratified.
Share of LSG expenditures in consolidated expenditures in the Republic of Serbia (%) |  |  | 14.75 (2019) |  | 17-18 | 10.9 | A lower share of local self-government expenditures is the consequence of the funding for priority and capital-intensive investments being taken over by the national level, together with the implementation of fiscal discipline improvement measures, expenditure control measures and measures for limiting local self-government borrowing.
LSGU capacity for the implementation of good governance principles (%) |  |  | 39 (2018) |  | 52-55 | 55.4 | At the end of 2025, performance in good governance was measured using the SCTM's Good Governance Index. The measurement indicated the growth of LSGU capacity in the field of good governance.
Availability and quality of priority public service delivery of the local self-government (Composite scale (1-10)) |  |  | 0 (2020) |  | 6.1 | - | The indicator was not measured in 2025 as donor funds for the implementation had not been provided.
.
Specific Objective 1.1: Improvement of the status and responsibilities of the local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Degree of ECLSG ratification (scale 1-5) |  |  | 3 (2020) |  | 4-5 | 3 | In 2025, three additional provisions from the first section of the Charter were adopted, through the Law on Supplementing the Law on the Ratification of the European Charter of Local Self-Government, adopted on 22 October 2025 (came into force eight days from its publication: “Official Gazette of the Republic of Serbia – International Agreements, number 10/2025). A total of 27 provisions of 30 have been ratified.
Average value of the good governance index in selected areas of: 1) accountability; 2) transparency, openness and participation (%) |  |  | 43 (2018) |  | 57-60 | 61.2 | At the end of 2025, performance in good governance was measured using the SCTM's Good Governance Index. The measurement indicated capacity growth of the LSGUs in the aforementioned fields of good governance.
The share of adopted laws in the total number of adopted laws which concern local self-government to a larger degree, which had been drafted with the participation of LSGUs (Scale (1- 5)) |  |  | 3 (2020) |  | 5 | 4 | A total of 6 laws pertainaining, to a larger extent, to LSG were taken into consideration for the purposes of reporting results in 2025 (e.g. additions and amendments of laws); for five of these laws, it is confirmed that the LSGs and their national associations had taken a more direct role in the drafting process. This is a result showing 83% participation, which according to the composite scale for the calculation of this indicator results in the value of 4.
.
Measure 1.1.1: Continuation of harmonisation of the Serbian legal framework for local self-government with the principles of the European Charter on Local Self-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Adopted amendments and additions to the Law on the ratification of ECLSG and increased degree of ECLSG acceptance in RS (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 1.00 | 1.00 | In 2025, three additional provisions from the first section of the Charter were adopted by the Law on Supplementing the Law on the Ratification of the European Charter of Local Self-Government, adopted on 22 October 2025 (came into force eight days from the publication: “Official Gazette of the Republic of Serbia – International Agreements, number 10/2025).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.1.1: Drafting of the Law on amendments and additions to the Law on the ratification of ECLSG and its referral to the Government for the determination of Bills | Q4 2024 | MPALSG |  | - | ..
1.1.1.2: Elaboration of a harmonisation needs assessment for framework and sector-specific laws with the ratified principles of the ECLSG | Q4 2024 -> Q4 2025 | MPALSG | Not commenced | - | In October 2025, the Law on additions to the Law on Ratification of the European Charter on Local self-Government (ECLSG) was adopted, ratifying an additional 3 provisions of the ECLSG. As the law was adopted in the last quarter of 2025, this analysis has not been started. SCTM will continue its cooperation with MPALSG in the upcoming period, to ratify additional provisions of the ECLSG, as was envisaged in the working version of the new Local Self-Government System Reform Programme 2026-2030. |  | The Law on additions to the Law on Ratification of the European Charter on Local self-Government was only adopted in Q4 2025, and that was the precondition for the elaboration of this analysis. | The working version for the new Local Self-Government System Reform Programme calls for the continuation of MPALSG activities on further ratification of the ECLSG in cooperation with SCTM.
.
Measure 1.1.2: Improvement of the electoral system and local administration capacity building for local elections
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of the chairpersons and secretaries of the Municipal/City Electoral Commissions who are certified for the implementation of local electoral procedures (%) |  |  | 0.00 (2020) |  | 75.00 | 0.00 | The precondition for the achievement of this indicator is the amendment to the Law on Local Election.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.2.1: Elaboration of an analysis that will identify the legal framework for the implementation of mandatory professional development for the management of Local Electoral Commissions (primarily chairpersons and secretaries of Local Electoral Commissions) | Q4 2024 -> Q4 2025 | MPALSG | Not commenced | - | Amendments and additions to the legal framework for the implementation of local elections were adopted on 23 April 2024, only three days before the elections were called, so the elaboration of the Manual for Local Elections was not feasible. Instead, the SCTM elaborated 56 model documents for the implementation of the local election that were envisaged as a constituent part of the planned Manual. These were sent to their members on 26 April 2024, on the day the elections were called. |  | The activity was not implemented as it was predicated on legal framework amendments that would prescribe the issuance of certificates. | Amendment to the legal framework that would prescribe the issuance of certificates.
1.1.2.2: Elaboration of a Manual for Local Elections | Q4 2024 -> Q4 2025 | MPALSG | Completed | 100% | Amendments and additions to the legal framework for the implementation of local elections were adopted on 23 April 2024, only three days before the elections were called, so the elaboration of the Manual for Local Elections was not feasible. Instead, the SCTM elaborated 56 model documents for the implementation of the local election that were envisaged as a constituent part of the planned Manual. These were sent to their members on 26 April 2024, on the day the elections were called. |  | Since the amendments and additions to the legal framework were only adopted on 23 April 2024, just three days before the local elections were called, the elaboration of a Manual for Local Elections was not feasible, but the instructional materials were submitted in the form of model local documents. | In the previous period, the SCTM was publishing the Manual for Local Elections just prior to the elections themselves, but following any changes of the relevant legal framework that may have preceeded that. In that sense, the SCTM will begin its work on the Manual following any future amendments to the Law on Local Elections, that may come prior to the local elections in 2028.
1.1.2.3: Analysis of the possibility of implementation of mandatory professional development and certification for the management of Local Electoral Commissions | Q3 2024 -> Q4 2025 | MPALSG | Not commenced | - | .. |  | The activity was not implemented as it was predicated on the amendment to the legal framework that would prescribe the issuance of certificates. | Amendment to the legal framework that would prescribe the issuance of certificates.
1.1.2.4: Elaboration and implementation of the national programme of e-training for the certificate for the local elections procedure implementation (primarily for the permanent composition of electoral commissions) | Q4 2024 -> Q4 2025 | MPALSG | Not commenced | - | .. |  | The activity was not implemented as it was predicated on the amendment to the legal framework that would prescribe the issuance of certificates. | Amendment to the legal framework that would prescribe the issuance of certificates.
.
Measure 1.1.3: Improvement of the legal framework and procedures for direct participation of citizens in local self-government management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The share of cities, municipalities and city municipalities with employees who were trained in the implementation of the new legal framework on referendums and popular initiatives, in the total number of cities, municipalities and city municipalities (%) |  |  | 0.00 (2020) |  | 90.00 | 0.00 | In 2025, there were no trainings covering the topic of referendums and popular initiatives
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.3.1: Preparation of a Guide for the implementation of referendums and popular initiatives (with the standard forms of legal acts and documents being used) | Q2 2024 | MPALSG |  | - | ..
1.1.3.2: Training of the local self-government employees for the implementation of the referendum and popular initiative procedures (two annual seminars for the Heads of administrative departments, 8 regional trainings for local administration employees) | Q2 2025 | MPALSG | Not commenced | - | In 2025, the SCTM did not implement the envisaged regional trainings for local administration employees. |  |  | Implementation of regional trainings for local administration employees was envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030 (periodic implementation to ensure the maximum coverage of local self-government employees who would attend these trainings).
1.1.3.3: Implementation of an analysis of the position of city municipalities, encompassing detailed conditions or obligations for the establishment of city municipalities, their organisation and role, participation of citizens and city municipality funding (applying a differentiated approach relative to population, geographical and economic criteria) | Q4 2024 | MPALSG |  | - | ..
.
Measure 1.1.4: Improvement of local self-government participation in the elaboration of national legislation and public policies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Legal framework improved with a view to a higher participation of local levels of government in the process of drafting public policy and general documents regulating local self-government issues (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | -
The share of laws pertaining to LSGUs on which information were submitted through the SCTM’s LSG information system, relative to the total number of laws pertaining to LSGUs (%) |  |  | 65.00 (2020) |  | 95.00 | 100.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.4.1: Establishing a Draft Law on amendments and additions to the Law on Local Self-Government within the Working Group, with a view to introduce a provision for mandatory involvement of local self-government units, or national association of local self-government units, in the process of drafting public policy documents, laws and other general acts regulating the issues of interest for the local self-government, and its subsequent referral to the Government for establishment of the bill | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | The working version of the Draft Law on amendments and additions to the Law on Local Self-Government was prepared in 2025. |  | The Working Group has not been formed. | Establishment of a Working Group for the purposes of drafting the law.
1.1.4.2: Continually and regularly informing the local government on the adopted amendments to the legal framework (SCTM’s Law Alert System) | Q4 2025 | MPALSG | Completed | - | In 2025, a total of six laws were adopted (i.e., amendments and additions) which pertain, to a larger extent, to LSG. These were: Law on Additions to the Law on ECLSG Ratification; Air Protection Law; Waste Management Law; Law on Additions and Amendments of the Law on Tax Procedure and Tax Administration; Law on Additions and Amendments of the Law on Charges for the Use of Public Goods; Law on Additions and Amendments to the Law on the Register of Administrative Procedures. LSGs were informed, in a timely manner, of all the most important amendments and additions pertaining to the LSG, as well as on the most important provisions of the law, through SCTM’s “Legal News” newsletter. |  |  | Monitoring of legislative activities pertinent to LSG and continual regular dissemination of the information to the local governments on the adopted legislative changes will proceed as part of the regular operation of SCTM.
.
Measure 1.1.5: Further development of local self-government capacities for the application of the good governance principle
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of local staff trained in the application of good governance principle (cumulatively) (number) |  |  | 831.00 (2020) |  | 2,600.00 | 2,931.00
The percentage of the total number of cities, municipalities and city municipalities that have adopted the new Code of Ethics (%) |  |  | 7.00 (2020) |  | 60.00 | 36.50 | Despite intensive trainings, promotions and a more direct support to cities and municipalities in the adoption of a Code of Ethics for the LSG officials, the percentage of progress over the years has grown slower than expected. This indicator was certainly affected by the election cycles in the LSGs in the preceding years, since the Code is adapted by the local assembly, requiring a more stable operational status − a consensus on prioritisation and voluntary adoption of documents (this is not a legal requirement). At the end of 2025, a total of 62 local self-governments had adopted the aforementioned document (36.5% of a total of 170 LSGs).
The number of cities, municipalities and city municipalities that were recognised with awards for the application of the good governance principles (cumulative) (Number) |  |  | 8.00 (2020) |  | 28.00 | 28.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.5.1: Implementation of the support package for the enhancement of accountability and implementation of anti-corruption policies at the local level in five LSGUs | Q4 2025 | MPALSG | Completed | 100% | Support packages aimed at improving accountability and preventing corruption at the local level were implemented in Vlasotince, Vrbas, Vrnjačka Banja, Lebane and Subotica. The support focused on strengthening the implementation of local anti-corruption plans and integrity plans, as well as on the improvement of the normative and institutional framework in key areas relevant for corruption prevention. During the implementation of activities, the mechanisms for conflict of interest management, protection of whistleblowers and implementation of ethical standards were enhanced, through the adoption of internal acts, appointment of authorised persons and implementation of targeted trainings for employees and officials. Transparency and accountability in the financing of programmes of public interest and civil society organisations were improved through the development and publication of public call plans, improvement of the monitoring and reporting procedures, as well as through strengthening the capacities of employees for the implementation, monitoring and evaluation of the funded programmes. In addition, procedures ensuring operation transparency of public services, institutions and enterprises, as well as the procedures for nominating and appointing management and supervision bodies, were improved. Based on the measurement of the Good Governance Index of accountability and corruption prevention, the average value for the index at the level of the entire support package has increased by 25.53%.
1.1.5.2: Monitoring of the implementation of Good Governance programmes within the Sectoral Programme for Continual Professional Development of employees in LSGs | Q4 2025 | NAPA | Completed | 100% | In 2025, the SCTM organised 5 one-day regional accredited trainings, 2 with the topic of Cooperation with the Civil Society Organisations, attended by 62 participants, and 3 with the topic of Financing Programmes of Public Importance, which is implemented by the associations, attended by 74 participants (Sector Programme for Professional Development of the Employees in the Local Self-Government for 2025). In cooperation with the OSCE mission, 3 additional trainings were organised, with the topic of Cooperation with Civil Society Organisations − good governance and inclusion of the local community in decision-making, attended by 47 participants. |  |  | In the working version of the new Local Self-Government System Reform Programme, the continuation of LSG capacity building has been envisaged through the implementation of training from the field of good governance within the Sector Programme for Professional Development of Employees in the LSGUs.
1.1.5.3: Promotion of the Code of Ethics of local self-government officials (internet conference, organisation of workshops, organisation of national, regional and local events, guide distribution, distribution of the posters with the Code of Ethics text etc.) | Q4 2025 | MPALSG | Completed | 100% | The SCTM provides continual advisory support to the members interested in adopting a Code of Ethics for LSG officials and/or in introducing mechanisms for its implementation. Ending with 2025, a total of 62 LSGs (36.5%) had adopted this Code, and 15 of them also had a Council monitoring its implementation (in 2025, the City Municipality of Vračar was supported in establishing its Council). In addition, in 2025, the Sixth Edition of the Guide for the Application of the Code of Ethics for local self-government officials, intended primarily for the councillors elected at the local election in December 2023 and June 2024, was printed in 15,000 copies and distributed to all LSGs in May 2025. |  |  | As part of SCTM's regular operation, the promotion of the Code of Ethics for LSG officials will continue, as will the advisory support to cities and municipalities for the adoption and implementation of this Code.
1.1.5.4: E-training for officials on the implementation of the Code of Ethics for local self-government officials | Q4 2025 | MPALSG | Completed | 100% | In 2020, SCTM developed an e-training programme for officials on the implementation of the Code of Ethics for LSG officials, as well as instructional materials (written and audio-visual), and the trainings have been held regularly since 2021 (as a rule of thumb, once per year). The training cycle in 2025 was implemented from 15 to 23 October. The training was successfully completed by 123 participants from 56 members of the SCTM. |  |  | In the working version of the Local Self-Government System Reform Program 2026-2030, further capacity building has been envisaged for local officials for the implementation of the Code of Ethics through the implementation of periodic e-trainings.
1.1.5.5: Improvement of the managerial accountability culture in 5 LSGUs through the improvement of the Code of Ethics and Integrity Plan, as well as through their implementation | Q3 2025 | Selected LSGUs | Completed | 97.38% | Technical assistance was provided for the elaboration of the Integrity Plan and the Integrity Plan Implementation Report, as well as for the development of the Code of Conduct for civil servants and ancillary staff and in 9 LSGUs.
1.1.5.6: Development of the fourth analysis of local self-government performance evaluation in the field of good governance using the SCTM’s good governance index (using a sample of 60 LSGUs) | Q4 2025 | MPALSG | Completed | 100% | At the end of 2025, the SCTM conducted a regular periodic performance and capacity evaluation of LSGUs in the field of good governance application, using the Good Governance Index. The evaluation was performed using a sample of 57 and not 60 LSGUs, but the results can be considered comparable from the methodological viewpoint. Progress in all areas of good governance (accountability, transparency and participation, equality, efficiency and effectiveness, and anticorruption) has been found for the LSGUs, in particular: from 52.9% in 2023 to 55.4% in 2025. |  |  | In the working version of the Local Self-Government System Reform Program 2026-2030, continuation of periodical LSGU performance evaluation in the field of good governance has been envisaged.
1.1.5.7: Implementation of the support package for the improvement of transparency and participation in five LSGUs (support to the inclusion of citizens in the process of budget adoption and transparency of the budgeting process) | Q4 2025 | MPALSG | Completed | 100% | The municipalities of Bogatić, Boljevac, Kuršumlija, Mionica and the city municipality of Pantelej in Niš were the beneficiaries of a support package aimed at improving citizen participation and transparency in budget planning and in the funding of civil society organisations. By the end of the project, the plans for the implementation of participatory budgeting were developed and implemented in the municipalities of Boljevac, Kuršumlija and CM Pantelej in Niš, as was the plan for the gradual introduction of gender-sensitive budgeting. In four municipalities (Bogatić, Kuršumlija, Mionica and Pantelej – Niš), gender-sensitive targets and indicators were formulated and implemented in the preparation of the 2025 budget. In all five municipalities, citizen guides were elaborated for the key budget documents (draft budget for 2025, decision on the budget for 2025, final budget account for 2023), which improved availability of budget information and made them easier to understand. Transparency of civil society organisations funding was improved through the publication of public calls and reports on the implemented projects and effects achieved. Additional support was provided for the implementation of participatory budgeting and the elaboration of citizen guides for budgeting documents for 2026. According to the measurement of the Good Governance Index in the field of transparency and participation, the average value for the index at the level of the entire support package has increased by 26.92%.
1.1.5.8: Organisation of a public call for the annual award competition for the best municipal/city administration in terms of applying good governance principles | Q4 2025 | MPALSG | Completed | 100% | The public call for the Annual Award for the Good Governance Principle Application in 2024 was opened at the end of May 2025. In addition to a 7.4 million dinar fund provided by MPALSG in line with the Rulebook on the manner and criteria for the distribution of funds to fund the programmes supporting the development and operation of the local self-government system (“Official Gazette of the RS” no. 101/21 and 69/24), the award recipients in 4 good governance categories were also awarded ICT equipment sets in the total value of 4,885,000.00 dinars awarded by SCTM from the funds of the “Partnership for Good Local Government” programme supported by the Swiss Government. The MPALSG committee selected 4 LSGUs: Sokobanja (efficiency and effectiveness), Zaječar (transparency and public participation in the work of local self-government), Veliko Gradište (accountability and rule of law) and Raška (equality and anti-discrimination). |  |  | In the working version of the Local Self-Government System Reform Program 2026-2030, continuation of the good governance principle promotion has been envisaged through the annual award for the best LSGUs.
1.1.5.9: Implementing the local self-government support package (for the elaboration/review and implementation of multiannual action plans for the implementation of participatory processes in the decision-making related to the use of LSG's own revenues, support for local community councils in the application of participatory mechanisms in the elaboration and implementation of development programmes and local community financial plans) | Q1 2025 | MPALSG | Completed | 100% | The activity was successfully implemented within the project (MED 3, supported by Swiss Government) and contributed to strengthening the institutional capacities of local self-government units (LSGUs) and local community (LC) councils for the implementation of participatory mechanisms in the process of planning and decision-making on the use of own revenues and local development programmes. The support encompassed technical assistance, advisory services and the development of standardized model documents, which allowed for more consistent and transparent implementation of citizen participation at the local level. Within support to LSGUs in 2025, a final analysis was conducted on the practice of public debates on the budget for 2025 in 44 LSGUs, and the methodological tools for citizen participation monitoring were finalised (LIPA index, Local Participation Index). These analyses have allowed for an insight into the degree of harmonisation with legal and own procedures, transparency of the process and the manner of reporting on citizen proposals. The results showed moderate progress compared to the previous period, but have also identified room for improvement with regards to the quality of reporting, proposal valuation, their treatment in the budget and involvement of the citizens in the early stages of the budget cycle. Implementation of direct support to LC councils in the development and implementation of action plans and financial programmes ended in 2024, and there have been no new activities in this field. This support resulted in a clearer definition of the procedures for communication with citizens, introduction of mechanisms for the collection and processing of proposals submitted by citizens, as well as through standardisation of the documentation that accompanies planning and implementation of development initiatives. In this way, the capacities of LCs in terms of sustainable implementation of participatory mechanisms in planning, budgeting and implementation monitoring were strengthened. The activity was implemented fully according to plan, while the objectives pertaining to the domain of strengthening the participatory practices at the local level were achieved and contributed to meeting the expected project outcomes. |  |  | Sets of recommendations were prepared for LSGUs and national institutions, including the proposals for the amendments in the normative acts regulating public consultations and the budgeting process, which set the foundation for further systemic strengthening of participatory administration after the completion of the project. In this way, the value and long duration of the achieved results was ensured, as was the potential for their replication and institutionalisation in a wider context.
1.1.5.10: Preparation and implementation of the programme for the financing of 14 local self-governments, aimed at supporting development and implementation of participatory models for the allocation of own revenues | Q4 2024 -> Q4 2025 | MPALSG | Completed | 100% | The activity was successfully implemented and completed within the project. Of 15 partner LSGUs, 14 continued applying their participatory programmes, while the Municipality of Arilje did not participate in the activity. The project team provided advisory and technical support in the preparation, implementation and finalisation of local calls and procedures, through a combination of field work and remote assistance. Direct benefit of the last cycle of this activity, which ended in 2025, was enjoyed by 2,527 citizens, including 856 women, which exceeded the project target values. In parallel, a pilot activity was implemented regarding youth participation in two LSGUs (Užice and Žabalj), where the participants developed and chose project proposals through a vote in schools. The selected proposals were funded from local budgets, which allowed the model to test, in practice, the applicability of participatory mechanisms in the submodel of “allocation of own funds” at the level of LCs and educational institutions. In 2025, the second cycle of support to local media ended; through 182 feature reports on local and national channels, it contributed to raising awareness among the citizens and increasing the visibility of the participatory practices. Media reports indicated increasing trust in local institutions and a greater level of preparedness of citizens to participate in the creation of local solutions. The activity has been implemented in line with the planned objectives and has contributed to a functional and sustainable establishment of participatory own-fund allocation model in partner LSGUs.
1.1.5.11: Elaboration and promotion of innovative e-models of citizen participation in the adoption of decisions on the allocation of own funds | Q1 2025 | MPALSG | Completed | 100% | In 2024, all activities for the improvement of the e-Consultation Portal were completed: They were implemented in cooperation with GIZ and the Public Policy Secretariat of the Republic of Serbia. The project was implemented in two stages; after the successful implementation of the first stage, the second stage was launched with the help of the MED Programme. In the second stage, all local self-government units (LSGUs) got the opportunity to publish their public policy documents on the Portal and conduct consultations with citizens. Once the evaluation was finished, the tender was awarded to eSmart Systems, which implemented the project responsibly. The Portal has been tested and is fully functional, and training for LSGU representatives has been organised on the premisses of the National Academy of Public Administration (NAPA) to ensure its efficient use. The training was organised in cooperation with the Public Policy Secretariat of the Republic of Serbia, and the participants acquired the necessary knowledge and skills for the use of the e-Consultations Portal as a mechanism for open and transparent consultations.
1.1.5.12: Establishment and capacity building for local good governance centres | Q4 2025 | MPALSG | Completed | 100% | In 2025, the training program for the implementation of good governance principles in practice was organised for 22 employees (13 women, 9 men) from 22 LSGUs. In addition, 25 employees from 25 LSGUs (14 women, 11 men) further advanced their skills and knowledge through additional training. A total of six LSGUs established an expert good governance centre, i.e, working group, in 2025. |  |  | The Programme will continue monitoring the operation of the already established, and establishment of new good governance centres until the end of June 2026.
.
Measure 1.1.6: Improvement of vertical and horizontal oversight in performing original and delegated tasks of the LSGUs
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The legal framework regulating the oversight function of the city/municipality assemblies was improved (reporting of executive bodies to the assembly, questions from councillors − interpellation, strengthening the position of working bodies − proposing draft acts, etc.) (0 − No, 1 − Yes) |  |  | 0.00 (2020) |  | 0.00 | -
Improved legal framework regulating the functioning of the administrative districts (strengthening the coordination role of the administrative districts and their supervisory function over the performance of local self-government tasks in the territorial units at the level of administrative districts) (0 − No, 1 − Yes) |  |  | 0.00 (2020) |  | 0.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.6.1: Establishing a Draft Law on amendments and additions of the Law on Local Self-Government put forth by the Working Group (improvement of the oversight function of the local assembly − provisions pertaining to executive bodies’ reporting to the assembly, introduction of interpellation, strengthening the position of the working bodies for proposing of Acts, introduction of LSGU obligation to make the legislation in force from their area of competence available in an electronic format, introduction of a second instance body for administrative proceedings within original competencies) and its submission to the Government for the purposes of establishing a Draft Law | Q4 2024 -> Q4 2025 | MPALSG | In progress | - | The working version of the Draft Law on amendments and additions to the Law on Local Self-Government was prepared in 2025. |  | The Working Group has not been formed. | Establishment of a Working Group for the purposes of drafting the law.
1.1.6.2: Preparation of the model local acts for the implementation of amendments and additions of the Law on Local Self-Government (LLG) regarding the strengthening of the oversight function of the assembly, strengthening the position of working bodies and introducing the obligation of publishing the LSGU legislation in force (rules of procedure for the assembly, model reports of executive bodies, model decision on the publication of the LSGU’s legal acts etc.) | Q2 2025 | MPALSG | Not commenced | - | .. |  | The precondition for the achievement of the activity is the amendment to the Law on Local Self-Government.
1.1.6.3: Implementation of the model local acts for the implementation of amendments and additions to the LLSG regarding the introduction of a second-instance decision-making body in the administrative proceedings (amendments and additions to the model statute, model procedure for the selection of the members of the second-instance body, rules of procedure for the second-instance body) | Q2 2025 | MPALSG | Not commenced | - | .. |  | The precondition for the achievement of the activity is the amendment to the Law on Local Self-Government.
1.1.6.4: Development and implementation of trainings for assembly secretaries to support the implementation of amendments and additions to the Law on Local Self-Government in the part pertaining to the improvement of municipal assembly functions | Q4 2025 | NAPA | Not commenced | - | The activity was not implemented in the envisaged period. |  | The process of amendments and additions of the Law on Local Self-Government has not been implemented, and that process was the prerequirement for the implementation of this activity. | In the working version of the Local Self-Government System Reform Programme 2026-2030, the activities on amendments and additions to the Law on Self-Government have been envisaged, and that will fulfil the precondition for the activities that support its implementation.
1.1.6.5: Development and implementation of the training programme for persons engaged in the work of the second-instance body in the administrative proceedings | Q4 2025 | MPALSG | Not commenced | - | The precondition for the achievement of the activity is the amendment to the Law on Local Self-Government.
1.1.6.6: Elaboration of the amendments and additions of the Law on Local Self-Government (defining the time limit for approval, opinion or adoption of the act by a state administration body, which is a part of the procedure implemented by the LSGU and the time limit for the submission of information upon request from LSGUs, which are in the competence of a state administration body, redefining and expanding the function of administrative districts, strengthening the coordination role of the administrative districts and their oversight function over the execution of the tasks by the local self-government and, in particular, their preventative and advisory function in the field of oversight implemented by the state bodies), and referral to the Government for the establishment of a Bill | Q4 2025 | MPALSG |  | - | There were no activities on the amendments of the Law on Public administration in 2025.
1.1.6.7: Development of a plan for the implementation of a new functional framework and capacity building in administrative districts for the implementation of new district functions and regional units of line ministries | Q4 2024 -> Q4 2025 | MPALSG |  | - | .. |  | The precondition for the achievement of the activity is the amendment to the Law on Public Administration.
.
Specific Objective 1.2: Improvement of local self-government financing system
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Share of LSG tax revenues in total tax revenues in the Republic of Serbia (%) |  |  | 10.12 (2020) |  | 12.24-12.3 | 10.5 | In 2025, the share of local self-government tax revenue in the total tax revenue of the Republic of Serbia is lower than expected, as local sources of taxation, primarily property tax and local taxes, have a limited fiscal potential and insufficient collection rate compared to the more dynamic and profitable tax forms at the level of the central government.
Share of capital expenditures in total expenditures of local self-government (%) |  |  | 15.54 (2019) |  | 17.41-17.5 | 15.8 | In 2025, the share of the capital expenditures in the total expenditures of local self-government units was lower than expected because the current expenditures for wages, social services and communal maintenance were given priority and have limited the space for investments, while at the same time, numerous projects were postponed or implemented in a narrower scope due to administrative procedures, insufficient readiness of the project documentation and limited access to funding sources.
Share of LSGUs which have adopted medium-term plans (%) |  |  | 0 (2020) |  | 36-40 | 6.2 | For the medium-term planning cycle in the period 2025-2027, only 9 LSGUs (of the referent value of 145 LSGUs) have adopted medium-term plans, which is a lower result compared to the previous cycles. This indicates the necessity to further support and invest additional efforts to address challenges in harmonising medium-term plans and linking them to the programme budgeting process on the local level.
.
Measure 1.2.1: Reform of local self-government funding system and support to fiscal decentralisation
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Reformed systemic legal framework (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | - | -
Share of property tax revenue in the total budget revenue of the LSG (%) |  |  | 15.80 (2019) |  | 17.50 | 15.90 | The share of property tax revenue in the local self-government budgets is lower than expected, due to a combination of poor tax base coverage, insufficient collection, low tax discipline and limited administrative capacities of local tax administrations. All these factors lead to the fact that property tax, despite formally being an own source of revenue for municipalities and cities, has a relatively modest fiscal significance in practice.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.1.1: Continued operation of the Commission for Local Self-Government Funding in line with its competence prescribed in the Law on LSG Funding | Q4 2025 -> Q4 2026 | MoF | In progress | - | The work of the Commission was relaunched in November 2021. It was agreed that a proposal for the improvement of the local self-government funding system be elaborated based on an analysis that was to be conducted by the Ministry of Finance. |  | Continued operation of the Commission for the Local Self-Government Funding has not yet been ensured as it is necessary to first look at all of the effects of the implemented fiscal consolidation measures and current activities on financial discipline strengthening in local self-government units, so that the work of the Commission would be based on stable and sustainable grounds. | Once a comprehensive view of the effects of the implemented fiscal consolidation measures has been formed and the degree of compliance with the guidelines from the Instruction on the elaboration of decisions on local self-government unit budgets has been determined, the continued work of the Commission for local self-government funding shall be ensured, to consider and propose measures for the improvement of the local self-government funding on sustainable grounds.
1.2.1.2: Improvement of the funding system in line with the findings of the local self-government funding system analysis (implementation and impacts of the systemic legal framework, structure of the revenues and expenditures of the LSGUs, planning and realisation of the revenues and expenditures, compliance of the LSGUs with MoF instructions) | Q4 2025 -> Q4 2027 | MoF | Not commenced | - | The Ministry of Finance elaborated an analysis of local self-government funding, based on which a proposal for the improvement of local government funding should be elaborated. |  | The local self-government financing system has not yet been improved in line with the analysis findings as it is necessary to first ensure a stable and predictable fiscal framework, including better financial discipline of local self-government units and impact analysis of the implemented measures, so that the proposed changes could be sustainable in medium- and long-term. | After the appropriate financial discipline level has been established in the LSGUs, a new meeting of the Commission will be called and proposals for the improvements to the local self-government funding system shall be considered.
1.2.1.3: Support to further capacity development of the local tax administration (formation of a network and exchange between the LTA units, implementation of yearly training programmes and workshops, advisory support, direct technical support to individual LSGUs etc.) | Q4 2025 | MoF | In progress | 100% | Three cycles of regional meetings were held for all LTAs in 2025 (SCTM’s LTA Network), in cooperation of SCTM (through the SDC programme) and the Programme “Accountable Local Finances and Citizen Inclusion” MED III (Helvetas), as follows: the first cycle in February 2025, with the topics: amendments and additions to the Law on Tax Procedure and Tax Administration (LTPTA) as well as the Law on Property Tax (LPT); amendments and additions to the Rulebook on standard tax return forms on the ascertained property tax i.e., for the determination of property tax. One-day regional meetings of the Network were held in Belgrade and Vrnjačka Banja, with the participation of 185 participants from 87 LSGUs. - second cycle in June 2025, with the topics of: Exchange of data between LTAs and other bodies (data exchange system on the e-Government portal; access to information of public importance and personal data protection). One-day regional meetings of the Network were held in Vrnjačka Banja and Belgrade, with the participation of 162 participants from 85 LSGUs. - third cycle in September 2025, with the topics: property tax audit and audit of the tax return forms PPI-1 One-day regional meetings of the Network were held in Kragujevac and Belgrade, with the participation of 157 participants from 77 LSGUs. In mid-December 2025, a meeting of the SCTM’s Network for LTAs was organised in two regional locations, with the topic of “Implementation of new and amended legislation in the work of LTAs and preparation for the elaboration of the annual tax assessment for 2025” One-day regional meetings of the Network were held in Vrnjačka Banja and Belgrade, with the participation of 160 participants from 89 LSGUs. In 2025, SCTM performed consultations with its members on the proposals for amendments and additions of the LTPTA. The consolidated list of suggestions was submitted to the MoF in the form of an initiative, and some of the proposals were accepted through amendments and additions to the LTPTA adopted at the beginning of December 2025. In addition, coordination with the LSGUs continued with regards to the Law on the Charges for the Use of Public Goods, and the consolidated proposals were submitted to the MoF within the consultative process in October 2025. |  | /. | Within its operation and provision of support to its members, the SCTM will continue LTA capacity building and advocating for LSG interests.
.
Measure 1.2.2: Support to LSGUs for the improvement of the budget planning process
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The average capacity of LSGUs for the implementation of the good governance principle in line with the good governance index in LSGU in the field of accountability (%) |  |  | 45.00 (2018) |  | 70.00 | 59.90 | At the end of 2025, performance in good governance was measured using the SCTM's Good Governance Index. The measurement indicated the growth of total LSGU capacity in the field of good governance. Still, somewhat less progress has been observed in the field of accountability.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.2.1: Providing general support to LSGs in the development of medium-term plans (advisory support to all LSGs, model and instructions development and exchange of information with all LSGs) | Q4 2025 | PPS | Completed | 100% | In 2025, advisory support for the development of medium-term plans was provided based on LSG requests. The SCTM organised the autumn cycle of seminars to support LSGs in elaborating budgets for 2026, which included the topics related to medium-term planing in LSGUs. Four regional seminars were organised, and one webinar, with 244 representatives from 89 LSGs taking part, within the Programme of the Swiss Development Cooperation “Partnership for Good Local Self-Government”.
1.2.2.2: Implementation of 10 support packages, to support municipalities in elaborating LSGU medium-term plans | Q4 2024 | PPS |  | - | ..
1.2.2.3: Implementation of 11 support packages, to support municipalities in the preparation of capital budgets | Q4 2024 | MoF | Completed | - | Through the EU Exchange 6 Programme, the SCTM finalised the support packages for the preparation of capital budgets in 11 beneficiary LSGUs in 2024, including the elaboration of the implementation report, using, as an example, one capital project included in the budget for 2024 in each beneficiary LSGU. Based on the experiences acquired during the implementation of support packages, guidelines were prepared with model materials for LSGUs for the implementation of the complete cycle of capital project (CP) management, for the capital projects not subject to the Regulation on CP (the projects of the assessed value below the budgetary threshold defined in the Regulation). In addition, in cooperation with the Ministry of Finance, the final versions of model documents were agreed, regarding the establishment and functioning of local Capital Investment Commissions (acting on the local CPs that are subject to the Regulation, i.e., with the estimated value exceeding 2 million euros), and were submitted to all LSGUs in mid-2024. |  | /.
1.2.2.4: Development, preparation and monitoring of the implementation of professional development for LSG employees in the domain of programme and capital budget preparation, and their harmonisation with local development planning (development of a medium-term plan of the LSGU and its interlinking with the programme and capital budget of the LSGU, gender-responsive and participatory budgeting) | Q4 2025 | NAPA | Completed | 100% | In 2025, the SCTM organised two trainings on Implementing the process of participatory budgeting, which was completed by 44 participants. SCTM: Using the calls directed to SCTM and in cooperation with the colleagues from NAPA, the plans for the following year are examined on an annual level, for the programme of professional development for the LSGU employees in the domain of programme and capital budget preparation and medium-term planning, which was also done in 2025. Despite the SCTM not implementing the targeted accredited training programmes in this domain in 2025, the current and LSG-relevant information on the topics of programme and capital budget preparation were presented through seminars and through the work of the SCTM Networks, as was also the case for other reporting activities for 2025. It is important to note that, the instructive materials (Manual) on capital project management on the local level were finalised through coordination of the MoF and SCTM, in the second half of 2025. This material, with any further amendments and additions to the Regulation on Capital Projects in line with the Concept of public investment policy prepared by the MoF, shall be relevant for the consideration of the improvement of professional development programmes for the LSGU employees during 2026. This is the Manual for the implementation of the Regulation on Capital Projects in Local Self-Governments, which includes the a step-by-step review (flowchart) with models of accompanying documents LSGs need for the implementation of the Regulation (available at: https://www.skgo.org/storage/app/uploads/public/175/515/816/1755158163_Prirucnik%20za%20primenu%20Uredbe%20o%20KP%20u%20LS%20sa%20prilozima.zip ).. |  |  | In the part that relates to the update of the professional development for LSGU employees, the activity is implemented every calender year in coordination with NAPA and the competent line institutions, and training delivery from this activity has also been envisaged in the working version of the Local Self-Government System Reform Programme for 2026-2030.
1.2.2.5: Consideration of the possibilities for modifying the programme budget structure to improve its alignment with the needs of developmental and public policies | Q4 2025 | MoF | In progress | 100% | In line with the agreements achieved during the elaboration of the AP LSGSRP for 2024-2025 and the approved Addendum within the EU Exchange 6 Programme, the SCTM finalised the proposals for possible changes in LSG programme budget structure to better align it with the needs of development and public policies (linking the development and medium-term planning with programme budgeting) in line with this activity. After coordination at the end of 2024 (in line with last year’s report), the final version of the analysis of medium-term planning alignment with programme budgeting on the local level was elaborated at the beginning of 2025, with recommendations for further improvement. The material was submitted to MoF and PPS for consideration, and towards the middle of the year, within the final report for EU Exchange 6, it was also submitted to all institutions and partners, members of the Programme Steering Committee. |  | /. | The prepared material can be useful as additional material for further consideration and consultations in steering the support to LSGs for improvement of the budget process implementation and for harmonisation with the MoF Instructions (the support envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030).
.
Measure 1.2.3: Improving local finance system transparency
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
A publicly accessible electronic system for presenting and monitoring the status of local budgets has been set up (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 1.00 | 0.00 | The possibility of a public electronic presentation for the local government budget within the System for Budget Preparation, Execution, Accounting and Reporting (SPIRI) is being considered.
Share of LSGUs which have publicly accessible budget portals (%) |  |  | 1.70 (2020) |  | 20.00 | 21.00 | The entered indicator value pertains to 36 LSGs (of 170 reference LSGs) with introduced public budget portals – the reporting value is the same as in 2024, at the end of the EU Exchange 6 Programme.
The share of LSGs that publish monthly reports (or cumulative monthly reports) on budget execution on their webpages (%) |  |  | 9.40 (2020) |  | 40.00 | 15.30 | This value was entered based on the local transparency index (LTI) maintained by Transparency Serbia (https://www.transparentnost.org.rs/sr/istraivanja-o-korupciji/lti). The data is based on the report for 2025, and the indicator is measured relative to the total number of LSGs (170). The indicator achievement level is higher than in the previous year, 2024 (12.4%). The results regarding the publication of the monthly reports on LSG budget execution are still very modest (considerably lower than the target value), but it is relevant to note, from the viewpoint of transparency, that the publication of six-month and nine-month reports on LSG budget execution is at a significantly higher level – 48.8% for 2025 (according to the same source).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.3.1: Establishment of a public electronic presentation of the local government budget (planning and execution of revenues and expenditures of the budget for each of the LSGs) | Q4 2024 -> Q4 2026 | MoF | Not commenced | - | The Ministry of Finance has included the local governments into the operation of the information systems SPIRI and Central Information System for the Calculation of Salaries/Compensation of Employees, Appointed and Elected Persons in the Public Sector (ISKRA). |  | It was ascertained that it was more effective to develop a public electronic presentation within the existing SPIRI system, than to build a new information system to allow for this. | Establishment of electronic presentations for local government budgets within the SPIRI will be considered, to be implemented by the end of the year.
1.2.3.2: Elaboration of 20 LSG budget portals | Q4 2024 | MoF |  | - | ..
1.2.3.3: Monitoring of the implementation of the programmes from the Good Governance field within the Sectoral Programme for Continual Professional Development of employees in LSGs | Q4 2025 | NAPA | Completed | 100% | In 2025, the SCTM held accredited training with the topic “The process of participatory budgeting”, in the form of two webinars (20 and 23 May), within the Programme Partnership for Good Local Self-Government. At the webinar held on 20 May 2021, 21 participants (19 women, 2 men) successfully completed the knowledge assessment, and the total number of attendees was 29 (26 women and 3 men). At the webinar held on 23 May, the test was passed by 12 participants (10 women, 2 men), of a total of 18 participants (15 women and 3 men). |  |  | The implementation of trainings from the scope of this activity was also envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030.
.
Measure 1.2.4: Measure 2.4: Intensive development of the public internal financial control (PIFC) at the local level
Institution in charge: MINISTRY OF FINANCE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
% of certified internal auditors in local self-government units (%) |  |  | 64.00 (2019) |  | 70.00 | - | The data for indicators at the level of measure 2.4 will become available following the annual reporting on FMC and internal audit activities for 2025.
The LSGUs that joined the reporting system on their FMC system (%) |  |  | 55.86 (2019) |  | 100.00 | - | The data for indicators at the level of measure 2.4 will become available following the annual reporting on FMC and internal audit activities for 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.4.1: Establishment and/or further development of the internal audit, financial management and control and managerial accountability functions at the local level, as well as PIFC reporting by LSGUs (advisory support, training, formation of networks of LGSs) | Q4 2025 | MoF | Completed | 100% | Within this activity, the horizontal support for LSGs was provided again in 2025, in coordination of the MoF/Central Harmonisation Unit (CHU) with partner programme RELOF 3 and SCTM (within the EU Exchange 6 Programme and the SDC's Programme Partnership for Good Local Self-Government). In addition to the continual interaction and advisory support upon LSG request, we would also emphasize the following groups of activities: - In February 2025, two one-day seminars were held for LSG employees on risk management within the FMC system. The seminars were held in Belgrade and Niš, with the participation of a total of 136 representatives from 41 LSGUs (the last cycle of FMC seminars within the EU Exchange 6 Programme); - In November and December 2025, regional workshops were organised for LSGs, also in the FMC domain, with emphasis on the delegation system, managerial accountability and implementation of the appropriate methodology (RACI methodology). Regional workshops were held in Niš, Vrnjačka Banja, Belgrade and Novi Sad, with a total of 87 participants from 45 LSGUs (supported by the Programme Partnership for Good Local Self-Government/SDC); - In terms of horizontal support to LSGs in the domain of internal audit, the activities in 2025 were largely dictated by the amendments and additions to the Law on the Budget System, adopted the previous year (2024), which pertained, among other things, to more precise rules for organisational positioning and operation of IA within LSGs. Hence, by mid-year, efforts were invested into modelling local implementation acts and additional guidelines for cities and municipalities in these matters. The prepared draft material − Guidelines with the Model Decision on Establishment of an IA Service − was presented and discussed at a meeting for the competent representatives of cities and municipalities held in June 2025 in Belgrade (a total of 85 participants from 50 LSGs participated). |  |  | Support for internal financial control at the local level in the period following 2025 is planned within the new Public Finance Management Reform Programme.
1.2.4.2: Direct support to LSGUs for the establishment and/or further development of internal audit and financial management and control functions | Q4 2024 | Selected LSGUs |  | - | ..
1.2.4.3: Capacity building in 10 LSGU systems in the domain of implementing external audit findings | Q3 2025 | Selected LSGUs | Completed | 100% | A total of 12 trainings were held for managers in the LSGU systems on actions to be taken in line with the external audit reports, with a total of 207 participants (trainings held in 10 LSGs − 131 participants; 2 regional trainings − 76 participants).
1.2.4.4: Introduction/improvement of internal audit in 10 LSGU systems including joint internal audit | Q3 2025 | Selected LSGUs | Completed | 100% | Two advanced trainings were held (master class) for internal auditors from LSGUs. In addition, mentor support in IA was provided to Raška and Mali Zvornik.
1.2.4.5: Introduction/improvement of the FMC in 10 LSG systems | Q3 2025 | Selected LSGUs | Completed | 100% | Support was provided for FMC introduction in 17 PEs from 6 LSGUs − Babušnica, Mali Zvornik, Novi Pazar, Raška, Žabalj and Zrenjanin. In addition, FMC introduction was supported in 11 institutions from 3 LSGUs − Babušnica, Mali Zvornik and Raška. The FMC system was fully established in 6 LSGU systems (in administrations, all PEs and all indirect budget beneficiaries (IBBs)): Babušnica, Mali Zvornik, Pirot, Raška, Žabalj and Zrenjanin. In addition to the support to 10 LSGUs implemented within the RELOF 3 project, direct expert support for FMC improvement was provided to 2 other LSGUs in 2025, in line with the interest shown and the resources available. These were the municipalities of Merošina and Ruma, with which the SCTM concluded Agreements on Cooperation for the improvement of the FMC system, in line with which the support was implemented by the end of 2025. LSGUs were supported through a combination of direct expert support and workshop format, in cooperation of SCTM and the RELOF 3 Project.
.
Specific Objective 1.3: Improvement of the organisation and capacities of the local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
LSGU capacity for human resources management in local administration (%) |  |  | 51 (2020) |  | 64-68 | 56.7 | Towards the end of 2025, the SCTM conducted a performance measurement for the HRM system in LSGUs, which was the first performance measurement since the introduction of professional competences for LSGU employees. In that sense, the index itself was updated, particularly the part relating to the new requirements in the domain of competences. Despite the continual project support to the HRM function since the introduction of the civil service system and the modern human resources management in the LSGUs, it is evident that progress in the capacities for this function is very slow. With constant and systemic challenges pertaining to human resources in LSG bodies, the change in the system since the introduction of professional competencies for civil servants should be seen as one of the key reasons of such decelerated growth of this particular indicator; it can objectively be expected that the results of the available support to LSGUs will only become more evident in the upcoming period. In addition, another factor affecting the result of performance measurement is the fact that the measurement in 2025 included about 40 LSGUs that had never been beneficiaries of any kind of direct technical assistance for HRM function improvement, which will be supported in its improvement in the upcoming period. The sample for the 2025 measurement included 93 LSGUs, of which 23 were cities (24.73%), 6 LSGUs were municipalities with over 50,000 population (6.45%), while the majority were municipalities below 50,000 population, 64 (68.82%).
Share of LSGUs which have established inter-municipal cooperation in the total number of LSGUs (%) |  |  | 27 (2020) |  | 34-43 | 62
.
Measure 1.3.1: Improving the human resources management function in local administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The LSGU capacity for human resources management in local administration (average value of the SCTM’s HRM index in select fields: human resources organisation and planning; filling vacant positions, assessing employee performance, disciplinary responsibility and appeals procedure, communication, ethics, values and organisational culture) (Index − composite indicators) |  |  | 58.00 (2020) |  | 75.00 | 64.70 | Towards the end of 2025 the SCTM conducted a performance measurement for the HRM system in LSGUs, which was the first performance measurement since the introduction of professional competences for LSGU employees. The previous measurement for this indicator, conducted in 2022, showed a value of about 70%, so that the decline in 2025 was surely caused by the novelties in the competence domain, as the LSGUs are only just working on introducing it, and by the fact that the index is, in itself, additionally demanding. In addition, another factor affecting the result of performance measurement is the fact that the measurement in 2025 included about 40 LSGUs that had never been beneficiaries of any kind of direct technical assistance for HRM function improvement, which will be supported in its improvement in the upcoming period. The sample for the 2025 measurement included 93 LSGUs, of which 23 were cities (24.73%), 6 LSGUs were municipalities with over 50,000 population (6.45%), while the majority were municipalities below 50,000 population, 64 (68.82%).
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.1.10: Monitoring the implementation of the regional accredited trainings on “Legislation and procedures in the employment process” for HRM employees and members of competition commissions | Q2 2024 | NAPA |  | - | ..
1.3.1.11: Monitoring the implementation of the regional accredited trainings on “Legislation and procedures in the employment process” for HRM employees and members of selection committees | Q2 2024 | NAPA |  | - | ..
1.3.1.12: Monitoring the implementation of the training programme on “The role and activities of human resources management units in implementing selection procedures and with regards to selection committees” | Q2 2024 | NAPA |  | - | ..
1.3.1.13: Monitoring the implementation of 9 regional accredited trainings on “Conducting competence-based interviews” for employees in LSGUs | Q1 2024 | NAPA |  | - | ..
.
Measure 1.3.2: Improvement of professional development for employees in LSGU bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The LSGU capacity for professional development in local administration (average value of the SCTM’s HRM index in select fields: professional development and employee training) (Index − composite indicators) |  |  | 30.00 (2020) |  | 65.00 | 35.30 | Despite the progress compared to the baseline, this result is evidently below the expected level at the end of the reporting period. Another factor affecting the result of performance measurement is the fact that the measurement in 2025 included about 40 LSGUs that had never been beneficiaries of any kind of direct technical assistance for HRM function improvement, which will be supported in its improvement in the upcoming period. The sample for the 2025 measurement included 93 LSGUs, of which 23 were cities (24.73%), 6 LSGUs were municipalities with over 50,000 population (6.45%), while the majority were municipalities below 50,000 population, 64 (68.82%). The trend for this indicator was initially more positive, so the previous measurement for 2022 resulted in the value of almost 50%. Still, bearing in mind the latest data, it can be said that there is a particular challenge within the HRM function pertaining to the capacity and status regarding professional development within LSGUs, which will be subject to additional analyses to find room for improvement in that field, in the future. Reports of the Professional Development Council for previous years are also reporting a decline in the number of special professional development programmes that the LSGUs are adopting, after previously having sent them to the Council for its opinion.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.2.11: Monitoring the implementation of e-training on professional development in LSGUs | Q4 2025 | NAPA | Not commenced | - | This activity has not been implemented in 2025, as the detailed support plan within the Project “EU for Human Resources Management in Local Self-Government − phase 3” calls for this activity to be implemented in the final stage of the project. The Project is being implemented from December 2024 to December 2028, and, in line with the project timeline. In addition to numerous other activities, it will also include the improvement and implementation of e-learning on the system of professional development in local self-governments. |  | Improvement and implementation of an e-learning programme on the professional development system in local self-governments − planned within the Project “EU for Human Resources Management in Local Self-Government − phase 3” (IPA 2024), will be implemented at a later date as confirmed in the project timeline.
.
Measure 1.3.3: Support to organisational and functional transformation of local self-government and harmonisation of organisational structures established by LSGUs for the exercise of their competences and tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Harmonisation of the organisational structure of the local administration (average ratio of basic and auxiliary functions in local administration) (%) |  |  | 0.60 (2020) |  | 1.00 | 0.00 | In 2025, no functional analysis was conducted as donor funds had not been secured.
Harmonisation of the organisational forms in LSGUs with the basic typology of organisational forms that the LSGUs can establish (%) |  |  | 0.00 (2020) |  | 45.00 | 0.00 | The precondition for the achievement of this indicator is the amendment to the Law on Local Self-Government.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.3.1: Elaboration of a Draft Law on amendments and additions to the Law on Local Self-Government by a working group, in order to regulate organisational units according to the nature of the tasks performed by local self-government units, and its referral to the Government to put forth as a Bill | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | The working version of the Draft Law on amendments and additions to the Law on Local Self-Government was prepared in 2025. |  | The Working Group has not been formed. | Establishment of a Working Group.
1.3.3.2: Elaboration of functional analyses in 15 LSGUs | Q4 2024 | MPALSG |  | - | ..
1.3.3.3: Implementing financial support (fund) for the application of functional organisational models in local administrations and technical support for model implementation | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.3.3.4: Elaboration of functional analyses to assess the achieved organisational and functional changes in pilot local administrations | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.3.3.5: Development of recommendations for the harmonisation of sectoral laws and bylaws with the basic types of organisational forms that LSGUs are allowed to establish | Q4 2024 | MPALSG |  | - | ..
1.3.3.6: Support to the transformation of organisational forms of LSGUs in line with the bylaws (elaboration of manuals and model local acts for the transformation of organisational forms, ensuring continual advisory support to LSGUs) | Q4 2024 -> Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.3.3.7: Conducting an enhancement opportunity analysis for the roles and responsibilities of LSGUs in the civil protection field, with the aim to build LSGU capacities in civil protection by forming general-purpose civil protection units and alert units in all LSGUs. | Q4 2024 | MoI |  | - | ..
.
Measure 1.3.4: Continued development of intermunicipal cooperation in exercising the competencies of local self-governments
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Established and functional national financial mechanism to support intermunicipal cooperation* (Number) |  |  | 4.00 (2020) |  | 28.00 | - | The indicator was not measured in 2025 as donor funds for the implementation had not been provided.
Improved basic and sectoral legal framework with a view to developing intramunicipal cooperation (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 0.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.4.1: Providing advisory (expert and technical) assistance to the LSGUs in the process of intramunicipal cooperation establishment and continued development of tools for its implementation (model intramunicipal agreements, guidelines for conclusion and the implementation of the intermunicipal cooperation (IMC) process, etc.) | Q4 2025 | MPALSG | Completed | 100% | Advisory support to the LSGUs in the process of establishing intramunicipal cooperation (IMC) is continually available, provided through SCTM. Of the activities in 2025, it is relevant to point out the promotion of the IMC mechanism as particularly applicable in the context of establishing the function of local ombudsmen. In that sense, the IMC potential was presented at the conference “Cooperation of local ombudsmen and city and municipality administrations”, held on 27-28.5.2025 in Vrnjačka Banja, organised in cooperation of SCTM and the Association of Ombudsmen in Serbia (AOS). Local ombudsmen, department heads and their associates took part in the conference, with a total of 62 taking part from 25 SCTM members. Furthermore, the topic of IMC was given additional attention at the conference entitled “Setting up intermunicipal cooperation with regards to ombudsmen − challenges and obstacles”, held on 3-4 October 2025 in Aranđelovac, organised by the local Ombudsman of Kragujevac. |  |  | Continued advisory support to cities and municipalities was also envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030.
1.3.4.2: Financial support to intermunicipal cooperation projects | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.3.4.3: Elaboration of a Draft Law on amendments and additions to the Law on Local Self-Government by a working group to regulate the possibility of introducing mandatory forms of IMC in the exercise of local self-government competences, and its referral to the Government to put forth as a Bill | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | The working version of the Draft Law on amendments and additions to the Law on Local Self-Government was prepared in 2025. |  | The Working Group has not been formed. | Establishment of a Working Group.
1.3.4.4: Harmonisation of sectoral legislation to intensify intermunicipal cooperation in special areas (Law on Public Enterprises, Law on Communal Services, Law on Passenger Transport, Law on Waters etc.) | Q4 2025 | MPALSG | Completed | - | The SCTM identified and analysed a whole set of sectoral legislation, wherein amendments of particular provisions could facilitate intermunicipal cooperation in different fields. In 2025, these findings were translated into amendments and initiatives have been prepared that will be referred to the competent state bodies. The following legislative acts were analysed from the viewpoint of IMC: Law on Public Enterprises; Law on Road Transport of Passengers; Law on the Rights of Veterans, Military Disabled Veterans, Civilian War Invalids and Members of Their Families; Law on Refugees; Law on Financial Support to Families with Children; Law on Expropriation; Regulation on Energy Vulnerable Customers.
1.3.4.5: Analysis and drafting of legislative measures and other administrative actions aimed at improving the role of the administrative district councils in encouraging intermunicipal cooperation | Q4 2024 | MPALSG |  | - | ..
1.3.4.6: Development of an online training on intermunicipal cooperation | Q4 2024 | Selected LSGUs |  | - | ..
.
Measure 1.3.5: Improvement of local self-government development planning system
Institution in charge: Public Policy Secretariat of the Republic of Serbia
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Share of LSGUs which have adopted development plans in the total number of LSGUs (%) |  |  | 4.10 (2020) |  | 80.00 | 83.50 | In 2025, 121 of 145 LSGUs have adopted development plans.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.5.1: Conducting consultations with the local government representatives and proposers of special legislation regulating sectoral planning documents at the local level, which are not in line with the Law on the Planning System and preparation of recommendations | Q1 2025 | PPS | In progress | - | As the foundation for the consultations on planning framework optimisation at the local level, an updated Compliance Review of Special Laws with the Law on the Planning System with recommendations was elaborated in in 2025, in cooperation with the SCTM. It was found that there were 22 laws prescribing the obligation of adopting public policy documents for the autonomous provinces and 25 laws for LSGUs, of which there were 17 special laws pertaining to autonomous provinces and 18 special laws pertaining to LSGUs that were not harmonised with the Law on the Planning System of the Republic of Serbia. The Regulation on the Methodology of Public Policy Documents Drafting (“Official Gazette of the RS” no. 20/25) came into force in March 2025, prescribing that an autonomous province, or an LSGU, in line with their competences and needs, shall decide which planning areas it shall adopt a strategy or programme on, or shall encompass in the medium-term plan. |  | Consultations for the optimisation of the planning framework at the local level were postponed, so that they would align with the commencement of activities on the planning framework optimisation at the national level, which was planned for 2026, with support from EU4PAR. | The PPS will encourage the proposers of special laws to consider the possibility of harmonising special laws in the part pertaining to mandatory public policy documents drafting at the local level.
1.3.5.2: Support to LSGUs for the drafting of Development Plans, monitoring and reporting (advisory support, instructions and ensuring coordination and exchange of experiences etc.) | Q4 2025 | PPS | Completed | 100% | Support was provided to LSGUs in the elaboration of development plans throughout 2025, as well as in monitoring of their implementation and reporting according to the LSGU requirements. In cooperation with the SCTM, the PPS prepared Guidelines for the elaboration of performance reports for LSGU development plans, based on the experiences from the development plan performance reporting piloting in three LSGUs, conducted by SCTM within EU Exchange 6 Programme. The guidelines were published on the PPS website and presented to cities and municipalities at regional seminars for LSGU development plans performance reporting, organised by SCTM/SDC, GIZ/SDC and PPS. In addition, the SCTM supported the municipality of Svrljig through its own funds in the drafting of the Development Plan Implementation Performance Report. The PPS prepared an Analysis of the integration of Agenda 2030 in the local development plans documents in Serbia, as well as an Analysis of the compliance of objectives, measures and indicators of AP Vojvodina development plans with the SDG indicators, with support from GIZ and SDC. These documents are available on the RSJP website.
1.3.5.3: Support to LSGUs in drafting/review of Development Plans (direct technical support of 8 LSGUs) | Q4 2024 | PPS |  | - | ..
1.3.5.4: Monitoring the implementation of the training programmes for the application of the planning system at local level, envisaged in the Sectoral continual professional development programme in the LSGUs | Q4 2025 | NAPA | Completed | 100% | Three one-day seminars were organised in November 2025 for reporting on the performance of LSGU development plans. Despite the initial plan to organise the trainings in an accredited format, in coordination between PPS, SCTM and GIZ/SDC project for Agenda 2030, it was decided to proceed with non-accredited seminars. After the publication of the Guidelines for the preparation of performance reports on the implementation of LSGU development plans, their presentation and trainings for LSG representatives in their implementation were the subject of the aforementioned regional seminars. A total of 81 participants from 46 LSGs and 2 regional development agencies took part in these seminars. |  |  | In the part that relates to the update of the professional development for LSGU employees, the activity is implemented every calender year in coordination with NAPA and the competent line institutions.
1.3.5.5: Promotion of a business information system for LSGUs (analytical service of LSGUs and analytical-reporting system of LSGUs) | Q4 2024 | PPS |  | - | ..
.
Specific Objective 1.4: Improvement of the quality and availability of services of local administration bodies, utility services and services of public institutions
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Established baseline values for improvement of user satisfaction with local services (0 - No, 1 - Yes) |  |  |  |  | 0 | 1 | The indicator was implemented in Q3 2025. The composite indicator was developed based on the Survey of citizen satisfaction with the services provided by LSGUs. This survey was implemented at the end of 2023, while its results and findings were published in June 2024. The value for the composite indicator was 17.64 of the maximum 35. The composite indicator comprises of overlapping data from three separately measured vectors of local administration: responsiveness, participation and efficiency.
.
Measure 1.4.1: Development and improvement of basic methodology and tools for monitoring the execution of local self-government competencies and tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The level of development of tasks in priority areas of local self-government was analysed (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 0.00 | -
The percentage of administrative functions from the Single Catalogue of Functions of LSGUs (functions of administrative bodies) performed by the LSGUs (Number) |  |  | 0.00 (2020) |  | - | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.1.1: Elaboration of a Draft Law on amendments and additions to the Law on Local Self-Government by a working group to develop new modalities of management of the process of delegating competencies to the local self-government units in line with the Constitution and the legal possibilities, and its referral to the Government to put forth as a Bill | Q3 2024 -> Q4 2025 | MPALSG | In progress | - | The working version of the Draft Law on amendments and additions to the Law on Local Self-Government was prepared in 2025. |  | The Working Group has not been formed. | Establishment of a Working Group.
1.4.1.2: Updating the list of competencies and functions at all levels of government and updating the Single Catalogue of Functions at the local level | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.4.1.3: Elaboration of an analysis − verification of the degree of established functions in priority areas from the single catalogue of functions, on a sample of 45 LSGUs | Q4 2024 | MPALSG |  | - | ..
1.4.1.4: Elaboration of an analysis of expenditures and capacities in priority areas of local self-government (financial, human, material etc.) for the performance of a selected sample of key competencies identified in the single catalogue of functions of LSGUs | Q4 2025 | MPALSG |  | - | The activity has not been implemented as no financial support from donors was secured.
.
Measure 1.4.2: Improvement of local self-government capacities for the provision of administrative services
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Share of LSGUs which have an established OSS (Number) |  |  | 14.00 (2020) |  | 39.00 | 70.00 | The number of established one-stop shops at the end of 2025 is 70 in total, with 5 OSSs opened in 2025.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.2.1: Support to the ministries in the census of administrative procedures delegated to the LSGUs in the Register of administrative procedures and support for LSGU capacity building for the use of the Register administrative procedures | Q4 2025 | PPS | Completed | 100% | Throughout 2025, the PPS implemented the following activities intended for LSGU capacity building for the use of RAP and publication of their own registers: 3 webinars supported by the SCTM with a total of 431 participants; 2 webinars supported by NAPA with 97 participants; 6 regional trainings with support from NAPA, held in NAPA regional centres, for 106 participants and direct collaboration and support in the work of 26 LSGUs, i.e., 260 participants. In addition, the SCTM provided expert and technical support to 16 LSGUs in the finalisation of the process for the census and publication of procedures on the RAP Portal.
1.4.2.3: Elaboration of an analysis of LSGU capacities for the introduction of e-government, with a view to form intermunicipal ICT centres for support/coordination/improvement of e-government | Q3 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.4.2.4: Support to piloting one intermunicipal ICT centre for e-government coordination and improvement | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.4.2.5: Support for the establishment of OSSs / integration of administrative procedures in 10 LSGUs | Q4 2025 | MPALSG | In progress | - | This support is being implemented through SCTM within the Partnership for Good Local Self-Government Programme (Swiss Development Cooperation). Activity implementation began in 2025, but will continue into 2026. In the first half of 2025, preparatory activities were conducted and the support package was determined in more detail; it was decided that the support would relate to the set-up of OSSs through the integration of procedures and increase of availability of services to vulnerable population categories, and that the support could encompass more than LSGUs (up to 12 LSGUs). Hence, in June 2025, the First Call was opened and 5 beneficiary LSGUs were selected; then, through the Second Call in September and October, another 7 beneficiary LSGUs were selected. The selected municipalities and cities were: Aleksinac, Svrljig, Petrovac na Mlavi, Vlasotince, Varvarin, Prokuplje, Jagodina, Kraljevo, Raška, Bosilegrad, Surdulica and Vladimirci. Introductory activities were performed by the end of the year, on the grounds of the Agreement on Cooperation between the SCTM and beneficiary LSGUs, including introductory visits. Effective provision of support will continue into 2026. |  |  | Continued support was also envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030.
1.4.2.6: Implementation of the support package for the improvement of efficiency of administrative services in five LSGUs | Q4 2025 | MPALSG | Completed | 100% | Within this activity, comprehensive technical and advisory support was provided in five local self-government units to improve the efficiency of administrative services. The beneficiaries were Arilje, Veliko Gradište, Ćuprija, Kosjerić and Temerin. The support encompassed the establishment of one-stop shops, harmonisation of administrative procedures with the requirements of the Registry of Administrative Procedures, work processes optimisation, improvement of the records and introduction of electronic office management, as well as enhancing transparency and capacities of the employees in info and service centres. As a result of this support, a total of 49 one-stop shops were established in all five municipalities. All municipalities adopted the Instruction on the method of conducting administrative procedures, while the procedures have been entered into the Registry of Administrative Procedures and published on the Portal in four municipalities. Electronic registry office was established in four local self-government units. Based on measurement results of the Good Governance Index of accountability and corruption prevention, the average value for the index at the level of the entire support package has increased by 38.73%.
1.4.2.7: Support in the establishment of youth offices at the level of all five LSGUs, autonomously or through IMC | Q4 2025 | Ministry of Tourism and Youth (MTY) | Not commenced | - | The Ministry is supporting the already established Youth Offices through financial support for the implementation of projects, based on public competitions, while the Ministry had not been supported in the previous year to open new youth offices as part of its activities.
1.4.2.8: Development of online trainings for LSG managers in the field of performance management and lines of accountability | Q4 2025 | NAPA | Completed | 100% | Training entitled Accountability in action − How to introduce the concept of managerial accountability in LSGU was developed within the project, in an online format, as part of the LSGU Managers Training Programme for 2026.
1.4.2.9: Support to managerial accountability strengthening in local self-government units | Q4 2025 | MPALSG | Completed | 100% | With support of the Project Reform of Local Finances in the Republic of Serbia (RELOF3), which started in 2023, a set of measures were implemented, aimed at capacity building of managers employed in local self-government units in the field of managerial accountability, good governance and performance management. The Project, funded by the Swiss Government, is being implemented in 10 local self-government units (Kragujevac, Novi Pazar, Pirot, Sremska Mitrovica, Užice, Zrenjanin, Babušnica, Mali Zvornik, Raška and Žabalj), which had also participated in the previous stages of the RELOF project. With the support from this Project, the performance plan for local self-government units was developed, and forms were elaborated to assess organisational performance, in order to measure it. Organisational performance measurement shall be used to re-engineer the work assessment of local self-government unit employees. Within this activity, three trainings were additionally developed and implemented, intended for the widest circle of employees and managers in LSGUs, namely: Accountability in action − how to introduce the concept of managerial accountability in LSGUs; Managing the local administration − from plans to results; and Efficient performance management for local self-government organisational units. These trainings are a part of the Training Programme for local self-government unit managers in 2026, at the National Academy of Public Administration.
.
Measure 1.4.3: Launching systemic reform of public utility activities and services
Institution in charge: MINISTRY OF CONSTRUCTION, TRANSPORT AND INFRASTRUCTURE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Improved basic legal framework in the field of communal activities and provision of public utility services (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 0.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.3.1: Referring the Draft Law on amendments and additions to the Law on Communal Services to the Government for consideration and establishment of a Bill | Q3 2024 | MCTI |  | - | ..
1.4.3.2: Development of a bylaw to regulate the methodology for communal services tariffs | Q4 2025 -> Q4 2026 | MCTI | In progress | - | At the beginning of 2025, the MCTI formed a Working Group for the elaboration of the aforementioned methodology, and its first meeting was held at the end of September. In line with the agreements made, support for the update of the existing methodology and for the innovation of the accompanying tool will be provided through SCTM (within the Partnership for Good Local Self-Government Programme/SDC) and the activity shall continue after the end of 2025. |  |  | Elaboration of a bylaw to regulate the methodology for communal services tariffs was envisaged for 2026 in the working version of the Local Self-Government System Reform Programme 2026-2030.
1.4.3.3: Preparation of model local acts for the implementation of the new law on communal services | Q2 2025 -> Q4 2026 | MCTI | In progress | - | With regards to this activity, some of the materials were prepared in 2025, namely, the Guidelines for the harmonisation of the Decision on Communal Services with the additions and amendments of the law. In addition to the above and in line with the agreement between the MCTI and the SCTM, development of a model programme for the construction and maintenance of communal infrastructure has also been planned, as well as modelling of an annual programme for the performance of communal services, which will follow in 2026. |  |  | The continued activities on the development of model local acts for the implementation of the Law on Communal Services was envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030.
1.4.3.4: Organisation of training for the implementation of the new law on communal services | Q2 2025 -> Q4 2026 | MCTI | In progress | - | Trainings for local self-governments for the implementation of the Law on Communal Services were postponed for 2026. |  | Since the planned bylaws and model acts had not been prepared in 2025 for LSGs for the implementation of the Law on Communal Services, the implementation of trainings that were supposed to include these materials was postponed for 2026. | Organisation of trainings for LSGUs on the implementation of the Law on Communal Services was envisaged in the working version of the Local Self-Government System Reform Programme 2026-2030.
1.4.3.5: Development of an electronic portal for reporting on the performance of communal services | Q4 2025 -> Q4 2026 | MCTI | In progress | - | Development of an electronic portal for reporting on the performance of communal services will contribute to the digitalisation of the processes, reducing human error in entering data, offering the option to view the current data and the possibility of refreshing the database in real time. |  | Elaboration of a standard form for reporting on the status of communal services | Development of a digital platform for reporting on the status of communal services.
1.4.3.6: Establishing a Commission to propose measures and define guidelines for the purposes of developing public utility enterprises | Q4 2024 -> Q4 2025 | MCTI | Completed | - | .. |  | A Commission to propose measures and define guidelines for the purposes of developing public utility enterprises has been established.
1.4.3.7: Establishing an obligation for all LSGUs to regularly evaluate the operation of local enterprises and report to the line ministry thereof, so that recommendations for the improvement of their operation can be made | Q4 2024 -> Q4 2025 -> Q4 2026 | Ministry of Economy (MoE) | In progress | - | The software for supervision over PUEs was upgraded through continual technical support. Work has started on a comprehensive analysis of the status of all enterprises established by LSGUs. Cooperation with the RELOF 3 Programme and SCTM continued (also within Swiss Development Cooperation) to form an analytical foundation to ascertain ownership policy and corporate governance for public enterprises and limited companies founded by the autonomous provinces and local self-government units, as well as by city municipalities, in line with the law. Namely, pursuant to Art. 49 of the Law on the Management of Companies Owned by the Republic of Serbia (LMCORS), which became effective in September 2024, an analysis process began, comprising several successive steps which, in addition to general reviews based on available data bases, also include in-depth review of the situation on a sample of 20 LSGUs, as well as the capital city and entities in AP Vojvodina. In 2025, the methodology for the evaluation was reconciled and the implementation of individual visits to the selected LSGUs began, and shall continue into early 2026. After that, the collected data will be processed and the situation analysis will be prepared, coordinated by the Ministry of Economy with the aforementioned partners. |  |  | The completion of the company situation analyses for all companies established by the LSGUs and software upgrade for the software for oversight over public enterprises owned by the state.
1.4.3.8: Trainings and mentoring for indirect budget beneficiaries from 10 LSGUs on improving managerial accountability | Q4 2025 | Ministry of Economy (MoE) | Completed | 100% | Nine trainings on managerial accountability and transparency in IBBs were held, with 99 participants, as well as two regional conferences with 34 participants. Support was also provided for FMC introduction in 11 IBBs from 3 LSGUs − Babušnica, Mali Zvornik and Raška. Training and mentoring for IBBs on the improvement of annual operational programs and operational reports were implemented in Babušnica, Kragujevac, Mali Zvornik, Novi Pazar and Zrenjanin (52 IBBs), as well as 3 trainings with 33 participants and LSGU mentoring in the improvement of the oversight function through the consolidation of the operational programmes and reports. |  |  | The completion of introduction of FMC to IBBs, support to increasing transparency and implementing ownership policy over IBBs
1.4.3.9: Trainings and mentoring for public and other enterprises founded by 10 LSGUs on improving managerial accountability | Q4 2025 | Ministry of Economy (MoE) | Completed | - | Forty trainings were held on managerial accountability: introduction to managerial accountability, delegating, ethics and integrity, and organisational accountability culture. A total of 111 participants were at the trainings.
1.4.3.10: Trainings and mentoring for public and other enterprises founded by 10 LSGUs on lines of accountability | Q4 2025 | Ministry of Economy (MoE) | Completed | 100% | Support was provided for FMC introduction in 17 PEs from 6 LSGUs − Babušnica, Mali Zvornik, Novi Pazar, Raška, Žabalj and Zrenjanin. Ten workshops were held on the use of external audit findings with a total of 131 participants. Two regional workshops were held for public enterprises and their founders, with a total of 76 participants. Support was provided through dialogue facilitation between public enterprises and their founders in 8 LSGUs for the topic of indicator establishment. |  |  | Trainings and mentoring for the improvement of certain lines of accountability that were identified as weak links through the measurement of the RELOF index in 2025.
1.4.3.11: Trainings and mentoring for public and other enterprises founded by 10 LSGUs on corporative management | Q4 2025 | Ministry of Economy (MoE) | Completed | - | The trainings on oversight over public enterprises on the local level were attended by 48 participants, while 13 were trained on the improvement of the quality of reporting through software use.
.
Measure 1.4.4: Improvement of local public services through local economic development and the implementation of the public private partnership model
Institution in charge: MINISTRY OF JUSTICE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Improved legal framework regulating the LSGU activities in the field of LED (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 0.00 | 1.00 | The Law on Investments was improved in the part related to the LSGU actions in the field of LED. It was established that, in addition to the Law on Local Self-Government, Art. 20 paragraph 1 item 7 and Art. 32 item 4), all valid investment attraction programs that were regulated by Government Regulations in force represented a sufficient instrument for attracting investments for the purposes of investments of local importance, which was the direct basis for the action of competent municipal/city bodies in the field of local economic development.
The percentage of the total number of LSGUs with adopted LED programmes (%) |  |  | 5.00 (2019) |  | 30.00 | 0.00 | The data is unavailable. Commission for state aid control does not have the requested data. In 2025, they stopped assessing the programmes as this was state aid according to the de minimis principle.
Percentage of LSGUs which have PPP projects (%) |  |  | 48.00 (2020) |  | 60.00 | 71.00 | The planned value has been achieved.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.4.1: Preparation of the draft amendments and additions to the Law on Investments in the part pertaining to the adoption of LED programmes and with a view to define a set of LSGU tasks in the field of LED, as well as a set of services LSGUs deliver to businesses | Q4 2025 | Ministry of Economy (MoE) | Abandoned | - | Supplementary amendments and additions to the Law on Investments were abandoned. The Law on Investments, Art. 20 regulates the local economic development unit. It is not necessary to further regulate the position and operation of this unit. In addition, the Law on Local Self-Government, Art. 20 and 32, regulates these issues. |  |  | The need for amendments to the Law on Investments, pertaining to the section on LED, shall be continually considered.
1.4.4.2: Support to LSGUs in implementing activities in the field of LED (advisory and mentor support, forming a network and exchange of knowledge, regional workshops, elaboration of instructional materials, expert support for the elaboration of LED programmes etc.) | Q4 2025 | Ministry of Economy (MoE) | In progress | 100% | A part of capacity building for this activity was implemented with support of SCTM through workshops held in September 2025, with the topic of “Incentivising LSG policy aimed at increasing the competitiveness of the local economy”, through exchange of LSG experiences, experiences of employers, as well as the scientific community, and through proposals on the directions for the improvement of the local incentives policy. Forming a network of LSGs continued through the meeting of the SCTM’s LED Network (also in September), with the presentation of current topics in this field, project opportunities, as well as support programmes for businesses offered by the Ministry of Economy. Within the TAIEX Programme, a training was held for LSGs in October with the topic of − short food supply chains, while two workshops were held in December, as part of the Swiss Development Cooperation, for the elaboration of a local planning document on employment. By mid-year, direct expert support within the SCTM’s SIDA project in the domain of women entrepreneurship ended in two LSGUs (Zrenjanin and Žagubica), while 4 new LSGUs were selected in the new competition (two for support in the domain of LED, one for social and one for women's entrepreneurship), in which the support package will continue to be implemented in 2026. |  |  | Through coordination of the competent stakeholders and in line with the available resources, support to cities and municipalities in implementing LED-related activities is provided continually.
1.4.4.3: Monitoring the implementation of trainings in the field of LED | Q4 2025 | NAPA | Completed | 100% | In line with the previously commenced activities and the plan for 2025, SCTM finalized the implementation of the accredited training “Applying the rules for state aid control at the local level” (two regional trainings in person and one online training with a total of 42 participants from 30 LSGs), and commenced the implementation of the accredited training on “Instruments for incentivising economic growth and supporting the economy” (regional trainings were held in December 2025 in Kragujevac and Niš, and the implementation shall continue into Q1 2026). |  |  | The continuation of trainings for cities and municipalities in the field of LED in line with further plans and available resources.
1.4.4.4: Drafting of the amendments and additions of the Law on PPP (in line with the needs and situational analysis) | Q4 2025 -> Q4 2026 | Ministry of Economy (MoE) | In progress | - | A working group was formed for the drafting of the amendments to the Law on PPP. The working group is working on harmonising the provisions of the Law with the EU Directives 23 and 24. |  |  | In 2026, the Bill for the Law on PPP will be prepared.
1.4.4.5: Support to LSGUs in the process of selecting private partners, implementation of potential PPP projects and control of their implementation (advisory and mentor support, direct technical support etc). | Q4 2025 | Ministry of Economy (MoE) | Completed | - | Meetings with LSGUs were held continually, to provide support in all stages of preparation and implementation of PPP projects. The Commission prepared a Manual for information purposes and to facilitate implementation of PPP projects. The Manual is publicly available on the website of the Commission for Public Private Partnership.
.
Measure 1.4.5: Measure 4.5: Elaboration of methodological and analytical tools for monitoring the LSGU services and the satisfaction of citizens with their quality
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Survey implemented on the availability and quality of priority services of the LSGU (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 1.00 | - | The indicator was not measured in 2025 as donor funds for the implementation had not been provided.
Survey conducted on the satisfaction of the citizens with services (0 - No, 1 - Yes) |  |  | 0.00 (2020) |  | 1.00 | - | The indicator was not measured in 2025 as donor funds for the implementation had not been provided.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.5.1: Conducting a survey and measuring availability and quality of priority LSGU services | Q4 2025 | MPALSG | Not commenced | - | The activity has not been implemented as no financial support from donors was secured.
1.4.5.2: Conducting a survey of citizen satisfaction with LSGU services | Q3 2024 | MPALSG |  | - | ..
1.4.5.3: Development of a methodology to measure the quality and availability of LSGU services in the domain of personal status of the citizens with guidelines for the improvement of the position of vulnerable population categories and survey of the satisfaction of these population groups with the services delivered | Q4 2024 | MPALSG |  | - | ..