## All activities export 1
The annual report on the implementation of the Action Plan for 2025, for: |  |  |  |  | Action Plan for the Implementation of the e-Government Development Programme in the Republic of Serbia for the period 2023–2025
Coordinating and reporting institution: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document the Action Plan pertains to: |  |  |  |  | e-Government Development Programme in the Republic of Serbia for the period 2023–2025 with the Action Plan for its implementation
General Objective 1: Development of an efficient and user-oriented administration in a digital environment
Document proposed by: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Overall result achieved by Serbia from the EU report on the comparison of e-Governments: eGovernment Benchmark Report (%) |  |  | 48.6 (2022) |  | 59 | -
.
Specific Objective 1.1: e-Government infrastructure development and ensuring interoperability
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of the state administration bodies, AP and LSGU bodies keeping their registers and other software solutions in the state centres for data storage and management (Number) |  |  | 36 (2022) |  | 60 | 60
The number of bodies taking over data from the Central Population Register, Real Estate Cadastre, Business Registers Agency and the Address Register via the Government Service Bus (Number) |  |  | 435 (2022) |  | 520 | 568 | Integration of the CPR and BRA through the Registry Office has encompassed more than 400 bodies.
The percentage of healthcare institutions connected to the Unified Information and Communication Network for e-Government (%) |  |  | 0 (2022) |  | 11 | 11
.
Measure 1.1.1: Upgrade of the State Data Storage and Management Centres* in Belgrade and Kragujevac
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of registers and other software solutions managed in state centres for data management and storage (Number) |  |  | 83.00 (2022) |  | 120.00 | 280.00 | This number does not include the software solutions managed in state centres for data management and storage through the colocation service. The colocation service is used by 21 bodies.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.1.1: Equipping of the Data Centre Kragujevac with ICT equipment | Q3 2023 | ITE | Completed | 100% | .. |  |  | A new phase has started, with the deadline for completion in Q2 2027, so the equipping will continue.
1.1.1.2: Upgrade to the cloud platform in the Data Centre Kragujevac | Q4 2023 | ITE | Completed | - | .. |  |  | Upgrade to the cloud platform will continue, but at the moment work is being done on migrating software solutions from the bodies to the cloud.
1.1.1.3: Implementation of the Network Operation Centre (NOC) system to the entire UIC | Q4 2024 | ITE | Completed | - | .. |  |  | The implementation of the system has been completed and the Office plans to expand and increase the capacity of the NOC system in the upcoming period, for which the funds from the budget have been planned. The activity is scheduled in the AP for the period 2026–2030.
1.1.1.4: Construction of the Facility 3 of the Data Centre Kragujevac | Q4 2025 -> Q3 2027 | ITE | In progress | 100% | The works on the first three phases of construction of facilities have been completed. Currently, installation works are being performed on facilities of phase 1 and 2, while in phase 3, the final construction works are in progress and the installation works shall continue once the construction is complete. |  | Deviation from the previously defined plan arose from the circumstances that were impossible to predict in the planning stages. To mitigate the consequences of this deviation, the work dynamic was adapted and the activities were reorganised, to ensure continuity of works and the implementation of the project within the revised time limits. | Deviation from the previously defined plan arose from the circumstances that were impossible to predict in the planning stages. To mitigate the consequences of this deviation, the work dynamic was adapted and the activities were reorganised, to ensure continuity of works and the implementation of the project within the revised time limits.
1.1.1.5: Migration of software systems of the bodies to the cloud (data centres) | Q4 2025 -> Q4 2030 | ITE | In progress | 100% | The activity is continual. In 2025, 22 software solutions were migrated to the cloud. |  |  | The new time limit for completion has been set for Q4 2028.
1.1.1.6: Integration of healthcare institutions to the Unified ICT Network of state bodies | Q4 2025 -> Q4 2028 | ITE | In progress | 100% | A total of 28 integrations of healthcare institutions into the Unified ICT Network of state bodies have been completed. |  |  | The new time limit for completion has been set for Q4 2028.
.
Measure 1.1.2: Improvement of the electronic processing by authorities through the use of the eID system, the Registry Office, e-Payments, e-Delivery and e-Archives
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of bodies** conducting all their office operations exclusively via the Registry Office (Number) |  |  | 0.00 (2022) |  | 400.00 | 432.00 | A total of 432 instances for the Registry Office system have been established. However, based on the available data, less than 200 bodies use the system actively in their everyday work. There are no precise data on the number of bodies performing office operations exclusively through the Registry Office, bearing in mind that a combined method of operation is frequently used in practice, which encompasses parallel use of electronic and traditional procedures.
The number of bodies with their existing software solutions connected to the Registry Office and the e-Archives (Number) |  |  | 0.00 (2022) |  | 10.00 | 10.00 | More than 10 integrations of the existing software solutions with the Registry Office system have been performed. However, the exact number of organs whose production solutions are integrated with the Registry Office and e-Archives cannot be precisely defined, since the bodies are not submitting notifications on moving their integrated systems into production environment. The only data available is the data on bodies to which technical parameters for integration have been issued.
The number of state administration bodies using collaboration services (Number) |  |  | 21.00 (2022) |  | 30.00 | 33.00 | In the Action Plan, what is written for this indicator is: the unit of measure and nature − Number − Higher values are PREFERABLE. Why it is showing its status as red − we believe it to be an error within the system!!
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.2.1: Improvement of the functions of the "Pay on the e-Government Portal" system (for collecting payments on all fees or charges that are paid, within a single transaction, for the provision of one service, charging only one transaction fee | Q3 2023 | ITE | Completed | - | ..
1.1.2.2: Issuance of certificates on facts that are subject to official records in line with the time limits for the creation of technical and human resources conditions − stage I: Establishment of an information system “VOJEVID” (principal design and software − the module for Military Service Obligation), provision of hardware and network infrastructure | Q3 2023 | MoD | Completed | - | ..
1.1.2.3: Establishment of the e-Archives | Q4 2023 -> Q4 2024 -> Q2 2025 | ITE | Completed | - | Activity was completed in Q3 2025.
1.1.2.4: Issuance of certificates on facts that are subject to official records in line with the time limits for the creation of technical and human resources conditions − stage II: Establishment of software − the module for labour and material obligations | Q3 2024 | MoD | Completed | - | ..
1.1.2.5: Drafting the amendments to the Law on e-Government for the purposes of harmonisation with the EU Directive 2019/1024 | Q4 2025 | MPALSG | In progress | - | ..
1.1.2.6: Issuance of certificates on facts that are subject to official records in line with the time limits for the creation of technical and human resources conditions − stage III: Development of an application for the issuance of certificates for the e-Government Portal and its connectivity with the databases of state bodies | Q4 2025 | MoD | Completed | - | ..
1.1.2.7: Promotional and educational activities within the administration for the purposes of revoking the obligation of submitting proof of payment for clients in the procedures conducted using the system for e-Payment | Q4 2025 | ITE | Completed | - | ..
.
Measure 1.1.3: Establishing new and upgrading existing Registers and electronic records to support the e-Government development
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of established and upgraded electronic records (registers) (Number) |  |  | 35.00 (2022) |  | 40.00 | 37.00 | There has been a change in priorities. Instead of developing new records/registers, the priorities were: Development of electronic services, connecting the existing records, automatic data exchange.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.3.1: Establishing and developing the geodetic-cadastral IS (GCIS) Development of an integrated system for the real estate cadastre and the registration of rights − ISREC | Q4 2023 | RGA | In progress | 39.81% | “All funds allocated within the Second Real Estate Management Project (REMP 2) for the implementation of development activities and the implementation of the solution of an integrated ISREC in the selected SREC for 2025, were utilized in line with the agreed time limits and the required quality of works and results. Ending with 2025, the solution for the integrated ISREC has been implemented in 66 local self-government units (LSGUs): -2 LSGUs in 2021 (Savski Venac and Sopot); - 3 LSGUs in 2022 (Stari Grad, Rakovica and Vračar); - 17 LSGU in 2023 (Beočin, Novi Sad 1, Novi Sad 2, Novi Sad 3, Sremski Karlovci, Voždovac, Mladenovac, Čukarica, Novi Beograd, Obrenovac, Palilula, Zemun, Zvezdara, Surčin, Grocka, Barajevo and Lazarevac), - 19 LSGUs in 2024 (Doljevac, Gadžin Han, Niš, Ljig, Aleksinac, Ražanj, Merošina, Ub, Titel, Srbobran, Bečej, Temerin, Žabalj, Svrljig, Kragujevac, Aranđelovac, Topola, Rača and Knić), and - 25 LSGUs in 2025 (Novi Pazar, Tutin, Raška, Lajkovac, Leskovac, Medveđa, Lebane, Crna trava, Vlasotince, Bojnik, Pirot, Babušnica, Bela Palanka, Dimitrovgrad, Prokuplje, Žitorađa, Blace, Kuršumlija, Vranje, Bosilegrad, Trgovište, Surdulica, Bujanovac, Preševo and Vladičin Han)." |  |  | As the REMP 2 project implementation continues, funded by a World Bank loan, the implementation of the developed solution for the integrated ISREC will continue throughout the territory of the Republic of Serbia, in all remaining cities and municipalities.
1.1.3.2: Establishing a system for electronic registration in status registers of the BRA (replacement of the CORE system for the procedure of registration, migration of the existing and implementation of new registers, integration with other e-Government systems and improvement of interoperability) | Q4 2024 -> Q4 2025 | BRA | Completed | - | ..
1.1.3.3: Improvement of the geospatial data distribution system − GeoSerbia 2.0 | Q4 2023 | RGA | Completed | - | ..
1.1.3.4: Establishment of a Metaregister to ensure interoperability in e-Government | Q2 2024 -> Q4 2025 -> Q4 2026 | ITE | In progress | - | ..
1.1.3.5: Establishment of an external support system for the social protection system (CALL DESK for social protection) | Q4 2024 -> Q1 2026 | Ministry of Labour, Employment, Veteran and Social Affairs (MOLEVSA) | In progress | 60% | Public procurement was initiated and the contract was signed in December 2024. In 2025, all activities from the contract were implemented according to plan. |  | There were no deviations in implementation. | The implementation of the activities from the contract ends on 20 February 2026.
1.1.3.6: Upgrade of the Social Card register | Q4 2024 -> Q1 2026 | Ministry of Labour, Employment, Veteran and Social Affairs (MOLEVSA) | Not commenced | - | This activity was not implemented. |  | Ministry of Finance did not grant the approval for the usage of funds allocated in the Law on the Budget for 2025 for this activity. The Law on the Budget for 2026 plans these funds. | The new time limit is Q4 2028.
1.1.3.7: Improvement of the IS for social protection SOPIS | Q4 2024 -> Q4 2026 | Ministry of Labour, Employment, Veteran and Social Affairs (MOLEVSA) | In progress | 80% | Public procurement was initiated and the contract was signed in December 2024. In 2025, all activities from the contract were implemented according to plan. |  | There were no deviations in implementation. | The implementation of the activities from the contract ends on 30 November 2026.
1.1.3.8: e-Space | Q4 2025 -> Q4 2026 | MCTI | In progress | - | Amendments to the Law on Planning and Construction from 2025, Article 201 supplemented with a provision in paragraph 5, stating: “The Government shall more closely regulate the manner and time limits for the exchange of documentation and submissions in the procedures for the preparation, coordination and monitoring of the drafting of planning documents, as well as the format in which the conditions shall be submitted (e-Space).” This provides the legal grounds for the adoption of a bylaw for the purposes of regulating the conditions and manner of monitoring the status regarding spatial planning, as well as reporting thereof. |  | The lack of the legal grounds and bylaw. The legal grounds provided for the adoption of a bylaw for the purposes of regulating the conditions and manner of monitoring the status regarding spatial planning, as well as reporting thereof. | Article 166g of the Law on Planning and Construction prescribes that the Agency for Spatial and Urban Planning shall, inter alia, establish and maintain the e-Space for the purposes of preparation, coordination and monitoring of the drafting of spatial and urban planning documents.
1.1.3.9: Digitalisation of two registers defined based on the previously implemented analysis that will ascertain the priority for the digitalisation of basic registers | Q1 2025 | ITE | Abandoned | 100% | .. |  | The activity was abandoned. | This has been reported on since 2024.
1.1.3.10: Upgrade to the IS in child and family services | Q4 2025 | MOLEVSA | Not commenced | - | This activity was not implemented. |  | The approval of the Ministry of Finance was not granted. | Launching a new one-year contract for 2026. The new time limit is Q4 2026.
1.1.3.11: Upgrade to the IS in the system for the protection of veterans and persons with disability | Q4 2025 | Ministry of Labour, Employment, Veteran and Social Affairs (MOLEVSA) | Not commenced | - | This activity was not implemented. |  | There was no need to upgrade the system in 2025. | Launching a new one-year contract for 2026. The new time limit is Q4 2026.
1.1.3.12: Establishing an IS for the residential social welfare institutions | Q4 2025 -> Q2 2026 | Ministry of Labour, Employment, Veteran and Social Affairs (MOLEVSA) | Completed | 100% | Public procurement was initiated and the contract was signed in October 2024. In 2025, all activities from the contract were implemented according to plan. |  | There were no deviations in implementation. | The implementation of the activities from the contract was completed on 01 June 2025.
1.1.3.13: Establishing and developing the geodetic-cadastral IS (GCIS) IS for the cadastre of infrastructure and underground facilities (software) | Q4 2025 | RGA | In progress | 3.681% | In 2024, the activities on the establishment of an IS for the utility cadastre were completed; this is a subsystem of the future cadastre of infrastructure and underground facilities. As the implementation of the project REMP 2 continues, funded by a World Bank loan, the activities on the establishment of an IS for infrastructure facilities shall continue, as the second subsystem of the future IS for the cadastre of infrastructure and underground facilities. |  |  | As the project implementation continues, funded by a World Bank loan, REMP 2, the implementation of the developed solution for the integrated ISREC will continue throughout the territory of the Republic of Serbia, in all remaining cities and municipalities.
1.1.3.14: Development of the Disaster Risk Register | Q4 2025 | RGA | Completed | - | All funds allocated in 2025 for the implementation of development activities and the implementation of the solution of the Disaster Risk Register were utilized by the RGA in line with the agreed time limits and the required quality of works and results. |  |  | To continue the initiated activities on the implementation of the GCIS, which is of strategic importance for the Republic of Serbia, the RGA will continue the activities of development and implementation of the IS for the cadastre of infrastructure and underground facilities as part of the project REMP 2, funded through a World Bank loan. Specifically, in 2026, procurement will be conducted for the service of development of a solution for the IS for infrastructure facilities.
1.1.3.15: Establishing and developing the geodetic-cadastral IS (GCIS) IS for land consolidation | Q4 2024 | RGA | Not commenced | - | The commencement of activities on setting up the IS for land consolidation (specifically, the information system and control module) requires the adoption of the Law on Land Consolidation, which has been planned for June 2026 in the Reform Agenda (Reform 1.3.1. Improvement of competitiveness of the agriculture sector). Once this Law is adopted, it is expected that activities on the development and implementation of an IS for land consolidation will commence in Q3 2026. |  |  | To continue with the already started activities on the implementation of the GCIS, RGA has been approved a new project, funded under a World Bank loan (REMP 2), where one of the components will be the development and implementation of the IS for land consolidation.
1.1.3.16: Establishing the smart infrastructure for geospatial data (Smart SDI) | Q4 2025 | RGA | In progress | 100% | All funds approved for the implementation of activities planned for 2025 have been utilized in line with the annual plan, approved by SIDA. |  |  | Due to the importance of the Project SmartSDI results for the sustainable development of the Republic of Serbia, as well as the concrete results achieved by the project partners RGA and Lantmateriet in the first three years of the Project (2023-2025), SIDA has approved the extension of funding for new project activities in the amount of SEK 15,000,000 by mid-2027. The new project activities, which will be agreed at the beginning of 2026, will ensure full sustainability of the results achieved in the first three years of the project, on one hand, and, on the other hand, will allow for further development of the geospatial data as a reliable foundation for the adoption of reality-adapted decisions aimed at sustainable development of the Republic of Serbia.
1.1.3.17: Digitalisation of the register of agricultural holdings (the development of the software solution e-Agrar) | Q4 2025 | Ministry of Agriculture, Forestry and Water Management (MAFWM) | Completed | - | ..
1.1.3.18: Establishing and developing the geodetic-cadastral IS (GCIS) IS for mass real estate appraisal and determination of the price index for residential real estate | Q4 2025 | RGA | Not commenced | - | Technical specification of the IS for mass real estate appraisal was supplemented, so that it includes the implementation of new technologies and methods in the process of elaborating a mass appraisal model. The new databases, that have become available for use in the meantime, have also been taken into consideration. |  |  | To continue the initiated activities on the implementation of the GCIS within the REMP 2 project funded by the World Bank, which includes, as it constituent part, the IS for mass real estate appraisal, in the upcoming period the RGA will commence the process of developing the IS for mass real estate appraisal and calculation of the individual index for all residential real estate, but also a composite index for residential real estate.
.
Measure 1.1.4: Improvement of public administration human capacities for the set up and use of information technologies in e-government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of employees in IT officer positions (Number) |  |  | 6,402.00 (2022) |  | 6,700.00 | - | CROCO is charged with reporting.
The number of employees trained to work in the digital environment, per body and local self-government unit in which they are employed (Number) |  |  | 1,200.00 (2022) |  | 1,200.00 | - | MDULS_Internal records on the certificates issued/certificates on completed trainings
Number of employees in IT officer positions in state administration bodies (Number) |  |  | 610.00 (2022) |  | 680.00 | - | CROCO is charged with reporting.
Number of employees in IT officer positions in local self-government bodies (Number) |  |  | 470.00 (2022) |  | 510.00 | - | CROCO is charged with reporting.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.4.1: Capacity building for the organisational unit charged with e-government tasks related to the implementation of the Law on e-Government | Q1 2024 | MPALSG | Not commenced | - | ..
1.1.4.2: Implementing trainings for public administration civil servants regarding the definition of procedures and control over the implementation of acts on information security, prescribed in the act on security and personal data protection, prescribed in the Law on Personal Data Protection; | Q1 2024 | ITE | Completed | 100% | ..
1.1.4.3: Elaboration of a public administration needs assessment for IT profiles and staff for IT project management and a proposal of a scheme for sustainable management of this staff within public administration and LSGUs | Q2 2025 | MPALSG | Completed | - | ..
1.1.4.4: Development of online courses in the field of e-Government for civil servants and LSGU employees on NAPA’s platform | Q4 2025 | NAPA | Completed | - | In 2025, the online training on Electronic Office Operations was completed by 142 participants, and the e-Archives training by 35 participants. The following online trainings were published, with a view to strengthen e-Government: Working and communicating with service users, Electronic business communication, New technologies, Strategic e-Government planning and transformation and re-engineering of business processes, Whole of Government approach (WoG), Digital transformation, e-Government and change management, Training on raising the awareness of civil servants on information security, Metaregister and interoperability, which were completed by 1,487 participants. In the curriculum for 2026, the following online trainings for civil servants and LSGU employees have been developed: Creating and providing quality public services and Higher quality of public services by way of digitalisation.
1.1.4.5: Implementation of trainings for employees tasked with providing electronic services within the public administration, through the use of software solutions | Q4 2025 -> Q2 2026 | ITE | Completed | 100% | The activity was completed in Q4 2025.
1.1.4.6: Elaboration of the LSGU capacity building analysis for the introduction of e-Government, for the purposes of establishing ICT service/coordination centres to support the establishment and improvement of e-Government for local self-government groups | Q4 2025 | MPALSG | Not commenced | - | ..
.
Measure 1.1.5: Improvement of information security and standards
Institution in charge: MINISTRY OF INFORMATION AND TELECOMMUNICATIONS
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The percentage of bodies with an established and functional information security system and complying with information security standards (ISO 27001 and ISO 2000, with an adopted Information Security Act), relative to the number of regular and unscheduled inspections performed in a calendar year (%) |  |  | 95.00 (2022) |  | 100.00 | 100.00
The percentage of bodies with an established and functional information security system and complying with information security standards (adopted Disaster Recovery Plan), relative to the number of regular and unscheduled inspections performed in a calendar year (%) |  |  | 90.00 (2022) |  | 100.00 | 100.00
Number of employees who have gone through cyber exercises in the public administration (Number) |  |  | 150.00 (2022) |  | 240.00 | 240.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.1.5.1: Informing the public on the use of electronic identification schemes and qualified trust services in electronic administrative procedures | Q4 2023 | Ministry of Information and Telecommunications (MIT) | Completed | - | The Ministry of Information and Telecommunications has implemented activities aimed at informing the public on the use of the electronic identification schemes and qualified trust services in electronic administrative procedures. Through media campaigns, presentations and trainings, the citizens and businesses were acquainted with practical advantages of these services, facilitating access to electronic administrative services with increased security and reliability of communication with public administration bodies.
1.1.5.2: Acquainting and educating civil servants on legislation and their practical application in the field of electronic identification schemes and qualified trust services. | Q4 2023 | MIT | Completed | - | The Ministry of Information and Telecommunications has implemented a set of activities aimed at informing the public on the opportunities and advantages of the use of electronic identification schemes and qualified trust services in electronic administrative procedures. Through media campaigns, public presentations and trainings, the citizens and businesses were acquainted with practical applications of these services, with the aim of facilitating access to electronic services, as well as increasing security and reliability of electronic communication with public administration bodies.
1.1.5.3: Setting up a Security Operation Centre (SOC) and Computer Emergency Response Team (CERT) | Q4 2023 | ITE | Completed | - | ..
1.1.5.4: Establishing a laboratory for information security and training of centres in ICT information security testing | Q4 2025 | ITE | Abandoned | - | The activity was abandoned. |  | The activity was abandoned. | The activity was abandoned.
1.1.5.5: Elaboration of a plan and organisation of cyber exercises to improve ICT security | Q4 2025 | ITE | Abandoned | - | The activity was abandoned. |  | The activity was abandoned. | The activity was abandoned.
1.1.5.6: Capacity building of the PA and LSG bodies in drafting and implementing a compliance verification plan for compliance with the information security act | Q4 2025 | MIT | Completed | - | The Ministry of Information and Telecommunications, in cooperation with the National Academy for Public Administration, organised a set of educational activities aimed at acquainting civil servants with the relevant legislation and practical aspects of implementing electronic identification schemes and qualified trust services. Through workshops, trainings and seminars, the employees gained knowledge that allows for a reliable and safe implementation of electronic services, as well as compliance with the relevant national and European legislation.
.
Specific Objective 1.2: Improvement of legal certainty in the use of e-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of acts arising from the work of inspection bodies, within the software solution e-Inspector, submitted to the Unique Electronic Mailbox of e-Government users (Number) |  |  | 17,532 (2022) |  | 35,000 | - | The credentials for access to the test and production environment of the new e-Delivery were assigned on 6 December 2023, which marked the formal start of activities on moving the e-Inspector system to the new environment. The new e-Delivery was uploaded to the production environment in May 2024, and has been available for use since then. However, e-Delivery was initiated or attempted from the e-Inspector system in only 25 cases, and was not completed successfully in any of them. The most likely reason has been identified to be the fact that the entities that were subject to inspections were not registered on the e-Government, which is the basic prerequirement for electronic delivery. In the meantime, the API of e-Delivery was modified, which required changes to the e-Inspector as well, so that e-Delivery could work. Despite the e-Inspector system being technically linked to the mailbox of the competent Ministry of Public Administration and Local Self-Government (MPALSG), actual senders in this system are different ministries and inspections that operate within them. This complexity of the roles has created the need for additional harmonisation regarding the labelling of senders and assigning competencies within the new delivery system. In parallel to this process, certain inspections began using the new Registry Office, which was already integrated with the new mailbox. This circumstance led to additional complications in setting up the single operational position on the method of using e-Delivery within the e-Inspector, being that one part of the system was acting according to new rules, while others were still transitioning. The initial idea was that the inspectors would only work inside the e-Inspector system, with the system automatically sending data to the e-Registry Office. However, in the course of business analysis workshops for the needs of integration of e-Inspector – e-Registry Office, it was concluded that additional services need to be developed on the e-Registry Office side, so that the integration could function in line with the needs and specific characteristics of users of the e-Inspector system. Information on the implemented web services on the Registry Office side was submitted in the week from 19 to 23 May 2025, meaning that the technical preconditions to continue with the functional integration had been met. In that context, it needs to be analysed from which system e-Delivery will be used.
The percentage of cases handled exclusively in the electronic format, relative to the total number of cases in the calendar year (%) |  |  | 0 (2022) |  | 40 | -
.
Measure 1.2.1: Ensure efficient protection of the rights of e-government users
Institution in charge: MINISTRY OF JUSTICE
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Further expansion of the opportunities for electronic initiation and conduct of court proceedings for the parties, through the e-Court application (Number) |  |  | 1.00 (2022) |  | 108.00 | -
Percentage of judges in Serbia who had undergone training at the Judicial Academy for work in a digital environment relative to the total number of judges in Serbia (%) |  |  | 15.00 (2022) |  | 38-40.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.1.1: Sustainable development of the register of wills – Judicial professions | Q4 2025 | MoJ | In progress | - | The Ministry of Justice is planning to continue working on the improvements of this system. Easier work for users, secure access, and transparent announcements.
1.2.1.2: Sustainable development of the register of Register of Granted and Revoked Powers of Attorney – Judicial professions | Q4 2025 | MoJ | In progress | - | The Ministry of Justice is planning to continue working on the improvements of this system. Easier work for users, secure access, and transparent announcements.
1.2.1.3: Development and implementation of the Super SAPS application for case management | Q4 2025 | MoJ | Not commenced | - | The Ministry of Justice is expecting an official response of the EU Delegation on the status of the Contract.
1.2.1.4: Sustainable development of the e-Auction platform for electronic sale of moveable and immoveable assets through public auction in the enforcement proceedings (fully electronic process of public auction announcement, submitting bids (bidding), closing the sale and automatic determination of the best offer) | Q4 2025 | MoJ | Completed | - | The Ministry of Justice is planning to continue working on the improvements of this system. Easier work for users, secure access, and transparent announcements.
1.2.1.5: Sustainable development of the ESB infrastructure platform for system interoperability, e-Court and maintenance and upgrade to the centralised court electronic notice board | Q4 2025 | MoJ | In progress | - | The Ministry of Justice is planning to continue working on the improvements of this system. Easier work for users, secure access, and transparent announcements.
1.2.1.6: Conducting training for judiciary employees on working with electronic files and data in electronic records, as well as with the systems used to conduct electronic procedures | Q4 2025 | Judicial Academy (JA) |  | - | ..
1.2.1.7: Implementing digital literacy-relevant trainings in line with the Judicial Academy annual training programme | Q4 2025 | JA |  | - | ..
.
Measure 1.2.2: Improvement of delivery within e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of bodies using the Unique Electronic Mailbox for delivery (Number) |  |  | 13.00 (2022) |  | 285-300.00 | 240.00 | A miscalculation occurred. The calculation included the bodies that formally did have access, but that did not realistically perform delivery. Once the records were “cleaned”, the number of active bodies decreased.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.2.2.1: Organising trainings for all employees in administration to work with the Registry Office in line with the Law on e-Government and the Regulation on office operations | Q4 2025 | NAPA | Completed | - | The online training on Electronic Office Operations, which is always accessible, was completed by 142 participants, and the e-Archives training by 35 participants. In addition, 9 consultations were organised for successful implementation of the knowledge acquired on the online training for Electronic Office Operations, attended by 283 participants.
1.2.2.2: Promotion of electronic conduct of administrative procedures, including e-Delivery for citizens and businesses | Q4 2024 -> Q4 2025 | ITE | Completed | 100% | The activity "Communication and citizen user experience" ended with the completion of the procurement contract, in December 2024. |  |  | The activity "Communication and citizen user experience" encompassed the promotion of all services to citizens, available at the e-Government website.
1.2.2.3: Integration of the e-Inspector software with the e-Registry Office | Q4 2025 -> Q3 2026 | ITE | In progress | 100% | The issued production credentials have been saved in the integration system. The integration is not ready for full production usage yet. |  | The integration is in the testing stage, meaning that the production usage is postponed until all planned test activities have been completed. | Verification of test integration has been planned, as well as providing the appropriate technical documentation as a precondition for moving to production operation.
1.2.2.4: Cloud – signing and logging in using a certificate | Q4 2025 | ITE | Completed | 100% | In 2024, a total of 87,326 qualified cloud-based electronic certificates were activated.
1.2.2.5: Bringing the Contact Centre down to the level of inspections within LSGUs | Q4 2025 | MPALSG | Completed | - | ..
.
Specific Objective 1.3: Increasing the availability of e-government to citizens and businesses through the improvement of user services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
EU e-Government Benchmark – Key Enablers dimension (Index points) |  |  | 54 (2022) |  | 61-65 | 63 | The European benchmark no longer includes the Republic of Serbia, but the target values for 2025 had already been reached in 2024, in the last issue of the report that did include Serbia (https://digital-strategy.ec.europa.eu/en/library/digital-decade-2024-egovernment-benchmark).
EU e-Government benchmark – User Centricity dimension (Index points) |  |  | 77 (2022) |  | 87 | 89 | The European benchmark no longer includes the Republic of Serbia, but the target values for 2025 had already been exceeded in 2024, in the last issue of the report that did include Serbia (https://digital-strategy.ec.europa.eu/en/library/digital-decade-2024-egovernment-benchmark).
Local e-Government development index (LEI) (Number) |  |  | 25 (2022) |  | 39-40 | 40 | No recent data is available, but according to the available data, the target value for 2025 had already been reached in 2023, when the e-Government development at the local level was evaluated to be at medium development, with 40% of the LEI index criteria met https://lei.rs/vesti/2;
.
Measure 1.3.1: Improvement of the e-Government Portal and other software solutions
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of filings submitted using the e-Government Portal in one calendar year (Number) |  |  | 1,215,767.00 (2022) |  | 2,310,000-2,200,000.00 | 2,300,000.00
Percentage of compliance of the e-Government Portal features with the accessibility standards (%) |  |  | 75.00 (2022) |  | 98-100.00 | 100.00 | June 2025, the testing according to the UN e-Government Survey
The number of services delivered through the e-Government Portal in one calendar year (Number) |  |  | 210.00 (2022) |  | 218.5-230.00 | 255.00 | Calculated cumulatively
The percentage of users that rate their user experience for the services on the e-Government portal as positive (%) |  |  | 0.00 (2022) |  | 47.5-50.00 | 90.00 | Results of the independent research for 2023: 90% of satisfied citizens and 93% of users from the business sector; the Global Market Research and Public Polling Agency IPSOS implemented a survey at the beginning of 2023 on the functionality and visits to the e-Government Portal among citizens and businesses as active users. The survey determined how informed citizens and businesses were, as two different categories of subjects, on the services offered by the e-Government Portal, i.e., to what extent they were using them. As many as 90% of citizens with a user account and 93% of representatives of the business sector were satisfied with the last service delivered to them through the e-Government Portal. IPSOS implemented this public poll among citizens and businesses in Serbia on the e-Government Portal within the EDGE Project (Enabling Digital Governance), being implemented for the needs of the Office for Information Technologies and e-Government, funded by the World Bank.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.1.1: Establishment of a user experience measuring mechanism on the e-Government Portal | Q2 2023 | ITE | Completed | - | ..
1.3.1.2: Redesign of the Portal to allow for assessments – collecting user experiences and recognising the needs of end users | Q2 2024 | ITE | In progress | - | ..
1.3.1.3: Connecting other authentication systems (Tax Administration, BRA, CROSO, judicial portals and other state administration body systems, but also systems used in the business sector, e.g., banks) with the Identity Management System (identity federation) | Q3 2025 -> Q4 2030 | ITE | In progress | 100% | By the end of 2025, a total of 87 systems of different state bodies and other relevant institutions were connected with the single log in system, i.e., the Identity Management System (identity federation). |  | The activity is, by its nature, continual and cannot be strictly defined in terms of time limits, bearing in mind that new systems are constantly being connected and the integrations have to be adapted. Periodic status reports are defined as the measure of implementation, instead of a fixed completion date. | Integration of new systems with the single login system is planned to continue, with regular monitoring and recording of the number of interconnected systems in pre-specified time reference points.
.
Measure 1.3.2: Providing support to e-Government users
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of services with customer support via a Contact Centre (Number) |  |  | 250.00 (2022) |  | 332.5-350.00 | 255.00 | Support through the Contact Centre has been provided for all existing services on the e-Government Portal. In addition, the Contact Centre provides support to the users who are logging into other systems (e-Invoice, My e-Class Register, e-Agrar...) using their accounts on the eID portal. The value is calculated as cumulative. Note: A technical error has been made, the target value should have matched the indicator 1.3.2 and then the status would not have been red. This is because, however many services are offered on the Portal, that is the number of services supported by the Contact Centre.
The number of user tickets processed by the Contact Centre (Number) |  |  | 432,143.00 (2022) |  | 570,000-600,000.00 | 796,209.00 | The number of tickets processed is cumulative: 680,129.00 (2024)+116,080.00 (2025)=796.209,00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.2.1: Improvement of all Contact Centre capacities to support citizens and businesses and introduction of new communication channels (telephone, Viber, WhatsApp) | Q4 2024 -> Q4 2025 | ITE | Completed | - | Activity was completed in Q3 2025.
1.3.2.2: Development of a methodology for measuring user satisfaction with electronic public services | Q4 2024 | ITE | Completed | - | ..
1.3.2.3: Establishment of a service quality measurement mechanism on the e-Government Portal | Q4 2024 | ITE | Completed | - | ..
1.3.2.4: Ensuring the functionality of the e-Government Portal for monitoring case status via the Registry Office service | Q4 2025 | ITE | Completed | 100% | The service was launched into production in May 2024.
.
Measure 1.3.3: Affirmation of e-government (raising awareness among public servants and citizens on the importance of digitalisation and strengthening trust in electronic services)
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The total number of registered users at the Electronic Identification Portal (eid.gov.rs) (Number) |  |  | 1,405,460.00 (2022) |  | 3,325,000-3,500,000.00 | 2,783,615.00 | The database was “cleansed”: inactive accounts (not used for a long time), test accounts, double user accounts for the same person. The number of users has decreased, however, the database quality has improved.
Number of parameters for the ConsentID mobile phone app issued (number of users registered using the high reliability scheme) (Number) |  |  | 24,280.00 (2022) |  | 71,250-75,000.00 | 1,427,420.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.3.3.1: Promotion of e-Government services | Q3 2023 | ITE | Completed | - | ..
1.3.3.2: Elaboration and implementation of change management methodologies in the field of e-Government | Q4 2025 | ITE | Completed | 100% | ..
1.3.3.3: Promotion of e-Seal | Q4 2025 | MPALSG | In progress | - | ..
1.3.3.4: Promotion of e-Signature | Q4 2025 | MIT | Completed | - | Ministry of Information and Telecommunications implemented a whole set of activities in 2025 aimed at promoting the electronic signature and its wider application in the private sector. Special care was given to getting the users better acquainted with electronic services, as well as to raising awareness on the safe and legal use of the electronic signature. At the same time, the process of adopting a new Law on the Electronic Document, Electronic Identification and Trust Services in Electronic Operations, that is being harmonised with the latest EIDAS2 regulations of the European Union, creating the legal and technical basis for even broader use of the electronic signature in all sectors.
1.3.3.5: Promotion of the Registry Office | Q4 2025 | ITE | Completed | 100% | Promotional activities have been implemented since 2024, after the launch of the service.
.
Specific Objective 1.4: Data opening in Public Administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of resources available on the Open Data Portal (Number) |  |  | 5,995 (2022) |  | 7,600-8,000 | 6,565 | The planned indicator value was not achieved, as the upgrade and technical update process was conducted for the Open Data Portal. Within these activities, the data that were no longer valid, complete or relevant were removed, meaning that over 1,200 resources were deleted from the Portal. Although it had been originally planned to have the number of available resources in the range between 7,600 and 8,000, the current number of 6,564 resources is the result of a meticulous database clean-up, aimed at ensuring a higher quality, accuracy and reliability of published data. This approach is aimed at ensuring that the data available to citizens and other users be up-to-date, valid and usable, in line with the open data principle and good administration practice.
The number of visits to the Open Data Portal (Number) |  |  | 285,795 (2022) |  | 360,000-400,000 | 378,941
.
Measure 1.4.1: Enforcing the implementation of the legislative framework for open data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of public administration bodies* that share/publish open data on the Open Data Portal (Number) |  |  | 83.00 (2022) |  | 123.5-130.00 | 156.00
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.1.1: Drafting the methodology and standards for data opening with the definition of priority data sets | Q4 2023 | ITE | Abandoned | - | The activity was abandoned. |  | According to EU Regulation 2023/138, additional methodology and standards for data opening, with precise definition of priority data sets, is not necessary. The Regulation clearly prescribes high-value data sets, together with detailed information on their formats and granulation. This Regulation provides comprehensive guidelines and specifications that encompass the necessary information on priority data sets, eliminating the need for additional efforts in defining standards. This approach ensures consistency with regulatory requirements and preserves the resources that would otherwise be spent.
1.4.1.2: Elaboration of the Draft amendments to the Regulation on the Open Data Portal for the purposes of harmonisation with the EU Directive 219/1024 on reuse of data and for the purposes of closer regulation of the obligation to open data in line with the methodology, introduction of a data officer in all institutions | Q1 2025 | MPALSG | In progress | - | ..
1.4.1.3: Establishment and support to the Working Group for the coordination of the open data ecosystem expansion, opening of the public administration data, monitoring the implementation and providing support to institutions in data opening | Q4 2025 | ITE | Completed | 100% | New members of the Working Group were selected, and a meeting was held. At the meeting, new members were introduced, priority activities in the upcoming period were discussed, including the support to institutions in the process of data opening, progress monitoring and the improvement of coordination between different stakeholders in the open data ecosystem. |  |  | Concrete steps were agreed upon for further development and improvement of data access.
1.4.1.4: Implementing trainings for employees regarding data opening in Public Administration | Q4 2025 | NAPA | Completed | - | The training for Data Opening was organised 3 times with 72 participants. In the General Training Programme for civil servants for 2026, new trainings have been envisaged: Opening and administering institutional accounts on the Open Data Portal and Management of open data, expected to be implemented in 2026.
1.4.1.5: Improvement of the Open Data Portal software solution with a view to improving the user experience | Q4 2025 | ITE | Completed | - | .. |  |  | Although this activity was formally implemented, in the upcoming period it will be necessary to define the Open Data Portal upgrade as a continual activity. Since the Open Data Portal is a dynamic platform based on continually updated data, regular maintenance and upgrades to the back-end infrastructure must be provided, as well as continual development of new functions. The purpose of these activities is to improve system stability, speed of operation and reliability, as well as to ensure further improvement of the user interface and user experience. Improvement of the search, filtering and data viewing mechanisms have a particular significance, as that provides user with an easier and more efficient way to find relevant open data sets. Easier access to data has a direct impact, leading to more intensive and improved data use, which contributes to higher portal visibility and greater economic impacts of the open data. Bearing this in mind, in the future implementation steps, it is recommended that the upgrade to the Open Data Portal software solution be treated as a permanent and strategic process, which will enable the portal to remain technically modern, functional and adapted to the needs of different user groups.
1.4.1.6: Building human resources capacities (number and skills) at ITE in the organisational unit charged with open data | Q4 2025 -> Q4 2026 | ITE | In progress | - | The capacity building activity with regards to open data started once the necessary organisational and spatial conditions had been met, bearing in mind that the new office of the Office for IT and e-Government officially opened on 7 October 2025. Afterwards, the needs assessment ensued, as well as defining employee profiles, their future tasks, and identifying key knowledge and skills needed to work in the field of open data. Final steps in the selection procedure for new employees are under way. |  | The timeline for the activities has shifted since the move to the new business premises of the Office for IT and e-Government had previously shifted, leading to delays in establishing full organisational capacities. To overcome the the resulting delay, once the office had moved into the new building, the process of defining staffing needs and preparing structured on-boarding and training for new employees was immediately launched as a priority. | The selection of new employees and their admission into a structured on-boarding process, that will last from six months to a year, so that they would acquire the necessary competences for autonomous performance of tasks, is planned to be completed. Once the training is complete, new employees will be integrated into the open data team within the Open Data Hub, which will ensure sustainable strengthening of institutional capacities and further development of the open data ecosystem in the Republic of Serbia.
.
Measure 1.4.2: Support to open data use
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND E-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
The number of hackatons, datatons, open data weeks and open data challenges organised in a calendar year (Number) |  |  | 10.00 (2022) |  | 24.75-25.00 | 25.00 | In the previous calendar year, over 25 different events, workshops and trainings were organised to promote open data. This did not include only hackatons and datatons, but all other activities contributing to the expansion of the open data ecosystem, encouraging understanding and practical use of data in public, private and civil sector.
The number of bodies** that were supported in opening and/or reuse of open data (Number) |  |  | 28.00 (2022) |  | 61.38-62.00 | 139.00 | In the previous calendar year, the support to opening and/or reuse of open data was provided to a large number of institutions from the public and private sector. This data represents an approximate number, since the cooperation was also established with other institutions that were not individually included in this list.
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.2.1: Providing support to open data users for projects based on open data reuse and promotion (civil society organisations, institutions of higher education, media, scientific and research community, start-up community etc.) | Q4 2025 | ITE | Completed | - | The activity of supporting open data users was successfully completed in Q4 2025. During this period, the support was provided to a total of 70 central level bodies and institutions, including 63 district public prosecutor’s offices, the Ministry of Justice, Ministry of Labour, Employment, Veteran and Social Affairs, Ministry of Domestic and Foreign Trade, National Employment Service, Business Registers Agency, Environmental Protection Agency, and State Audit Institution. |  |  | Continual support to open data users is a continuous activity that is significant for capacity building of institutions, local self-governments and the private sector, as well as for encouraging the practical use of data and expansion of the open data ecosystem in the Republic of Serbia. The activity of providing support to open data users was successfully completed in Q4 2025. During this period, the support was provided to a total of 70 central level bodies and institutions, including 63 district public prosecutor’s offices, the Ministry of Justice, Ministry of Labour, Employment, Veteran and Social Affairs, Ministry of Domestic and Foreign Trade, National Employment Service, Business Registers Agency, Environmental Protection Agency, and State Audit Institution.
1.4.2.2: Implementing activities within the Open Data Challenge | Q4 2025 | ITE | Completed | - | ..
1.4.2.3: Implementing activities within the Open Data Week | Q4 2025 -> Q4 2026 | ITE | In progress | - | ..
1.4.2.4: Organising trainings on opening and reuse of data (for the public, private, civil, academic and media sector) | Q4 2025 | ITE | Completed | - | The activity of holding trainings for data opening and reuse was successfully completed in Q4 2025. The trainings were organised for the public sector, women entrepreneurs, the media, academic community, civil society and local self-government units (LSGU), which allowed for practical understanding and application of open data in operations, public service management and public service improvement. The organised trainings contributed to capacity building of different stakeholders and to strengthening the open data ecosystem in the Republic of Serbia. |  |  | Bearing in mind the significance and value of these trainings for data opening and reuse, these activities will continue in the future as well. Continued trainings will ensure constant capacity building for the public, private, academic and civil sector, as well as for the local self-government units, and will encourage the expansion and active use of the open data ecosystem in the Republic of Serbia.
1.4.2.5: Implementing promotional activities (Blog “Wednesday – a day for Open Data”, social media campaigns etc.) | Q4 2025 | ITE | Completed | - | Promotional activities in the field of open data were successfully implemented through several communication channels, including the social networks, Open Data Hub (ODH) and the official website of the Office for IT and e-Government. In December 2025, the topic of open data raised great public interest, so it was communicated actively every day through the media, news and features, significantly contributing to increasing the visibility of open data and getting the wider audiences engaged. |  |  | This is a continual process that is always ongoing and it is necessary for the development and expansion of the open data system, as well as for better understanding and use of open data by the public and the institutions.
1.4.2.6: Opening the Open Data Hub In “Ložionica” (after construction) | Q4 2025 -> Q4 2026 | ITE | In progress | - | In the building of “Ložionica”, an AI district has been set up as a spatial and organisational framework for the development of innovations, artificial intelligence and digital services, within which the Open Data Hub has been envisaged. The new building of the Office for IT and e-Government officially commenced operations on 7 October 2025, which provided basic infrastructural and organisational preconditions for further implementation of this project. |  | Full operational launch of the Open Data Hub depends on the reinforcement of human resources, i.e., on the selection and training of new employees. Bearing in mind the need for adequately trained and specialized staff, the timeline for the set up of the Hub has been adapted to the realistic possibilities of staffing. To mitigate the discrepancy, the planned process of employment and training of young employees is under way, with a defined programme for basic and specialised trainings in the field of open data. | It was planned that the newly hired employees start working in Q1 2026, together with the necessary trainings. Following the process of on-boarding and acquisition of the necessary competencies, it is expected that the team will become fully operational. Opening and fully functional operation of the Open Data Hub within the AI District in “Ložionica” has been planned for Q3 2026, when all staffing and organisational conditions will have been met for its unhindered operation and contribution to the development of the open data ecosystem in the Republic of Serbia.
1.4.2.7: Support to state administration bodies in the process of data opening through mentorship, technical assistance and targeted trainings based on the needs of individual bodies | Q4 2025 -> Q4 2026 | ITE | In progress | - | During the reporting period, within the activity 1.4.2.7 – Support to state administration bodies in the process of data opening through mentorship, technical assistance and targeted trainings based on the needs of individual bodies, comprehensive support was provided to a large number of institutions from the public and private sector. The support was implemented through different operational forms, including organised in-person and online trainings, themed workshops, individual mentor meetings, as well as continual technical assistance in the processes of preparing, publishing and reuse of open data. Activities were adapted to specific needs of individual bodies and institutions, contributing to strengthening of their capacities and improvement of the published data quality. During the year, support was provided to at least 139 institutions and organisations, including central level bodies and institutions, local self-government units and private sector entities, noting that the actual coverage was much wider since the activities were implemented with other institutions as well, but were not individually recorded. |  |  | Despite planned activities having been successfully implemented, this type of support is a process that requires continual work, regular monitoring and further institutional capacity building, bearing in mind the dynamic nature of the regulatory and technological environment, as well as constantly growing needs for high-quality standardized open data.
.
Measure 1.4.3: Introducing the “Smart City Concept”
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator name |  |  | Baseline value and year |  | Target value for 2025 | Achieved value in 2025 | Note
Number of LSGUs which were analysed with regards to their readiness to implement the “Smart City” concept (Number) |  |  | 0.00 (2022) |  | 1.00 | -
.
Activity | Deadline -> New deadline | Institution in charge | Status | Funds utilization (%) | Progress explanation |  | Reasons for deviation and measures undertaken | Future steps for implementation
1.4.3.1: Elaboration of an analysis of the possible manner of establishing smart cities and their interconnection within a network (cloud structure) with a proposal for implementation | Q2 2023 | MPALSG | Completed | - | ..
1.4.3.2: Implementing at least two pilot projects for the application of the smart city concept (bearing in mind cultural, regional and other specificities) | Q2 2023 | MPALSG | Completed | - | ..
1.4.3.3: Legislating the “Smart City” concept and prescribing the legal grounds for the adoption of a methodology to define the criteria for smart city development | Q4 2025 | MPALSG | In progress | - | ..
1.4.3.4: Elaboration of control panels and/or solutions for smart decision-making based on open data at the level of LSGUs | Q4 2025 | ITE | Abandoned | - | Funds for implementation have not been secured.